## Buyout Process Checklist
Table 4.14: Buyout Process Checklist (page 26)
Project Number: ________________________________________________________________________________
Project Name: ________________________________________________________________________________
Location: ________________________________________________________________________________
Project Manager: ________________________________________________________________________________
Start Date: ________________________________________________________________________________
BUYOUT PROCESS CHECKLIST FOR PRE-CONSTRUCTION PLANNING
ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES
19. Request and/or review subcontractor/supplier/vendor prices and qualifications.
☐ |  | 1 | Request subcontractor/supplier/vendor pricing if it was not requested or received during the bidding stage.
☐ |  | 2 | Compare actual subcontractor/supplier/vendor scope of work with the scope identified in the subcontractor/supplier/vendor bid submission.
☐ |  | 3 | Evaluate the subcontractor/supplier/vendor qualifications.
☐ |  | 4 | Compare pricing and qualifications among the subcontractors/suppliers/vendors.
20. Negotiate pricing and contract conditions and select subcontractors/suppliers/vendors.
☐ |  | 1 | Discuss potential cost savings with potential subcontractors/suppliers/vendors.
☐ |  | 2 | Review the contract or purchase order terms and conditions with potential subcontractors/suppliers/vendors prior to award.
☐ |  | 3 | Select all successful subcontractors/suppliers/vendors, and issue a letter of intent (if necessary).
21. Develop and issue purchase orders and contracts for materials and equipment.
☐ |  | 1 | Develop the purchase orders or contracts for subcontractors/suppliers/vendors.
☐ |  | 2 | Process and issue the purchase orders or subcontracts.
22. Order long-lead-time materials and equipment.
☐ |  | 1 | Compare the sequence, schedule and materials/equipment to identify long-lead-time items.
☐ |  | 2 | Negotiate and issue purchase orders and subcontracts for long-lead time items before negotiating standard purchase orders and subcontracts.
☐ |  | 3 | Issue a letter of intent or purchase order immediately to release long-lead-time items for order and delivery.
23. Request submittals, cut sheets and shop drawings.
☐ |  | 1 | Upon issuing the contract document, the subcontractor/supplier/vendor should be requested to assemble and submit samples, cut sheets or shop drawings.
☐ |  | 2 | Identify a deadline by which the submittals, cut sheets, and shop drawings must be submitted to the electrical contractor.
24. Develop and process log and book of submittals, cut sheets and shop drawings.
☐ |  | 1 | Develop a log, with sequential numbering, to track all submittals, including those of vendors and subcontractors (see also Activity 17 and Table 4.13).
☐ |  | 2 | Assemble two or more binders of all draft and approved submittals.
☐ |  | 3 | Submit and track required submittal items.