## Job Plan - CO Breakdown
Change Order ¦ Non-Contract
|  |  | w/ Status Breakdown | [5 empty] | Job Name | [8 empty] | Job # |  |  | Date
|  |  |  | CO Description: | [13 empty] | Submitted By:
Mark an "X" for the Change Order Status:
Does not add to the budget | [8 empty] | Adds only to the projected budget | [7 empty] | Approved--Adds to the current budget
| 10 POTC |  | This has the potential of becoming a change order. | [6 empty] | 30 IPC |  | GSL is incurring costs per owner directive & waiting formal approval. Not part of the contract or SoV, but should be in budget & cost projections. | [5 empty] | 40 APC |  | CO document has been fully executed and signed by both parties. This CO now becomes part of the contract and the schedule of values.
| Potential | [8 empty] | In Progress | [7 empty] | Approved
| 20 PCO |  | GSL has submitted a price for approval; no costs have been incurred on this proposal. | [6 empty] | 50 RECO |  | CO is rejected by owner. Costs need to be recognized as a budget adjustment. No change in contract value. |  |  |  |  | Was this change order entered before under
| Proposed | [8 empty] | Rejected | [6 empty] | a different status? |  |  |  |  | Yes |  | No
If yes, note the change of status--
| 70 CACO |  | GSL incurring costs per owner and waiting formal approval. Not part of the contract or SoV, but should be in budget & cost projections. | [6 empty] | 60 DiCO |  | Negotiating a CO price agreement. GSL began incurring costs. CO is not part of the contract or SoV, & needs to be in all budget and cost projections. | [7 empty] | from: |  |  | to:
| Canceled | [8 empty] | Disputed
Enter a breakdown(s) for the desired phase:
|  |  | PHASE: |  |  | 10 |  |  | 20 |  |  |  | 30 |  | 40 |  |  |  | 50 |  |  | Total
| HOURS |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  |  | 0
1 | Labor & Subsistence |  |  |  | 1 | 0 |  | 1 | 0 |  |  | 1 | 0 | 1 | 0 |  |  | 1 | 0 |  | 1 | 0
2 | Labor Burden |  |  |  | 2 | 0 |  | 2 | 0 |  |  | 2 | 0 | 2 | 0 |  |  | 2 | 0 |  | 2 | 0
3 | Materials |  |  |  | 3 | 0 |  | 3 | 0 |  |  | 3 | 0 | 3 | 0 |  |  | 3 | 0 |  | 3 | 0
4 | Sub-Contracts |  |  |  | 4 | 0 |  | 4 | 0 |  |  | 4 | 0 | 4 | 0 |  |  | 4 | 0 |  | 4 | 0
5 | GSL-Owned Equipment |  |  |  | 5 | 0 |  | 5 | 0 |  |  | 5 | 0 | 5 | 0 |  |  | 5 | 0 |  | 5 | 0
6 | Rental Equipment |  |  |  | 6 | 0 |  | 6 | 0 |  |  | 6 | 0 | 6 | 0 |  |  | 6 | 0 |  | 6 | 0
7 | Other |  |  |  | 7 | 0 |  | 7 | 0 |  |  | 7 | 0 | 7 | 0 |  |  | 7 | 0 |  | 7 | 0
8 | Performance Incentive |  |  |  | 8 | 0 |  | 8 | 0 |  |  | 8 | 0 | 8 | 0 |  |  | 8 | 0 |  | 8 | 0
| COST |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  |  | 0
| Margin |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  |  | 0
Margin %
| TOTAL: |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  |  | 0
Phase %
[7 empty] | Contract |  |  |  | Non-contract |  |  | Change Order #: |  | 0 |  | --
[14 empty] | Proposal #: | [6 empty] | Work Voucher #:
Notes:

## Job Plan, Long List
[7 empty] | Job Number |  |  | Date
Job Plan
Breakdown
Job Name
Budge Adjustment Description:
Person Submitting this form:
|  | Addition to the contract | [6 empty] | Addition as non-contract
| General Contractor | [6 empty] | Company Requesting work
| Proposal Number | [6 empty] | Contact Person
| Change Order Number | [6 empty] | Phone Number
Work Voucher Number
Job Plan Breakdown
| Code |  |  | Description | [5 empty] | Qty | Hours
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
[10 empty] | TOTAL | 0
Notes: