## Material Handling Checklist
Table 4.16: Material Handling Planning Process Checklist (page 29)
Project Number: ________________________________________________________________________________
Project Name: ________________________________________________________________________________
Location: ________________________________________________________________________________
Project Manager: ________________________________________________________________________________
Start Date: ________________________________________________________________________________
MATERIAL HANDLING PROCESS CHECKLIST FOR PRE-CONSTRUCTION PLANNING
ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES
25. Develop material delivery and handling plan.
☐ |  | 1 | Review the "Material Delivery/Storage and Site Logistics Best Practices" (see Table 4.18).
☐ |  | 2 | Establish and maintain a file of delivery receipts and packing slips.
☐ |  | 3 | Establish a material and equipment delivery and storage log
☐ |  | 4 | Create a material and equipment delivery schedule.
☐ |  | 5 | Establish standard procedures for receiving, handling and storage of materials and equipment.
26. Develop material storage and staging plan.
☐ |  | 1 | Complete the site logistics review checklist (Table 4.20).
☐ |  | 2 | Review the "Material Delivery/Storage and Site Logistics Best Practices" (see Table 4.18).
☐ |  | 3 | Develop a storage site layout that identifies where the materials and equipment are stored.