## Pre-Construction Checklist
Table 4.1: Checklist of Pre-Construction Planning Activities
PRE-CONSTRUCTION PLANNING CHECKLIST
ACT. | COMPLETION DATE | ACTIVITY CATEGORY | ACT. NO. | ACTIVITY | [5 empty] | Pre Bid
|  | Pre Bid |  | Prepare construction takeoff.
|  |  |  | Estimator review contractual considerations | Call Phi and or Troy
|  |  |  | Business Manager Pre-Bid contract review for unfavorable or high risk clauses | 9.2.005 – Review Contract for High Risk Clauses | Form? |  | Administrative Set Up |  | Team Selection and Turnover Meeting
Estimator To Create a Quick Start Plan (Recommended)
☐ |  | Team Selection and Turnover | 1 | Finalize selection of project manager, field supervisor and other key team members. | 9.2.010 – Team Selection
|  |  | 2 | Project Budget and Request a Job Number | Missing SOP | Job# Request Form |  | Layout and Sequencing Plan |  | Scope and Contract Review | Time Sensitive Issues
|  |  | 3 | Branch Manager Review Estimated Scope vs.Preposed Contract
|  |  | 4 | Branch and Business Managers Negociate Final contract & Create a Contract Summry | 9.2.005 – Review Contract for High Risk Clauses | Get from Julie
☐ |  |  | 5 | Hold turnover meeting between estimator and project manager, Branch Manager and Superintendent (Include field leadership if available) | 9.2.015 – Project Turnover Meeting | Need GSLs Agenda (Smartsheets) | Smartsheets ? | Material Handling Plan |  |  | Buyout Process
☐ |  |  | 6
☐ |  |  | 7
|  | Time Sensitive Issues | 8 | Prepare and Submit Long Lead Submittals |  |  |  | Schedule Development |  |  | Budget Preparation
|  |  | 9 | Procure Feeders | 9.2.020 – Procurement of Large Feeder Wire
|  |  | 10 | Order long-lead-time materials and equipment.
☐ |  | Administrative Setup | 11 | Administrative Setup / Job Folder | Missing SOP |  |  |  |  | Tracking and Control
|  |  | 12 | Set up computerized tracking and control system (forms, database, schedule, and tracking).
|  |  | 13 | Set Up Job in Procore | Missing SOP
|  | Scope and Contract Review | 14 | PM Review exicuted contract, Contract summay, and create a Contract Hot sheet for Field Leadership | Missing SOP |  |  |  |  | Construction Execution Kickoff
☐ |  |  | 15 | Conduct site visit | 9.2.070 – Conduct Site Visit | Site_Visit_Checklist
☐ |  |  | 16 | Project manager reviews plans, specifications, and schedule. | 9.2.040 – Project Manager Reviews Plans, Specifications & Schedule
|  |  |  | Field supervisor reviews plans, specifications, and schedule. | 9.2.050 – Field Supervisor Reviews Plans, Specifications & Schedule
|  |  | 17 | Identify value engineering and prefabrication opportunities and how to simplify the work. | 9.2.057 – Identify Value Engineering & Prefabrication Opportunities
|  | Budget Preparation | 18 | Compare estimated (bid) work activities and materials to planned performance. | 9.2.055 – Compare Estimated vs Planned Performance
|  |  | 19 | Compare Estimated Budget vs Proposed Revised Budget / Submit Revised Budget for Approval | Missing SOP | Job# Request Form
|  |  | 20 | Create Schedule of Values | Missing SOP
☐ |  | Layout and Sequencing Plan | 21 | Develop installation sequence and layout drawings, including panel, pull or conduit schedules.
Review the work sequence and long-lead-time material/equipment delivery dates.
☐ |  |  | 22 | Develop prefabrication drawings for field use (when applicable).
☐ |  | Planning and Scheduling | 23 | Create Job Plan
|  |  | 24 | Review customer's schedule and timeline.
|  |  | 25 | Identify work that impacts electrical activities.
☐ |  |  | 26 | Coordinate electrical schedule with customer schedule (recommended).
☐ |  |  | 27 | Create a Projected Manpower Schedule
|  |  | 28 | Create Three week Look-Ahead Schedule
29
☐ |  |  | 30
31
☐ |  |  | 32
☐ |  | Field Document Control Setup | 33 | Set up project files and create contact list. | 9.4.190 – Document Filing Standards |  |  |  | 9.4.190 – Document Filing Standards
|  |  | 34 | Create Job Site ORG CHART | Missing SOP
|  |  | 35 | 02-DRAWINGS & SPECS | 9.4.220 – Manage Drawing Logs
|  |  | 36 | 04-SUBMITTALS | 9.4.200 – Manage Submittals
|  |  | 37 | Create List of Issues & Continue the RFI Process (From Estimating) | 9.2.060 – Create List of Issues & Begin RFI Process; 9.4.205 – Manage RFIs (Requests for Information) | RFI Log in Pro Core
|  |  | 38 | 06-Daily Reports | 9.4.215 – Manage Daily Reports
|  |  | 39 | Week Status Update Letter | Missing SOP
|  |  | 40 | 01-BILLING/ Progress
|  |  | 41 | 02-CHANGE ORDERS
|  |  | 42 | 03-Purchace Orders / Ordering & Tracking Materials
|  |  | 43 | Manage Subcontractor and Vendor Communications | 9.4.290 – Manage Subcontractor Communications; 9.4.295 – Manage Vendor Supplier Communications
|  |  | 44 | Manage Communication with Owners Team | 9.4.285 – Manage Client/Owner Communications; 9.4.300 – Manage Architect/Engineer Communications; 9.4.305 – Manage Regulatory/Authority Communications; 9.4.310 – Manage General Contractor Communications
☐ |  |  | 45 | Manage Project Communications | 9.4.230 – Manage Correspondence; 9.4.270 – Manage Project Communications; 9.4.275 – Manage Internal Communications; 9.4.280 – Manage External Communications
|  |  | 46 | Manage Inspection | 9.4.240 – Manage Inspection Reports | [6 empty] | Document Type | Code
☐ |  |  | 47 | Initiate a change management system. | [7 empty] | Request For Information | RFI
☐ |  |  | 48 | Customize the computerized tracking and control system (database/schedule/etc.) for the current project. | [7 empty] | Submittal | SUBM
|  |  | 49 | Develop labor and materials tracking report. | [7 empty] | Change Order | CO
☐ |  |  | 50 | Initiate a submittal tracking and processing system. | [7 empty] | Potential Change Order | PCO
☐ |  |  | 51 | Develop a "Labor Requirements/Expectations" letter (for background check, etc.) (recommended). | [7 empty] | Purchase Order | PO
|  | Material Handling Plan | 52 | Develop material delivery and handling plan. | [7 empty] | Letter of Intent | LOI
|  |  | 53 | Develop material storage and staging plan. | [7 empty] | Meeting Minutes | MIN
☐ |  | Buyout Process | 54 | Price and/or review subcontractor/supplier/vendor prices and qualifications. | [7 empty] | Weekly Status Report | WSR
☐ |  |  | 55 | Negotiate pricing and contract conditions, and select subcontractors/suppliers/vendors. | [7 empty] | Daily Report | DR
☐ |  |  | 56 | Develop and issue purchase orders and contracts for materials and equipment. | [7 empty] | Transmittal | TRANS
☐ |  |  | 57 | Order long-lead-time materials and equipment. | [7 empty] | Contract | CNTR
☐ |  |  | 58 | Request submittals, cut sheets and shop drawings. | [7 empty] | Invoice | INV
☐ |  |  | 59 | Develop and process log and book of submittals, cut sheets and shop drawings. | [7 empty] | Quote | QUOTE
☐ |  | Construction Execution Kickoff Meeting | 60 | Review meeting schedule. | [7 empty] | Job Hazard Analysis | JHA
☐ |  |  | 61 | Review request for information (RFI) process. | [7 empty] | Safety Data Sheet | SDS
☐ |  |  | 62 | Review change order process and field change management process. | [7 empty] | Nonconformance Report | NCR
☐ |  |  | 63 | Review submittal processing procedure. | [7 empty] | Commissioning | CX
☐ |  |  | 64 | Review billing and invoicing procedures. | [7 empty] | O&M Manuals | OM
☐ |  |  | 65 | Review project and field reporting and tracking procedures. | [7 empty] | Time & Material | TM
☐ |  |  | 66 | Review electrical and customer schedules.