## Scope Contract Review
Table 4.5: Scope and Contract Review Checklist (page 17)
Project Number: ________________________________________________________________________________
Project Name: ________________________________________________________________________________
Location: ________________________________________________________________________________
Estimator: ________________________________________________________________________________
Bid Due Date: ________________________________________________________________________________
SCOPE AND CONTRACT REVIEW CHECKLIST FOR PRE-CONSTRUCTION PLANNING
ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES
5. Review contract for unfavorable or high risk clauses (performance recommended).
☐ |  | 1 | Complete the Contract Review Checklist (Table 4.6).
☐ |  | 2 | Identify all required bonds, permits and certificates.
☐ |  | 3 | Review contractual billing requirements.
☐ |  | 4 | Review and understand procedures for requesting change orders.
☐ |  | 5 | Identify whether disputes must be resolved through alternative dispute resolution, such as mediation or arbitration.
6. Project manager reviews plans, specifications and schedule.
☐ |  | 1 | Order extra sets of plans and specifications if necessary.
☐ |  | 2 | Complete the Scope and Schedule Review checklist (Table 4.7).
☐ |  | 3 | Compare the scope identified in the contract to the scope from the bid submission to verify that they match.
☐ |  | 4 | Compare the plans to the specifications to identify any discrepancies.
☐ |  | 5 | Review the customer-furnished schedule to determine whether the electrical work can be completed within the contractual timeframe.
7. Field supervisor reviews plans, specifications and schedule.
☐ |  | 1 | Complete the Scope and Schedule Review checklist (Table 4.7).
☐ |  | 2 | Review best field practices or lessons learned.
☐ |  | 3 | Identify value engineering and prefabrication opportunities (see Activity 23).
☐ |  | 4 | Identify labor requirements and begin selecting foremen.
☐ |  | 5 | Identify special tools that will need to be purchased or assembled.
8. Create a list of issues that need to be resolved and begin the request for information (RFI) process.
☐ |  | 1 | Establish a request for information (RFI) process (see Activity 16) and create a list of questions that require clarification.
☐ |  | 2 | Formalize the RFIs by assigning them a trackable number and submitting them to the owner/CM/GC.
9. Conduct a site visit (performance recommended).
☐ |  | 1 | Complete the Site Visit Checklist (Table 4.8).
☐ |  | 2 | Examine site access and layout, including parking, material delivery points and material lay-down and storage.
☐ |  | 3 | Identify locations and availability of material and personnel lifts, elevators, cranes, scaffolding and forklifts.
☐ |  | 4 | Create a plan for installing temporary power (when applicable).
☐ |  | 5 | Verify existing conditions and compare them to the conditions shown on the plans and described in the specifications.
10. Compare estimated (bid) work activities and materials to planned performance.
☐ |  | 1 | Compare the estimator's concept of how to perform the work to typical field operations and document differences.
☐ |  | 2 | Discuss unclear methods or discrepancies with the estimator.
☐ |  | 3 | Determine the cost difference between the as-bid and planned performance of the work.
11. Identify value engineering and prefabrication opportunities and how to simplify the work.
☐ |  | 1 | Review value engineering (VE) or prefabrication opportunities that were identified in the turnover meeting between the estimator and project manager.
☐ |  | 2 | Review procedures for formally requesting VE consideration if required.
☐ |  | 3 | Search for and identify additional VE and prefabrication items.
☐ |  | 4 | Identify additional ways to simplify the work.
☐ |  | 5 | Price out the cost difference between the as-bid and VE options.
12. Compare estimated (bid) work activities and materials to planned performance.
☐ |  | 1 | Take off the materials, equipment and systems in the order they will be constructed.
☐ |  | 2 | Code each plan sheet as you take it off so that you can return to it later and immediately identify the quantity of various materials shown on the sheet.
☐ |  | 3 | The final quantities should be identified by the units in which they will be purchased.
☐ |  | 4 | All assumptions should be noted on the quantity takeoff sheets.
☐ |  | 5 | Be sure the quantities that are estimated include a waste factor.
☐ |  | 6 | Compare the construction takeoff to the bid takeoff to identify significant differences or discrepancies.