## Team Selection Turnover
Table 4.2: Team Selection and Turnover Checklist (page 16)
Project Number: ________________________________________________________________________________
Project Name: ________________________________________________________________________________
Location: ________________________________________________________________________________
Estimator: ________________________________________________________________________________
Project Manager: ________________________________________________________________________________
TEAM SELECTION AND TURNOVER CHECKLIST FOR PRE-CONSTRUCTION PLANNING
ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES
1. Finalize selection of project manager, field supervisor and other key team members.
☐ |  | 1 | Assemble a list of project managers and review their current work-load and special skills.
☐ |  | 2 | Determine whether an ideal match can be made between the project manager and the job, and then select the project manager.
☐ |  | 3 | Assemble a list of field supervisors and review their current work-load and special skills.
☐ |  | 4 | Determine whether an ideal match can be made between the field supervisor and the job, and then select the project manager.
☐ |  | 5 | Work with the project manager, field supervisor, and/or the director of operations to select key foreman when appropriate.
2. Hold turnover meeting between estimator and project manager (when applicable).
☐ |  | 1 | Arrange a meeting time and location and ensure enough time has been allocated to transfer knowledge between the estimator and project manager.
☐ |  | 2 | Follow and complete a checklist that describes the information that should be transferred (See Table 4.3).
3. Hold separate turnover meeting between project manager and field supervisor.
☐ |  | 1 | Arrange a meeting time and location and ensure enough time has been allocated to transfer knowledge between the project manager and field supervisor.
☐ |  | 2 | Follow and complete a checklist that describes the information that must be transferred (see Table 4.3).
4. Hold pre-job (planning) kickoff meeting with internal team members to assign responsibilities.
☐ |  | 1 | Arrange a meeting time and location and ensure enough time has been allocated to assign planning responsibilities.
☐ |  | 2 | Invite internal team members that will be involved during the construction execution process, such as project manager, field supervisor, accounting, purchasing, and director of field operations.
☐ |  | 3 | Complete a checklist that describes the planning activities that must be completed and who is responsible for completion (see Table 4.4).