## Turnover Meeting Agenda
Table 4.3: Turnover Meeting Agenda (page 16)
Project Number: ________________________________________________________________________________
Project Name: ________________________________________________________________________________
Location: ________________________________________________________________________________
Estimator: ________________________________________________________________________________
Project Manager: ________________________________________________________________________________
TURNOVER MEETING AGENDA
Review Items:
1. | Project overview
| a. | Project name
| b. | Location
| c. | Type of work
| d. | Estimated cost and estimated work hours
| e. | Profit goal
| f. | General scope of work
| g. | Identify potential opportunities and challenges of the project
2. | Review the plans and specifications.
| a. | Go page by page through the plans to discuss the quantities and costs.
| b. | Review each section of the specifications.
| c. | Discuss how the estimator assumed the work would be performed (materials and methods).
| d. | Review others' work performance.
| e. | Identify discrepancies and ambiguities in the bid documents.
| f. | Identify design discrepancies or issues.
| g. | Identify potential errors in the bid documents.
| h. | Discuss information collected during a site visit.
| i. | Discuss information collected during a pre-bid meeting.
| j. | Identify potential cost savings from changes to materials and methods.
| k. | Identify potential prefabrication or internal value engineering opportunities.
| l. | Discuss alternative routing of conduits.
| m. | Identify any temporary power and lighting requirements.
3. | Review the cost estimate and bid price.
| a. | Review each bid line item and its cost.
| b. | Review overhead, profit and contingency funds.
| c. | Discuss wage rates.
| d. | Review the bid submission letter with clarifications and qualifications.
4. | Review subcontractor/vendor pricing and qualifications.
| a. | Review subcontractors and suppliers scope of work and qualifications.
| b. | Identify all pre-contract commitments and promises.
| c. | Verify minority business requirements.
5. | Review the schedule and milestones.
| a. | Review the owner-furnished schedule.
| b. | Review any preliminary schedule submitted with the bid.
| c. | Review work by others that will impact the electrical work.
| d. | Identify important material and equipment delivery dates.
| e. | Discuss holidays, vacations and potential weather events.
6. | Review manpower requirements and labor rates.
| a. | Review the manpower loading chart (if available).
| b. | Identify the estimated crew mix.
| c. | Identify any wage increases.
| d. | Review the potential for overtime.
7. | Review other items specific to this project:
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________
_______________________________________________________________________________________________