## GSL_SOP_Metadata
SOP ID | Name | SOP File Name | Title | Description | Phase | Category | Roles (RACI) | Discipline | Status | Document Type
9.1.050 | 9.1.050 - Prepare Construction Takeoff | 9.1.050 – Prepare Construction Takeoff.docx | Prepare Construction Takeoff |  | 1 - Estimating | Estimating | [Inferred] Project Manager (R) | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.055 – Procurement of Large Feeder Wire Reference: GSL Pre-Construction Planning – Construction Takeoff | Approved | SOP
9.2.005 | 9.2.005 - Review Contract for High Risk Clauses | 9.2.005 – Review Contract for High Risk Clauses.docx | Review Contract for High Risk Clauses | To establish a standardized process for reviewing contract terms to identify unfavorable or high-risk clauses before baseline planning begins, ensuring proper risk mitigation and approval protocols are in place. | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Branch Management | Approved | SOP
9.2.010 | 9.2.010 - Team Selection | 9.2.010 – Team Selection.docx | Team Selection | To establish a standardized process for selecting and assembling the project team immediately after project award, ensuring the right mix of skills, experience, and availability to meet project requirements. | 2 - Preconstruction | Preconstruction | Branch Manager (A); Project Manager (R); General Superintendent (C); Safety Coordinator (C); Purchasing (I); Prefabrication Lead (I); Project Coordinator (I) | Project Management / Operations | Approved | SOP
9.2.015 | 9.2.015 - Project Turnover Meeting | 9.2.015 – Project Turnover Meeting.docx | Project Turnover Meeting |  | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.2 Related SOPs: | Approved | SOP
9.2.020 | 9.2.020 - Procurement of Large Feeder Wire | 9.2.020 – Procurement of Large Feeder Wire.docx | Procurement of Large Feeder Wire |  | 2 - Preconstruction | Preconstruction | [Inferred] Purchasing (R); Project Manager (A) | Operations | Approved | SOP
9.2.030 | 9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | 9.2.030 – Review Contract for Unfavorable or High Risk Clauses.docx | Review Contract for Unfavorable or High-Risk Clauses |  | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Pre-Construction Created by: Schachinger Solutions GmbH Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Contract Review | Approved | SOP
9.2.040 | 9.2.040 - Project Manager Reviews Plans Specifications & Schedule | 9.2.040 – Project Manager Reviews Plans, Specifications & Schedule.docx | Project Manager Reviews Plans Specifications & Schedule |  | 2 - Preconstruction | Preconstruction | [Inferred] Superintendent (C); Project Manager (R) | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable or High-Risk Clauses; 9.41.025 – Field Supervisor Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Scope & Schedule Review | Approved | SOP
9.2.050 | 9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | 9.2.050 – Field Supervisor Reviews Plans, Specifications & Schedule.docx | Field Supervisor Reviews Plans Specifications & Schedule |  | 2 - Preconstruction | Preconstruction | [Inferred] Superintendent (C); Project Manager (R) | Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process Reference: GSL Pre-Construction Planning – Scope & Schedule Review | Approved | SOP
9.2.055 | 9.2.055 - Compare Estimated vs Planned Performance | 9.2.055 – Compare Estimated vs Planned Performance.docx | Compare Estimated vs Planned Performance |  | 2 - Preconstruction | Preconstruction | [Inferred] Estimator (C); Project Manager (A) | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.045 – Identify Value Engineering & Prefabrication Opportunities Reference: GSL Pre-Construction Planning – Bid vs. Execution Review | Approved | SOP
9.2.057 | 9.2.057 - Identify VE and Prefabrication Opportunities | 9.2.057 – Identify VE and Prefabrication Opportunities.docx | Identify VE and Prefabrication Opportunities |  | 2 - Preconstruction | Preconstruction | [Inferred] Prefabrication Lead (R); Project Manager (A) | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.060 | 9.2.060 - Create Issue List and Begin RFI Process | 9.2.060 – Create Issue List and Begin RFI Process.docx | Create Issue List and Begin RFI Process | To establish a standardized process for documenting project issues identified during pre-construction review and initiating the Request for Information (RFI) process to resolve them before construction begins. | 2 - Preconstruction | Preconstruction | ¦ Project Manager (A); ¦ Assistant PM/Project Coordinator (R); ¦ Field Supervisor (C); ¦ General Superintendent (C) | Project Management | Approved | SOP
9.2.070 | 9.2.070 - Conduct Site Visit | 9.2.070 – Conduct Site Visit.docx | Conduct Site Visit | To establish a standardized process for conducting pre-construction site visits to assess existing conditions, identify logistical requirements, and validate planning assumptions before mobilization. | 2 - Preconstruction | Preconstruction | ¦ Project Manager (A); ¦ Field Leadership (R); ¦ Safety Coordinator (R); ¦ General Superintendent (C) | Project Management / Field Operations | Approved | SOP
9.2.080 | 9.2.080 - Prepare Material Handling Plan | 9.2.080 – Prepare Material Handling Plan.docx | Prepare Material Handling Plan |  | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.090 | 9.2.090 - Develop Labor Budget | 9.2.090 – Develop Labor Budget.docx | Develop Labor Budget |  | 2 - Preconstruction | Preconstruction | [Inferred] Accounting (C); Project Manager (A) | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.100 | 9.2.100 - Prepare Layout & Sequencing Plan | 9.2.100 – Prepare Layout & Sequencing Plan.docx | Prepare Layout & Sequencing Plan |  | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.065 – Develop Labor Budget; 9.41.075 – Develop Project Schedule Reference: GSL Pre-Construction Planning – Layout & Sequencing | Approved | SOP
9.2.110 | 9.2.110 - Develop Project Schedule | 9.2.110 – Develop Project Schedule.docx | Develop Project Schedule |  | 2 - Preconstruction | Preconstruction | [Inferred] Superintendent (C); Project Manager (A) | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.120 | 9.2.120 - Establish Tracking & Control Systems | 9.2.120 – Establish Tracking & Control Systems.docx | Establish Tracking & Control Systems |  | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Pre-Construction Planning – Tracking & Control | Approved | SOP
9.2.130 | 9.2.130 - Construction Execution Kickoff Meeting | 9.2.130 – Construction Execution Kickoff Meeting.docx | Construction Execution Kickoff Meeting |  | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (R) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.140 | 9.2.140 - Develop Project Budget | 9.2.140 – Develop Project Budget.docx | Develop Project Budget |  | 2 - Preconstruction | Preconstruction | [Inferred] Accounting (C); Project Manager (A) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.360 – Manage Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.2.160 | 9.2.160 - Develop Procurement Plan | 9.2.160 – Develop Procurement Plan.docx | Develop Procurement Plan |  | 2 - Preconstruction | Preconstruction | [Inferred] Purchasing (R); Project Manager (A) | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.395 – Develop Project Budget; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.3.010 | 9.3.010 - Setup Office Trailer | 9.3.010 – Setup Office Trailer.docx | Setup Office Trailer | To establish a standardized process for setting up the project office trailer, ensuring proper placement, utilities, and functionality for project administration and team coordination. | 3 - Mobilization | Mobilization | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Site Administrator (R); ¦ Safety Coordinator (C); ¦ General Superintendent (C) | Project Management / Field Operations | Approved | SOP
9.3.020 | 9.3.020 - Setup Storage Trailer | 9.3.020 – Setup Storage Trailer.docx | Setup Storage Trailer | To establish a standardized process for setting up project storage trailers/containers, ensuring secure and organized storage for materials, tools, and equipment. | 3 - Mobilization | Mobilization | ¦ Field Supervisor (A); ¦ Foreman (R); ¦ Purchasing (C); ¦ Safety Coordinator (C) | Field Operations | Approved | SOP
9.3.030 | 9.3.030 - Setup Site Fencing and Access Control | 9.3.030 – Setup Site Fencing and Access Control.docx | Setup Site Fencing and Access Control | To establish a standardized process for installing site fencing and access control measures, ensuring site security and controlled entry/exit for personnel and deliveries. | 3 - Mobilization | Mobilization | ¦ Field Supervisor (A); ¦ Foreman (R); ¦ Safety Coordinator (R); ¦ Project Manager (C) | Field Operations / Safety | Approved | SOP
9.3.040 | 9.3.040 - Setup Temporary Power | 9.3.040 – Setup Temporary Power.docx | Setup Temporary Power | To establish a standardized process for installing temporary electrical power distribution, ensuring safe and adequate power for construction operations, trailers, and equipment. | 3 - Mobilization | Mobilization | ¦ Field Supervisor (A); ¦ Foreman/Journeyman (R); ¦ Safety Coordinator (C); ¦ Project Manager (C); ¦ Electrical Subcontractor (R) | Field Operations | Approved | SOP
9.3.050 | 9.3.050 - Setup Temporary Water | 9.3.050 – Setup Temporary Water.docx | Setup Temporary Water |  | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.060 | 9.3.060 - Setup Sanitary Facilities | 9.3.060 – Setup Sanitary Facilities.docx | Setup Sanitary Facilities |  | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer; 9.41.110 – Setup Temporary Water Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.070 | 9.3.070 - Setup Temporary Lighting | 9.3.070 – Setup Temporary Lighting.docx | Setup Temporary Lighting |  | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.105 – Setup Temporary Power; 9.41.110 – Setup Temporary Water; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.080 | 9.3.080 - Setup Signage | 9.3.080 – Setup Signage.docx | Setup Signage |  | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.090 | 9.3.090 - Setup Security | 9.3.090 – Setup Security.docx | Setup Security |  | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.125 – Setup Signage Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.100 | 9.3.100 - Setup Laydown Area | 9.3.100 – Setup Laydown Area.docx | Setup Laydown Area |  | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.095 – Setup Storage Trailer; 9.41.100 – Setup Site Fencing and Access Control Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.110 | 9.3.110 - Setup Equipment Staging | 9.3.110 – Setup Equipment Staging.docx | Setup Equipment Staging |  | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.120 | 9.3.120 - Setup Parking | 9.3.120 – Setup Parking.docx | Setup Parking |  | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.470 | 9.3.470 - Develop Site-Specific Safety Plan | 9.3.470 – Develop Site Specific Safety Plan.docx | Develop Site-Specific Safety Plan |  | 3 - Mobilization | Mobilization | [Inferred] Safety Coordinator (C); Project Manager (R); Field Supervisor (C) | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.010 | 9.4.010 - Conduct Coordination Meetings | 9.4.010 – Conduct Coordination Meetings.docx | Conduct Coordination Meetings |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Owner/GC Coordination Meetings; 9.41.170 – Conduct Progress Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.020 | 9.4.020 - Conduct Subcontractor Coordination Meetings | 9.4.020 – Conduct Subcontractor Coordination Meetings.docx | Conduct Subcontractor Coordination Meetings |  | 4 - Execution | Execution | [Inferred] Subcontractors (R); Project Manager (R); Field Supervisor (C) | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.030 | 9.4.030 - Conduct Client/Owner Meetings | 9.4.030 – Conduct Client Owner Meetings.docx | Conduct Client/Owner Meetings |  | 4 - Execution | Execution | [Inferred] Branch Manager (C); Project Manager (A); Field Supervisor (C) | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable Clauses; 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.040 | 9.4.040 - Conduct Safety Meetings | 9.4.040 – Conduct Safety Meetings.docx | Conduct Safety Meetings |  | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.115 – Setup Sanitary Facilities; 9.41.120 – Setup Temporary Lighting Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.045 | 9.4.045 - Identify Value Engineering & Prefabrication Opportunities | 9.4.045 – Identify Value Engineering & Prefabrication Opportunities.docx | Identify Value Engineering & Prefabrication Opportunities |  | 4 - Execution | Execution | [Inferred] Prefabrication Lead (R); Project Manager (A); Field Supervisor (C) | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.050 – Prepare Construction Takeoff Reference: GSL Pre-Construction Planning – Value Engineering & Prefabrication | Approved | SOP
9.4.050 | 9.4.050 - Conduct Prefabrication Coordination Meetings | 9.4.050 – Conduct Prefabrication Coordination Meetings.docx | Conduct Prefabrication Coordination Meetings |  | 4 - Execution | Execution | [Inferred] Prefabrication Lead (R); Project Manager (R); Field Supervisor (C) | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.050 – Prepare Construction Takeoff; 9.41.065 – Develop Labor Budget Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.055 | 9.4.055 - Procurement of Large Feeder Wire | 9.4.055 – 1 Procurement of Large Feeder Wire.docx | Procurement of Large Feeder Wire |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Operations | Approved | SOP
9.4.060 | 9.4.060 - Conduct Quality Meetings | 9.4.060 – Conduct Quality Meetings.docx | Conduct Quality Meetings |  | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Project Management / Quality Control Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.080 – Establish Tracking & Control Systems Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.190 | 9.4.190 - Document Filing Standards | 9.4.190 – A Document Filing Standards.docx | Document Filing Standards |  | 4 - Execution | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: All documentation-related SOPs (9.41.195 – 9.41.265 and beyond) Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.195 | 9.4.195 - Manage Project Documentation System | 9.4.195 – Manage Project Documentation System.docx | Manage Project Documentation System |  | 4 - Execution | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.005 – Team Selection; 9.41.010 – Project Turnover Meeting; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.200 | 9.4.200 - Manage Submittals | 9.4.200 – Manage Submittals.docx | Manage Submittals |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.050 – Prepare Construction Takeoff; 9.41.055 – Procurement of Large Feeder Wire; 9.41.075 – Develop Project Schedule; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.205 | 9.4.205 - Manage RFIs (Requests for Information) | 9.4.205 – Manage RF Is (Requests for Information).docx | Manage RFIs (Requests for Information) |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Pre-Construction Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.210 | 9.4.210 - Manage Meeting Minutes | 9.4.210 – Manage Meeting Minutes.docx | Manage Meeting Minutes |  | 4 - Execution | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Client/Owner Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.215 | 9.4.215 - Manage Daily Reports | 9.4.215 – Manage Daily Reports.docx | Manage Daily Reports |  | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.080 – Establish Tracking & Control Systems; 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.220 | 9.4.220 - Manage Drawing Logs | 9.4.220 – Manage Drawing Logs.docx | Manage Drawing Logs |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.225 | 9.4.225 - Manage Specifications | 9.4.225 – Manage Specifications.docx | Manage Specifications |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.200 – Manage Submittals; 9.41.220 – Manage Drawing Logs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.230 | 9.4.230 - Manage Correspondence | 9.4.230 – Manage Correspondence.docx | Manage Correspondence |  | 4 - Execution | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.205 – Manage RFIs; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.235 | 9.4.235 - Manage Permits | 9.4.235 – Manage Permits.docx | Manage Permits |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Safety / Compliance Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.240 | 9.4.240 - Manage Inspection Reports | 9.4.240 – Manage Inspection Reports.docx | Manage Inspection Reports |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Quality / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.235 – Manage Permits; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.270 | 9.4.270 - Manage Project Communications | 9.4.270 – Manage Project Communications.docx | Manage Project Communications |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.275 | 9.4.275 - Manage Internal Communications | 9.4.275 – Manage Internal Communications.docx | Manage Internal Communications |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.165 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.280 | 9.4.280 - Manage External Communications | 9.4.280 – Manage External Communications.docx | Manage External Communications |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.285 | 9.4.285 - Manage Client/Owner Communications | 9.4.285 – Manage Client Owner Communications.docx | Manage Client/Owner Communications |  | 4 - Execution | Execution | [Inferred] Branch Manager (C); Project Manager (R); Field Supervisor (C) | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.290 | 9.4.290 - Manage Subcontractor Communications | 9.4.290 – Manage Subcontractor Communications.docx | Manage Subcontractor Communications |  | 4 - Execution | Execution | [Inferred] Subcontractors (R); Project Manager (R); Field Supervisor (C) | Project Management / Subcontractor Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.295 | 9.4.295 - Manage Vendor Supplier Communications | 9.4.295 – Manage Vendor Supplier Communications.docx | Manage Vendor Supplier Communications |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (R); Field Supervisor (C) | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.200 – Manage Submittals; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.300 | 9.4.300 - Manage Architect/Engineer Communications | 9.4.300 – Manage Architect Engineer Communications.docx | Manage Architect/Engineer Communications |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.305 | 9.4.305 - Manage Regulatory/Authority Communications | 9.4.305 – Manage Regulatory Authority Communications.docx | Manage Regulatory/Authority Communications |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.310 | 9.4.310 - Manage General Contractor Communications | 9.4.310 – Manage General Contractor Communications.docx | Manage General Contractor Communications |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.150 – Conduct Project Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.315 | 9.4.315 - Develop Project Schedule | 9.4.315 – Develop Project Schedule.docx | Develop Project Schedule |  | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.010 – Project Turnover Meeting; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.320 | 9.4.320 - Update Project Schedule | 9.4.320 – Update Project Schedule.docx | Update Project Schedule |  | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.150 – Conduct Project Coordination Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.325 | 9.4.325 - Monitor Schedule Performance | 9.4.325 – Monitor Schedule Performance.docx | Monitor Schedule Performance |  | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.330 | 9.4.330 - Develop Schedule Recovery Plans | 9.4.330 – Develop Schedule Recovery Plans.docx | Develop Schedule Recovery Plans |  | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.325 – Monitor Schedule Performance; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.335 | 9.4.335 - Prepare Lookahead Schedules | 9.4.335 – Prepare Lookahead Schedules.docx | Prepare Lookahead Schedules |  | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.340 | 9.4.340 - Manage Resource-Loaded Schedules | 9.4.340 – Manage Resource Loaded Schedules.docx | Manage Resource-Loaded Schedules |  | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.345 | 9.4.345 - Conduct Schedule Review Meetings | 9.4.345 – Conduct Schedule Review Meetings.docx | Conduct Schedule Review Meetings |  | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.350 | 9.4.350 - Manage Schedule Change Requests | 9.4.350 – Manage Schedule Change Requests.docx | Manage Schedule Change Requests |  | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.355 | 9.4.355 - Manage Project Scope | 9.4.355 – Manage Project Scope.docx | Manage Project Scope |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.315 – Develop Project Schedule; 9.41.350 – Manage Schedule Change Requests; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.360 | 9.4.360 - Manage Change Orders | 9.4.360 – Manage Change Orders.docx | Manage Change Orders |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Operations | Approved | SOP
9.4.365 | 9.4.365 - Manage Potential Change Orders (PCOs) | 9.4.365 – Manage Potential Change Orders (PCOs).docx | Manage Potential Change Orders (PCOs) |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.370 | 9.4.370 - Manage Owner Directives | 9.4.370 – Manage Owner Directives.docx | Manage Owner Directives |  | 4 - Execution | Execution | [Inferred] Branch Manager (C); Project Manager (A); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.375 | 9.4.375 - Manage Scope Clarifications | 9.4.375 – Manage Scope Clarifications.docx | Manage Scope Clarifications |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.205 – Manage RFIs; 9.41.370 – Manage Owner Directives; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.380 | 9.4.380 - Manage Backcharges | 9.4.380 – Manage Backcharges.docx | Manage Backcharges |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.290 – Manage Subcontractor Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.385 | 9.4.385 - Manage Force Account Work | 9.4.385 – Manage Force Account Work.docx | Manage Force Account Work |  | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.380 – Manage Backcharges; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.390 | 9.4.390 - Manage Claims | 9.4.390 – Manage Claims.docx | Manage Claims |  | 4 - Execution | Execution | [Inferred] Branch Manager (A); Project Manager (A); Field Supervisor (C) | Project Management / Contract Administration / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.370 – Manage Owner Directives; 9.41.385 – Manage Force Account Work; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.400 | 9.4.400 - Monitor Project Costs | 9.4.400 – Monitor Project Costs.docx | Monitor Project Costs |  | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.405 – Manage Cost Forecasts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.405 | 9.4.405 - Manage Cost Forecasts | 9.4.405 – Manage Cost Forecasts.docx | Manage Cost Forecasts |  | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.410 | 9.4.410 - Manage Cost Codes | 9.4.410 – Manage Cost Codes.docx | Manage Cost Codes |  | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.415 | 9.4.415 - Manage Committed Costs | 9.4.415 – Manage Committed Costs.docx | Manage Committed Costs |  | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.420 | 9.4.420 - Manage Actual Costs | 9.4.420 – Manage Actual Costs.docx | Manage Actual Costs |  | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.425 | 9.4.425 - Manage Job Cost Reports | 9.4.425 – Manage Job Cost Reports.docx | Manage Job Cost Reports |  | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.430 | 9.4.430 - Manage Profit Projections | 9.4.430 – Manage Profit Projections.docx | Manage Profit Projections |  | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.435 | 9.4.435 - Manage Cost-to-Complete | 9.4.435 – Manage Cost to Complete.docx | Manage Cost-to-Complete |  | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.420 – Manage Actual Costs; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.440 | 9.4.440 - Prepare Billing Schedule | 9.4.440 – Prepare Billing Schedule.docx | Prepare Billing Schedule |  | 4 - Execution | Execution | [Inferred] Accounting (R); Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.445 | 9.4.445 - Prepare Monthly Pay Applications | 9.4.445 – Prepare Monthly Pay Applications.docx | Prepare Monthly Pay Applications |  | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.440 – Prepare Billing Schedule; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.450 | 9.4.450 - Track Accounts Receivable | 9.4.450 – Track Accounts Receivable.docx | Track Accounts Receivable |  | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Accounting / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.455 | 9.4.455 - Manage Lien Waivers | 9.4.455 – Manage Lien Waivers.docx | Manage Lien Waivers |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.460 | 9.4.460 - Manage Retainage | 9.4.460 – Manage Retainage.docx | Manage Retainage |  | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.465 – Manage Final Invoicing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.465 | 9.4.465 - Manage Final Invoicing | 9.4.465 – Manage Final Invoicing.docx | Manage Final Invoicing |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.455 – Manage Lien Waivers; 9.41.460 – Manage Retainage; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.475 | 9.4.475 - Conduct Safety Orientation | 9.4.475 – Conduct Safety Orientation.docx | Conduct Safety Orientation |  | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.480 | 9.4.480 - Conduct Safety Inspections | 9.4.480 – Conduct Safety Inspections.docx | Conduct Safety Inspections |  | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.485 | 9.4.485 - Conduct Safety Meetings | 9.4.485 – Conduct Safety Meetings.docx | Conduct Safety Meetings |  | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.490 | 9.4.490 - Report Safety Incidents | 9.4.490 – Report Safety Incidents.docx | Report Safety Incidents |  | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.485 – Conduct Safety Meetings; 9.41.495 – Investigate Accidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.495 | 9.4.495 - Investigate Accidents | 9.4.495 – Investigate Accidents.docx | Investigate Accidents |  | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Project Management / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.490 – Report Safety Incidents; 9.41.485 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.500 | 9.4.500 - Conduct Emergency Preparedness | 9.4.500 – Conduct Emergency Preparedness.docx | Conduct Emergency Preparedness |  | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.490 – Report Safety Incidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.505 | 9.4.505 - Conduct Safety Compliance Audits | 9.4.505 – Conduct Safety Compliance Audits.docx | Conduct Safety Compliance Audits |  | 4 - Execution | Execution | [Inferred] Safety Coordinator (C); Project Manager (A); Field Supervisor (C) | Safety / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.480 – Conduct Safety Inspections; 9.41.495 – Investigate Accidents; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.510 | 9.4.510 - Provide Safety Training | 9.4.510 – Provide Safety Training.docx | Provide Safety Training |  | 4 - Execution | Execution | [Inferred] Safety Coordinator (C); Project Manager (A); Field Supervisor (C) | Safety / Human Resources Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.475 – Conduct Safety Orientation; 9.41.485 – Conduct Safety Meetings; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.515 | 9.4.515 - Develop Quality Management Plan | 9.4.515 – Develop Quality Management Plan.docx | Develop Quality Management Plan |  | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.520 | 9.4.520 - Conduct Quality Meetings | 9.4.520 – Conduct Quality Meetings.docx | Conduct Quality Meetings |  | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.175 – Conduct Quality Meetings; 9.41.515 – Develop Quality Management Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.525 | 9.4.525 - Conduct Quality Inspections | 9.4.525 – Conduct Quality Inspections.docx | Conduct Quality Inspections |  | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Safety / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.515 – Develop Quality Management Plan; 9.41.520 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.530 | 9.4.530 - Manage Quality Testing | 9.4.530 – Manage Quality Testing.docx | Manage Quality Testing |  | 4 - Execution | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.525 – Conduct Quality Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.535 | 9.4.535 - Manage Nonconformance Reports (NCRs) | 9.4.535 – Manage Nonconformance Reports (NC Rs).docx | Manage Nonconformance Reports (NCRs) |  | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.530 – Manage Quality Testing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.540 | 9.4.540 - Manage Quality Records | 9.4.540 – Manage Quality Records.docx | Manage Quality Records |  | 4 - Execution | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.530 – Manage Quality Testing; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.545 | 9.4.545 - Manage Punch List Quality | 9.4.545 – Manage Punch List Quality.docx | Manage Punch List Quality |  | 4 - Execution | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.245 – Manage Punch Lists; 9.41.525 – Conduct Quality Inspections; 9.41.540 – Manage Quality Records; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.560 | 9.4.560 - Manage Manpower Allocation | 9.4.560 – Manage Manpower Allocation.docx | Manage Manpower Allocation |  | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.565 | 9.4.565 - Manage Equipment Allocation | 9.4.565 – Manage Equipment Allocation.docx | Manage Equipment Allocation |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.570 | 9.4.570 - Manage Material Allocation | 9.4.570 – Manage Material Allocation.docx | Manage Material Allocation |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.565 – Manage Equipment Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.576 | 9.4.576 - Manage Subcontractor Resources | 9.4.576 – Manage Subcontractor Resources.docx | Manage Subcontractor Resources |  | 4 - Execution | Execution | [Inferred] Subcontractors (R); Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.415 – Manage Committed Costs; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.580 | 9.4.580 - Manage Vendor Resources | 9.4.580 – Manage Vendor Resources.docx | Manage Vendor Resources |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.295 – Manage Vendor / Supplier Communications; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.585 | 9.4.585 - Plan Prefabrication Resources | 9.4.585 – Plan Prefabrication Resources.docx | Plan Prefabrication Resources |  | 4 - Execution | Execution | [Inferred] Prefabrication Lead (R); Project Manager (A); Field Supervisor (C) | Project Management / Field Operations / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.590 | 9.4.590 - Manage Specialty Contractor Resources | 9.4.590 – Manage Specialty Contractor Resources.docx | Manage Specialty Contractor Resources |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.575 – Manage Subcontractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.595 | 9.4.595 - Prepare Resource Reports | 9.4.595 – Prepare Resource Reports.docx | Prepare Resource Reports |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.590 – Manage Specialty Contractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.605 | 9.4.605 - Issue Purchase Orders | 9.4.605 – Issue Purchase Orders.docx | Issue Purchase Orders |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.415 – Manage Committed Costs; 9.41.600 – Develop Procurement Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.610 | 9.4.610 - Manage Vendor Prequalification | 9.4.610 – Manage Vendor Prequalification.docx | Manage Vendor Prequalification |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.290 – Manage Subcontractor Communications; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.615 | 9.4.615 - Manage Vendor Evaluations | 9.4.615 – Manage Vendor Evaluations.docx | Manage Vendor Evaluations |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.620 | 9.4.620 - Manage Expediting | 9.4.620 – Manage Expediting.docx | Manage Expediting |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.625 | 9.4.625 - Manage Delivery Tracking | 9.4.625 – Manage Delivery Tracking.docx | Manage Delivery Tracking |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.620 – Manage Expediting; 9.41.570 – Manage Material Allocation; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.630 | 9.4.630 - Manage Material Receiving | 9.4.630 – Manage Material Receiving.docx | Manage Material Receiving |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Field Operations / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.625 – Manage Delivery Tracking; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.631 | 9.4.631 - Release of Large Feeder Wire | 9.4.631 – Release of Large Feeder Wire.docx | Release of Large Feeder Wire |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Leadership / Purchasing | Approved | SOP
9.4.635 | 9.4.635 - Manage Material Inspection | 9.4.635 – Manage Material Inspection.docx | Manage Material Inspection |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Field Operations / Quality / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.530 – Manage Quality Testing; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.640 | 9.4.640 - Manage Storage and Logistics | 9.4.640 – Manage Storage and Logistics.docx | Manage Storage and Logistics |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.570 – Manage Material Allocation; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.645 | 9.4.645 - Manage Material Handling | 9.4.645 – Manage Material Handling.docx | Manage Material Handling |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Field Operations / Logistics / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.650 | 9.4.650 - Manage Inventory | 9.4.650 – Manage Inventory.docx | Manage Inventory |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Field Operations / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.645 – Manage Material Handling; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.655 | 9.4.655 - Prepare Procurement Reports | 9.4.655 – Prepare Procurement Reports.docx | Prepare Procurement Reports |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.650 – Manage Inventory; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.660 | 9.4.660 - Manage Procurement Closeout | 9.4.660 – Manage Procurement Closeout.docx | Manage Procurement Closeout |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.465 – Manage Final Invoicing; 9.41.650 – Manage Inventory; 9.41.655 – Prepare Procurement Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.665 | 9.4.665 - Reconcile Procurement Accounts | 9.4.665 – Reconcile Procurement Accounts.docx | Reconcile Procurement Accounts |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Accounting (R); Project Manager (A); Field Supervisor (C) | Accounting / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.420 – Manage Actual Costs; 9.41.660 – Manage Procurement Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.670 | 9.4.670 - Manage Vendor Closeout | 9.4.670 – Manage Vendor Closeout.docx | Manage Vendor Closeout |  | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.615 – Manage Vendor Evaluations; 9.41.660 – Manage Procurement Closeout; 9.41.665 – Reconcile Procurement Accounts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.675 | 9.4.675 - Conduct Daily Huddles | 9.4.675 – Conduct Daily Huddles.docx | Conduct Daily Huddles |  | 4 - Execution | Execution | [Inferred] Foreman (R); Project Manager (A); Field Supervisor (C) | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.680 | 9.4.680 - Conduct Weekly Foreman Meetings | 9.4.680 – Conduct Weekly Foreman Meetings.docx | Conduct Weekly Foreman Meetings |  | 4 - Execution | Execution | [Inferred] Foreman (R); Project Manager (A); Field Supervisor (C) | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.690 | 9.4.690 - Track Manpower Utilization | 9.4.690 – Track Manpower Utilization.docx | Track Manpower Utilization |  | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Field Operations / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.695 | 9.4.695 - Track Production Quantities | 9.4.695 – Track Production Quantities.docx | Track Production Quantities |  | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.400 – Monitor Project Costs; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.700 | 9.4.700 - Track Equipment Utilization | 9.4.700 – Track Equipment Utilization.docx | Track Equipment Utilization |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.565 – Manage Equipment Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.705 | 9.4.705 - Manage Work Packaging | 9.4.705 – Manage Work Packaging.docx | Manage Work Packaging |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.335 – Prepare Lookahead Schedules; 9.41.695 – Track Production Quantities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.710 | 9.4.710 - Manage Workface Planning | 9.4.710 – Manage Workface Planning.docx | Manage Workface Planning |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.705 – Manage Work Packaging; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.715 | 9.4.715 - Manage Field Coordination | 9.4.715 – Manage Field Coordination.docx | Manage Field Coordination |  | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.680 – Conduct Weekly Foreman Meetings; 9.41.705 – Manage Work Packaging; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.720 | 9.4.720 - Conduct Productivity Analysis | 9.4.720 – Conduct Productivity Analysis.docx | Conduct Productivity Analysis |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.695 – Track Production Quantities; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.725 | 9.4.725 - Resolve Field Problems | 9.4.725 – Resolve Field Problems.docx | Resolve Field Problems |  | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.715 – Manage Field Coordination; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.735 | 9.4.735 - Perform Field Quality Verifications | 9.4.735 – Perform Field Quality Verifications.docx | Perform Field Quality Verifications |  | 4 - Execution | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) | Field Operations / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.535 – Manage Nonconformance Reports; 9.41.720 – Conduct Productivity Analysis; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.745 | 9.4.745 - Manage Field Rework | 9.4.745 – Manage Field Rework.docx | Manage Field Rework |  | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.535 – Manage Nonconformance Reports; 9.41.725 – Resolve Field Problems; 9.41.735 – Perform Field Quality Verifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.755 | 9.4.755 - Implement Field Productivity Improvements | 9.4.755 – Implement Field Productivity Improvements.docx | Implement Field Productivity Improvements |  | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.720 – Conduct Productivity Analysis; 9.41.695 – Track Production Quantities; 9.41.585 – Plan Prefabrication Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.5.020 | 9.5.020 - Handling and/or Disposing of Excess Materials | 9.5.020 – Handling and or Disposing of Excess Materials.docx | Handling and/or Disposing of Excess Materials | To establish a standardized process for conducting commissioning meetings, ensuring proper coordination between all parties during the testing, verification, and turnover phases of the project. | 5 - Commissioning | Commissioning | ¦ Project Manager (A); ¦ Commissioning Agent (R); ¦ Field Supervisor (R); ¦ Quality/QA-QC (C); ¦ Subcontractors (R) | Project Management / Quality | Approved | SOP
9.5.550 | 9.5.550 - Manage Commissioning Activities | 9.5.550 – Manage Commissioning Activities.docx | Manage Commissioning Activities | To establish a standardized process for managing all commissioning activities, ensuring systematic testing, verification, and documentation of electrical systems prior to owner turnover. | 5 - Commissioning | Commissioning | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Commissioning Agent (R); ¦ Quality/QA-QC (R); ¦ Subcontractors (R) | Project Management / Quality | Approved | SOP
9.6.005 | 9.6.005 - Prepare for Turnover (Field Perspective) | 9.6.005 – Prepare for Turnover (Field Perspective).docx | Prepare for Turnover (Field Perspective) |  | 6 - Closeout | Closeout | [Inferred] Project Manager (A) | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.555 – Manage Project Turnover Documentation; 9.41.730 – Manage As-Built Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.6.010 | 9.6.010 - Conduct Closeout Meetings | 9.6.010 – Conduct Closeout Meetings.docx | Conduct Closeout Meetings | To establish a standardized process for conducting project closeout meetings, ensuring proper coordination of all closeout activities and successful project completion. | 6 - Closeout | Closeout | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Subcontractors (R); ¦ Client/Owner (I) | Project Management | Approved | SOP
9.6.015 | 9.6.015 - Manage Project Turnover Documentation | 9.6.015 – Manage Project Turnover Documentation.docx | Manage Project Turnover Documentation |  | 6 - Closeout | Closeout | [Inferred] Project Manager (A) | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.545 – Manage Punch List Quality; 9.41.550 – Manage Commissioning Activities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.6.020 | 9.6.020 - Manage Punch List Closeout | 9.6.020 – Manage Punch List Closeout.docx | Manage Punch List Closeout |  | 6 - Closeout | Closeout | [Inferred] Quality Inspector (C); Project Manager (A) | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.760 – Prepare for Turnover (Field Perspective); 9.41.555 – Manage Project Turnover Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.030 | 9.6.030 - Manage As-Built Drawings | 9.6.030 – Manage As Built Drawings.docx | Manage As-Built Drawings | To establish a standardized process for managing as-built drawings, ensuring accurate documentation of installed conditions for owner records and future maintenance. | 6 - Closeout | Closeout | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Foreman (R); ¦ Project Engineer/APM (R) | Project Management / Field Operations | Approved | SOP
9.6.035 | 9.6.035 - Submit Warranties | 9.6.035 – Submit Warranties.docx | Submit Warranties |  | 6 - Closeout | Closeout | [Inferred] Project Manager (A) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.770 – Manage Punch List Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.040 | 9.6.040 - Submit O&M Manuals | 9.6.040 – Submit O&M Manuals.docx | Submit O&M Manuals |  | 6 - Closeout | Closeout | [Inferred] Project Manager (A) | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.550 – Manage Commissioning Activities; 9.41.775 – Submit Warranties; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.050 | 9.6.050 - Provide Owner Training | 9.6.050 – Provide Owner Training.docx | Provide Owner Training |  | 6 - Closeout | Closeout | [Inferred] Branch Manager (C); Project Manager (A) | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.550 – Manage Commissioning Activities; 9.41.780 – Submit O&M Manuals; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.065 | 9.6.065 - Archive Project Documentation | 9.6.065 – Archive Project Documentation.docx | Archive Project Documentation |  | 6 - Closeout | Closeout | [Inferred] Site Administrator (R); Project Manager (A) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.265 – Manage Closeout Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.070 | 9.6.070 - Conduct Post-Project Review | 9.6.070 – Conduct Post Project Review.docx | Conduct Post-Project Review | To establish a standardized process for conducting post-project reviews, evaluating project performance, and identifying successes and areas for improvement. | 6 - Closeout | Closeout | ¦ Branch Manager (A); ¦ Project Manager (R); ¦ Field Supervisor (R); ¦ Operations Manager (C) | Project Management | Approved | SOP
9.6.080 | 9.6.080 - Capture Client Feedback | 9.6.080 – Capture Client Feedback.docx | Capture Client Feedback | To establish a standardized process for capturing client feedback at project completion, enabling continuous improvement and strengthening client relationships. | 6 - Closeout | Closeout | ¦ Branch Manager (A); ¦ Project Manager (R); ¦ Business Development (C); ¦ Executive Committee (I) | Project Management | Approved | SOP
9.6.085 | 9.6.085 - Document Lessons Learned | 9.6.085 – Document Lessons Learned.docx | Document Lessons Learned | To establish a standardized process for documenting lessons learned throughout and at the completion of projects, creating an organizational knowledge base for continuous improvement. | 6 - Closeout | Closeout | ¦ Operations Manager (A); ¦ Project Manager (R); ¦ Field Supervisor (R); ¦ Branch Manager (C) | Project Management | Approved | SOP

## Coverage Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category
9.1.050 - Prepare Construction Takeoff | Oversees Prepare Construction Takeoff | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 1 - Estimating
9.2.005 - Review Contract for High Risk Clauses | Oversees Review Contract for High Risk Clauses | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.010 - Team Selection | Selects Project Manager and assigns or approves final team assignments; Allocates resources across projects; Resolves resource conflicts. | Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Identifies required roles and skill sets; Recommends team members; Coordinates with Branch Manager on availability. | Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Validates field leadership assignments; Confirms crew availability and capability | General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Ensures safety-qualified personnel are assigned, Reviews site-specific safety requirements. | Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Informed of procurement resource needs | Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Informed of prefab support requirements | Prefabrication Lead | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction
9.2.015 - Project Turnover Meeting | Oversees closeout for Project Turnover Meeting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.020 - Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.020 - Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | Oversees Review Contract for Unfavorable or High-Risk Clauses | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.040 - Project Manager Reviews Plans Specifications & Schedule | Coordinates scheduling for Project Manager Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.040 - Project Manager Reviews Plans Specifications & Schedule | Manages technical documentation for Project Manager Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | Coordinates scheduling for Field Supervisor Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | Manages technical documentation for Field Supervisor Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.055 - Compare Estimated vs Planned Performance | Provides estimating support for Compare Estimated vs Planned Performance | Estimator | Sec. 9.9 Estimating Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.055 - Compare Estimated vs Planned Performance | Oversees Compare Estimated vs Planned Performance | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.057 - Identify VE and Prefabrication Opportunities | Coordinates prefabrication for Identify VE and Prefabrication Opportunities | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.057 - Identify VE and Prefabrication Opportunities | Oversees Identify VE and Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.060 - Create Issue List and Begin RFI Process | Manages overall issue resolution; Prioritizes RFIs; Tracks responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create Issue List and Begin RFI Process | Creates and submits RFIs; Maintains issue log; Follows up on responses ¦ | ¦ Assistant PM/Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create Issue List and Begin RFI Process | Contributes constructability issues; Reviews RFI responses for field impact ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create Issue List and Begin RFI Process | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | Coordinates site visit; Documents findings; Integrates into project planning ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | Conducts physical site inspection; Identifies constructability and logistics issues ¦ | ¦ Field Leadership | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | Assesses site safety conditions; Identifies hazards and requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction
9.2.080 - Prepare Material Handling Plan | Oversees Prepare Material Handling Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.090 - Develop Labor Budget | Provides financial support for Develop Labor Budget | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.090 - Develop Labor Budget | Oversees Develop Labor Budget | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.100 - Prepare Layout & Sequencing Plan | Oversees Prepare Layout & Sequencing Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.110 - Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.110 - Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.120 - Establish Tracking & Control Systems | Oversees Establish Tracking & Control Systems | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.130 - Construction Execution Kickoff Meeting | Leads coordination for Construction Execution Kickoff Meeting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.140 - Develop Project Budget | Provides financial support for Develop Project Budget | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.140 - Develop Project Budget | Oversees Develop Project Budget | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.160 - Develop Procurement Plan | Manages procurement for Develop Procurement Plan | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.160 - Develop Procurement Plan | Oversees Develop Procurement Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.3.010 - Setup Office Trailer | Approves trailer location and configuration; Coordinates delivery timing ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization
9.3.010 - Setup Office Trailer | Oversees physical setup; Coordinates with delivery vendor; Ensures utility connections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.010 - Setup Office Trailer | Sets up office equipment and supplies; Establishes filing systems ¦ | ¦ Site Administrator | Sec. 9.8 Site Administration | Covered | No change required. | 3 - Mobilization
9.3.010 - Setup Office Trailer | Reviews placement for safety compliance; Ensures egress requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization
9.3.010 - Setup Office Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 3 - Mobilization
9.3.020 - Setup Storage Trailer | Oversees setup and organization; Establishes security protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.020 - Setup Storage Trailer | Coordinates physical placement; Organizes interior layout ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.020 - Setup Storage Trailer | Coordinates material delivery timing with storage availability ¦ | ¦ Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 3 - Mobilization
9.3.020 - Setup Storage Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization
9.3.030 - Setup Site Fencing and Access Control | Oversees fencing installation; Establishes access protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.030 - Setup Site Fencing and Access Control | Coordinates installation; Manages gate operations ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.030 - Setup Site Fencing and Access Control | Defines safety requirements; Reviews emergency egress ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization
9.3.030 - Setup Site Fencing and Access Control | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | Oversees installation; Ensures code compliance ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | Installs temporary power system; Makes connections ¦ | ¦ Foreman/Journeyman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | Reviews safety requirements; Verifies GFCI protection ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | Coordinates with utility company; Approves power plan ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Electrical Subcontractor | Sec. 9.2 General Directives | Covered | No change required. | 3 - Mobilization
9.3.050 - Setup Temporary Water | Coordinates site setup for Setup Temporary Water | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.050 - Setup Temporary Water | Oversees Setup Temporary Water | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.060 - Setup Sanitary Facilities | Coordinates site setup for Setup Sanitary Facilities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.060 - Setup Sanitary Facilities | Oversees Setup Sanitary Facilities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.070 - Setup Temporary Lighting | Coordinates site setup for Setup Temporary Lighting | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.070 - Setup Temporary Lighting | Oversees Setup Temporary Lighting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.080 - Setup Signage | Coordinates site setup for Setup Signage | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.080 - Setup Signage | Oversees Setup Signage | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.090 - Setup Security | Coordinates site setup for Setup Security | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.090 - Setup Security | Oversees Setup Security | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.100 - Setup Laydown Area | Coordinates site setup for Setup Laydown Area | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.100 - Setup Laydown Area | Oversees Setup Laydown Area | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.110 - Setup Equipment Staging | Coordinates site setup for Setup Equipment Staging | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.110 - Setup Equipment Staging | Oversees Setup Equipment Staging | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.120 - Setup Parking | Coordinates site setup for Setup Parking | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.120 - Setup Parking | Oversees Setup Parking | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.470 - Develop Site-Specific Safety Plan | Reviews for safety compliance for Develop Site-Specific Safety Plan | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.470 - Develop Site-Specific Safety Plan | Oversees Develop Site-Specific Safety Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.470 - Develop Site-Specific Safety Plan | Field coordination for Develop Site-Specific Safety Plan | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.4.010 - Conduct Coordination Meetings | Leads coordination for Conduct Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.010 - Conduct Coordination Meetings | Field coordination for Conduct Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.020 - Conduct Subcontractor Coordination Meetings | Performs subcontracted work for Conduct Subcontractor Coordination Meetings | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.020 - Conduct Subcontractor Coordination Meetings | Leads coordination for Conduct Subcontractor Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.020 - Conduct Subcontractor Coordination Meetings | Field coordination for Conduct Subcontractor Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.030 - Conduct Client/Owner Meetings | Participates in client communications for Conduct Client/Owner Meetings | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution
9.4.030 - Conduct Client/Owner Meetings | Oversees Conduct Client/Owner Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.030 - Conduct Client/Owner Meetings | Field coordination for Conduct Client/Owner Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.040 - Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.040 - Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.040 - Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Coordinates prefabrication for Identify Value Engineering & Prefabrication Opportunities | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Oversees Identify Value Engineering & Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Field coordination for Identify Value Engineering & Prefabrication Opportunities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.050 - Conduct Prefabrication Coordination Meetings | Coordinates prefabrication for Conduct Prefabrication Coordination Meetings | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.050 - Conduct Prefabrication Coordination Meetings | Leads coordination for Conduct Prefabrication Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.050 - Conduct Prefabrication Coordination Meetings | Field coordination for Conduct Prefabrication Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.055 - Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.055 - Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.055 - Procurement of Large Feeder Wire | Field coordination for Procurement of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.060 - Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.060 - Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.060 - Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.190 - Document Filing Standards | Manages documentation for Document Filing Standards | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution
9.4.190 - Document Filing Standards | Oversees Document Filing Standards | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.190 - Document Filing Standards | Field coordination for Document Filing Standards | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.195 - Manage Project Documentation System | Manages documentation for Manage Project Documentation System | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution
9.4.195 - Manage Project Documentation System | Oversees Manage Project Documentation System | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.195 - Manage Project Documentation System | Field coordination for Manage Project Documentation System | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.200 - Manage Submittals | Manages technical documentation for Manage Submittals | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.200 - Manage Submittals | Field coordination for Manage Submittals | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.205 - Manage RFIs (Requests for Information) | Manages technical documentation for Manage RFIs (Requests for Information) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.205 - Manage RFIs (Requests for Information) | Field coordination for Manage RFIs (Requests for Information) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.210 - Manage Meeting Minutes | Manages documentation for Manage Meeting Minutes | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution
9.4.210 - Manage Meeting Minutes | Oversees Manage Meeting Minutes | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.210 - Manage Meeting Minutes | Field coordination for Manage Meeting Minutes | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.215 - Manage Daily Reports | Manages field operations for Manage Daily Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.215 - Manage Daily Reports | Oversees Manage Daily Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.220 - Manage Drawing Logs | Manages technical documentation for Manage Drawing Logs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.220 - Manage Drawing Logs | Field coordination for Manage Drawing Logs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.225 - Manage Specifications | Manages technical documentation for Manage Specifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.225 - Manage Specifications | Field coordination for Manage Specifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.230 - Manage Correspondence | Manages documentation for Manage Correspondence | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution
9.4.230 - Manage Correspondence | Oversees Manage Correspondence | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.230 - Manage Correspondence | Field coordination for Manage Correspondence | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.235 - Manage Permits | Oversees Manage Permits | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.235 - Manage Permits | Field coordination for Manage Permits | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.240 - Manage Inspection Reports | Oversees Manage Inspection Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.240 - Manage Inspection Reports | Field coordination for Manage Inspection Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.270 - Manage Project Communications | Manages communications for Manage Project Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.270 - Manage Project Communications | Field coordination for Manage Project Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.275 - Manage Internal Communications | Manages communications for Manage Internal Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.275 - Manage Internal Communications | Field coordination for Manage Internal Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.280 - Manage External Communications | Manages communications for Manage External Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.280 - Manage External Communications | Field coordination for Manage External Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.285 - Manage Client/Owner Communications | Participates in client communications for Manage Client/Owner Communications | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution
9.4.285 - Manage Client/Owner Communications | Manages communications for Manage Client/Owner Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.285 - Manage Client/Owner Communications | Field coordination for Manage Client/Owner Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.290 - Manage Subcontractor Communications | Performs subcontracted work for Manage Subcontractor Communications | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.290 - Manage Subcontractor Communications | Manages communications for Manage Subcontractor Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.290 - Manage Subcontractor Communications | Field coordination for Manage Subcontractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.295 - Manage Vendor Supplier Communications | Manages procurement for Manage Vendor Supplier Communications | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.295 - Manage Vendor Supplier Communications | Manages communications for Manage Vendor Supplier Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.295 - Manage Vendor Supplier Communications | Field coordination for Manage Vendor Supplier Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.300 - Manage Architect/Engineer Communications | Manages communications for Manage Architect/Engineer Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.300 - Manage Architect/Engineer Communications | Field coordination for Manage Architect/Engineer Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.305 - Manage Regulatory/Authority Communications | Manages communications for Manage Regulatory/Authority Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.305 - Manage Regulatory/Authority Communications | Field coordination for Manage Regulatory/Authority Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.310 - Manage General Contractor Communications | Manages communications for Manage General Contractor Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.310 - Manage General Contractor Communications | Field coordination for Manage General Contractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.315 - Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.315 - Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.315 - Develop Project Schedule | Field coordination for Develop Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.320 - Update Project Schedule | Coordinates scheduling for Update Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.320 - Update Project Schedule | Oversees Update Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.320 - Update Project Schedule | Field coordination for Update Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.325 - Monitor Schedule Performance | Coordinates scheduling for Monitor Schedule Performance | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.325 - Monitor Schedule Performance | Oversees Monitor Schedule Performance | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.325 - Monitor Schedule Performance | Field coordination for Monitor Schedule Performance | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.330 - Develop Schedule Recovery Plans | Coordinates scheduling for Develop Schedule Recovery Plans | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.330 - Develop Schedule Recovery Plans | Oversees Develop Schedule Recovery Plans | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.330 - Develop Schedule Recovery Plans | Field coordination for Develop Schedule Recovery Plans | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.335 - Prepare Lookahead Schedules | Coordinates scheduling for Prepare Lookahead Schedules | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.335 - Prepare Lookahead Schedules | Oversees Prepare Lookahead Schedules | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.335 - Prepare Lookahead Schedules | Field coordination for Prepare Lookahead Schedules | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.340 - Manage Resource-Loaded Schedules | Coordinates scheduling for Manage Resource-Loaded Schedules | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.340 - Manage Resource-Loaded Schedules | Oversees Manage Resource-Loaded Schedules | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.340 - Manage Resource-Loaded Schedules | Field coordination for Manage Resource-Loaded Schedules | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.345 - Conduct Schedule Review Meetings | Coordinates scheduling for Conduct Schedule Review Meetings | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.345 - Conduct Schedule Review Meetings | Oversees Conduct Schedule Review Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.345 - Conduct Schedule Review Meetings | Field coordination for Conduct Schedule Review Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.350 - Manage Schedule Change Requests | Coordinates scheduling for Manage Schedule Change Requests | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.350 - Manage Schedule Change Requests | Oversees Manage Schedule Change Requests | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.350 - Manage Schedule Change Requests | Field coordination for Manage Schedule Change Requests | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.355 - Manage Project Scope | Manages contract changes for Manage Project Scope | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.355 - Manage Project Scope | Field coordination for Manage Project Scope | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.360 - Manage Change Orders | Manages contract changes for Manage Change Orders | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.360 - Manage Change Orders | Field coordination for Manage Change Orders | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.365 - Manage Potential Change Orders (PCOs) | Manages contract changes for Manage Potential Change Orders (PCOs) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.365 - Manage Potential Change Orders (PCOs) | Field coordination for Manage Potential Change Orders (PCOs) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.370 - Manage Owner Directives | Participates in client communications for Manage Owner Directives | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution
9.4.370 - Manage Owner Directives | Oversees Manage Owner Directives | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.370 - Manage Owner Directives | Field coordination for Manage Owner Directives | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.375 - Manage Scope Clarifications | Manages contract changes for Manage Scope Clarifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.375 - Manage Scope Clarifications | Field coordination for Manage Scope Clarifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.380 - Manage Backcharges | Manages contract changes for Manage Backcharges | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.380 - Manage Backcharges | Field coordination for Manage Backcharges | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.385 - Manage Force Account Work | Manages contract changes for Manage Force Account Work | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.385 - Manage Force Account Work | Field coordination for Manage Force Account Work | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.390 - Manage Claims | Provides executive approval for Manage Claims | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution
9.4.390 - Manage Claims | Oversees Manage Claims | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.390 - Manage Claims | Field coordination for Manage Claims | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.400 - Monitor Project Costs | Provides financial support for Monitor Project Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.400 - Monitor Project Costs | Oversees Monitor Project Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.400 - Monitor Project Costs | Field coordination for Monitor Project Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.405 - Manage Cost Forecasts | Provides financial support for Manage Cost Forecasts | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.405 - Manage Cost Forecasts | Oversees Manage Cost Forecasts | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.405 - Manage Cost Forecasts | Field coordination for Manage Cost Forecasts | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.410 - Manage Cost Codes | Manages financial documentation for Manage Cost Codes | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.410 - Manage Cost Codes | Oversees Manage Cost Codes | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.410 - Manage Cost Codes | Field coordination for Manage Cost Codes | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.415 - Manage Committed Costs | Provides financial support for Manage Committed Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.415 - Manage Committed Costs | Oversees Manage Committed Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.415 - Manage Committed Costs | Field coordination for Manage Committed Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.420 - Manage Actual Costs | Provides financial support for Manage Actual Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.420 - Manage Actual Costs | Oversees Manage Actual Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.420 - Manage Actual Costs | Field coordination for Manage Actual Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.425 - Manage Job Cost Reports | Manages financial documentation for Manage Job Cost Reports | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.425 - Manage Job Cost Reports | Oversees Manage Job Cost Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.425 - Manage Job Cost Reports | Field coordination for Manage Job Cost Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.430 - Manage Profit Projections | Provides financial support for Manage Profit Projections | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.430 - Manage Profit Projections | Oversees Manage Profit Projections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.430 - Manage Profit Projections | Field coordination for Manage Profit Projections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.435 - Manage Cost-to-Complete | Provides financial support for Manage Cost-to-Complete | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.435 - Manage Cost-to-Complete | Oversees Manage Cost-to-Complete | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.435 - Manage Cost-to-Complete | Field coordination for Manage Cost-to-Complete | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.440 - Prepare Billing Schedule | Manages financial documentation for Prepare Billing Schedule | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.440 - Prepare Billing Schedule | Coordinates scheduling for Prepare Billing Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.440 - Prepare Billing Schedule | Oversees Prepare Billing Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.440 - Prepare Billing Schedule | Field coordination for Prepare Billing Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.445 - Prepare Monthly Pay Applications | Manages financial documentation for Prepare Monthly Pay Applications | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.445 - Prepare Monthly Pay Applications | Oversees Prepare Monthly Pay Applications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.445 - Prepare Monthly Pay Applications | Field coordination for Prepare Monthly Pay Applications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.450 - Track Accounts Receivable | Manages financial documentation for Track Accounts Receivable | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.450 - Track Accounts Receivable | Oversees Track Accounts Receivable | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.450 - Track Accounts Receivable | Field coordination for Track Accounts Receivable | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.455 - Manage Lien Waivers | Oversees Manage Lien Waivers | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.455 - Manage Lien Waivers | Field coordination for Manage Lien Waivers | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.460 - Manage Retainage | Manages financial documentation for Manage Retainage | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.460 - Manage Retainage | Oversees Manage Retainage | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.460 - Manage Retainage | Field coordination for Manage Retainage | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.465 - Manage Final Invoicing | Oversees Manage Final Invoicing | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.465 - Manage Final Invoicing | Field coordination for Manage Final Invoicing | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.475 - Conduct Safety Orientation | Leads safety activities for Conduct Safety Orientation | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.475 - Conduct Safety Orientation | Oversees Conduct Safety Orientation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.475 - Conduct Safety Orientation | Field coordination for Conduct Safety Orientation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.480 - Conduct Safety Inspections | Leads safety activities for Conduct Safety Inspections | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.480 - Conduct Safety Inspections | Oversees Conduct Safety Inspections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.480 - Conduct Safety Inspections | Field coordination for Conduct Safety Inspections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.485 - Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.485 - Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.485 - Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.490 - Report Safety Incidents | Leads safety activities for Report Safety Incidents | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.490 - Report Safety Incidents | Oversees Report Safety Incidents | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.490 - Report Safety Incidents | Field coordination for Report Safety Incidents | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.495 - Investigate Accidents | Leads safety activities for Investigate Accidents | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.495 - Investigate Accidents | Oversees Investigate Accidents | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.495 - Investigate Accidents | Field coordination for Investigate Accidents | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.500 - Conduct Emergency Preparedness | Leads safety activities for Conduct Emergency Preparedness | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.500 - Conduct Emergency Preparedness | Oversees Conduct Emergency Preparedness | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.500 - Conduct Emergency Preparedness | Field coordination for Conduct Emergency Preparedness | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.505 - Conduct Safety Compliance Audits | Reviews for safety compliance for Conduct Safety Compliance Audits | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.505 - Conduct Safety Compliance Audits | Oversees Conduct Safety Compliance Audits | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.505 - Conduct Safety Compliance Audits | Field coordination for Conduct Safety Compliance Audits | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.510 - Provide Safety Training | Reviews for safety compliance for Provide Safety Training | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.510 - Provide Safety Training | Oversees Provide Safety Training | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.510 - Provide Safety Training | Field coordination for Provide Safety Training | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.515 - Develop Quality Management Plan | Performs quality activities for Develop Quality Management Plan | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.515 - Develop Quality Management Plan | Oversees Develop Quality Management Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.515 - Develop Quality Management Plan | Field coordination for Develop Quality Management Plan | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.520 - Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.520 - Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.520 - Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.525 - Conduct Quality Inspections | Performs quality activities for Conduct Quality Inspections | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.525 - Conduct Quality Inspections | Oversees Conduct Quality Inspections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.525 - Conduct Quality Inspections | Field coordination for Conduct Quality Inspections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.530 - Manage Quality Testing | Provides quality oversight for Manage Quality Testing | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.530 - Manage Quality Testing | Oversees Manage Quality Testing | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.530 - Manage Quality Testing | Field coordination for Manage Quality Testing | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.535 - Manage Nonconformance Reports (NCRs) | Performs quality activities for Manage Nonconformance Reports (NCRs) | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.535 - Manage Nonconformance Reports (NCRs) | Oversees Manage Nonconformance Reports (NCRs) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.535 - Manage Nonconformance Reports (NCRs) | Field coordination for Manage Nonconformance Reports (NCRs) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.540 - Manage Quality Records | Provides quality oversight for Manage Quality Records | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.540 - Manage Quality Records | Oversees Manage Quality Records | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.540 - Manage Quality Records | Field coordination for Manage Quality Records | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.545 - Manage Punch List Quality | Provides quality oversight for Manage Punch List Quality | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.545 - Manage Punch List Quality | Oversees Manage Punch List Quality | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.545 - Manage Punch List Quality | Field coordination for Manage Punch List Quality | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.560 - Manage Manpower Allocation | Manages field operations for Manage Manpower Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.560 - Manage Manpower Allocation | Oversees Manage Manpower Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.565 - Manage Equipment Allocation | Oversees Manage Equipment Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.565 - Manage Equipment Allocation | Field coordination for Manage Equipment Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.570 - Manage Material Allocation | Oversees Manage Material Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.570 - Manage Material Allocation | Field coordination for Manage Material Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.576 - Manage Subcontractor Resources | Performs subcontracted work for Manage Subcontractor Resources | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.576 - Manage Subcontractor Resources | Oversees Manage Subcontractor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.576 - Manage Subcontractor Resources | Field coordination for Manage Subcontractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.580 - Manage Vendor Resources | Manages procurement for Manage Vendor Resources | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.580 - Manage Vendor Resources | Oversees Manage Vendor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.580 - Manage Vendor Resources | Field coordination for Manage Vendor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.585 - Plan Prefabrication Resources | Coordinates prefabrication for Plan Prefabrication Resources | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.585 - Plan Prefabrication Resources | Oversees Plan Prefabrication Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.585 - Plan Prefabrication Resources | Field coordination for Plan Prefabrication Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.590 - Manage Specialty Contractor Resources | Oversees Manage Specialty Contractor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.590 - Manage Specialty Contractor Resources | Field coordination for Manage Specialty Contractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.595 - Prepare Resource Reports | Oversees Prepare Resource Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.595 - Prepare Resource Reports | Field coordination for Prepare Resource Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.605 - Issue Purchase Orders | Manages procurement for Issue Purchase Orders | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.605 - Issue Purchase Orders | Oversees Issue Purchase Orders | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.605 - Issue Purchase Orders | Field coordination for Issue Purchase Orders | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.610 - Manage Vendor Prequalification | Manages procurement for Manage Vendor Prequalification | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.610 - Manage Vendor Prequalification | Oversees Manage Vendor Prequalification | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.610 - Manage Vendor Prequalification | Field coordination for Manage Vendor Prequalification | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.615 - Manage Vendor Evaluations | Manages procurement for Manage Vendor Evaluations | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.615 - Manage Vendor Evaluations | Oversees Manage Vendor Evaluations | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.615 - Manage Vendor Evaluations | Field coordination for Manage Vendor Evaluations | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.620 - Manage Expediting | Manages procurement for Manage Expediting | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.620 - Manage Expediting | Oversees Manage Expediting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.620 - Manage Expediting | Field coordination for Manage Expediting | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.625 - Manage Delivery Tracking | Manages procurement for Manage Delivery Tracking | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.625 - Manage Delivery Tracking | Oversees Manage Delivery Tracking | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.625 - Manage Delivery Tracking | Field coordination for Manage Delivery Tracking | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.630 - Manage Material Receiving | Manages procurement for Manage Material Receiving | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.630 - Manage Material Receiving | Oversees Manage Material Receiving | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.630 - Manage Material Receiving | Field coordination for Manage Material Receiving | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.631 - Release of Large Feeder Wire | Oversees Release of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.631 - Release of Large Feeder Wire | Field coordination for Release of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.635 - Manage Material Inspection | Oversees Manage Material Inspection | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.635 - Manage Material Inspection | Field coordination for Manage Material Inspection | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.640 - Manage Storage and Logistics | Oversees Manage Storage and Logistics | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.640 - Manage Storage and Logistics | Field coordination for Manage Storage and Logistics | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.645 - Manage Material Handling | Oversees Manage Material Handling | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.645 - Manage Material Handling | Field coordination for Manage Material Handling | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.650 - Manage Inventory | Manages procurement for Manage Inventory | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.650 - Manage Inventory | Oversees Manage Inventory | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.650 - Manage Inventory | Field coordination for Manage Inventory | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.655 - Prepare Procurement Reports | Manages procurement for Prepare Procurement Reports | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.655 - Prepare Procurement Reports | Oversees Prepare Procurement Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.655 - Prepare Procurement Reports | Field coordination for Prepare Procurement Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.660 - Manage Procurement Closeout | Manages procurement for Manage Procurement Closeout | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.660 - Manage Procurement Closeout | Oversees closeout for Manage Procurement Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.660 - Manage Procurement Closeout | Field coordination for Manage Procurement Closeout | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.665 - Reconcile Procurement Accounts | Manages procurement for Reconcile Procurement Accounts | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.665 - Reconcile Procurement Accounts | Manages financial documentation for Reconcile Procurement Accounts | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.665 - Reconcile Procurement Accounts | Oversees Reconcile Procurement Accounts | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.665 - Reconcile Procurement Accounts | Field coordination for Reconcile Procurement Accounts | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.670 - Manage Vendor Closeout | Manages procurement for Manage Vendor Closeout | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.670 - Manage Vendor Closeout | Oversees closeout for Manage Vendor Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.670 - Manage Vendor Closeout | Field coordination for Manage Vendor Closeout | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.675 - Conduct Daily Huddles | Leads crew activities for Conduct Daily Huddles | Foreman | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.675 - Conduct Daily Huddles | Oversees Conduct Daily Huddles | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.675 - Conduct Daily Huddles | Field coordination for Conduct Daily Huddles | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.680 - Conduct Weekly Foreman Meetings | Leads crew activities for Conduct Weekly Foreman Meetings | Foreman | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.680 - Conduct Weekly Foreman Meetings | Oversees Conduct Weekly Foreman Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.680 - Conduct Weekly Foreman Meetings | Field coordination for Conduct Weekly Foreman Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.690 - Track Manpower Utilization | Manages field operations for Track Manpower Utilization | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.690 - Track Manpower Utilization | Oversees Track Manpower Utilization | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.695 - Track Production Quantities | Manages field operations for Track Production Quantities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.695 - Track Production Quantities | Oversees Track Production Quantities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.700 - Track Equipment Utilization | Oversees Track Equipment Utilization | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.700 - Track Equipment Utilization | Field coordination for Track Equipment Utilization | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.705 - Manage Work Packaging | Oversees Manage Work Packaging | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.705 - Manage Work Packaging | Field coordination for Manage Work Packaging | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.710 - Manage Workface Planning | Oversees Manage Workface Planning | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.710 - Manage Workface Planning | Field coordination for Manage Workface Planning | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.715 - Manage Field Coordination | Manages field operations for Manage Field Coordination | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.715 - Manage Field Coordination | Oversees Manage Field Coordination | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.720 - Conduct Productivity Analysis | Oversees Conduct Productivity Analysis | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.720 - Conduct Productivity Analysis | Field coordination for Conduct Productivity Analysis | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.725 - Resolve Field Problems | Manages field operations for Resolve Field Problems | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.725 - Resolve Field Problems | Oversees Resolve Field Problems | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.735 - Perform Field Quality Verifications | Provides quality oversight for Perform Field Quality Verifications | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.735 - Perform Field Quality Verifications | Oversees Perform Field Quality Verifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.735 - Perform Field Quality Verifications | Field coordination for Perform Field Quality Verifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.745 - Manage Field Rework | Manages field operations for Manage Field Rework | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.745 - Manage Field Rework | Oversees Manage Field Rework | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.755 - Implement Field Productivity Improvements | Oversees Implement Field Productivity Improvements | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.755 - Implement Field Productivity Improvements | Field coordination for Implement Field Productivity Improvements | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.5.020 - Handling and/or Disposing of Excess Materials | Leads meeting coordination; Tracks commissioning progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning
9.5.020 - Handling and/or Disposing of Excess Materials | Conducts testing; Documents results; Identifies deficiencies ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.020 - Handling and/or Disposing of Excess Materials | Supports testing activities; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning
9.5.020 - Handling and/or Disposing of Excess Materials | Verifies quality requirements; Reviews test results ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | Covered | No change required. | 5 - Commissioning
9.5.020 - Handling and/or Disposing of Excess Materials | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Overall commissioning management; Schedule coordination ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Supports testing; Ensures systems ready; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Executes testing protocols; Documents results ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Verifies compliance; Reviews documentation ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.6.005 - Prepare for Turnover (Field Perspective) | Oversees closeout for Prepare for Turnover (Field Perspective) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | Leads closeout meetings; Tracks closeout progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | Reports field status; Coordinates punch completion ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | Participate; Complete their closeout requirements ¦ | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Client/Owner | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.015 - Manage Project Turnover Documentation | Oversees closeout for Manage Project Turnover Documentation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.020 - Manage Punch List Closeout | Provides quality oversight for Manage Punch List Closeout | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.020 - Manage Punch List Closeout | Oversees closeout for Manage Punch List Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | Manages as-built process; Submits final drawings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | Reviews markups for accuracy; Coordinates with field ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | Creates field markups; Documents actual conditions ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Engineer/APM | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.035 - Submit Warranties | Oversees Submit Warranties | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.040 - Submit O&M Manuals | Oversees closeout for Submit O&M Manuals | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.050 - Provide Owner Training | Participates in client communications for Provide Owner Training | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 6 - Closeout
9.6.050 - Provide Owner Training | Oversees Provide Owner Training | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.065 - Archive Project Documentation | Manages documentation for Archive Project Documentation | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 6 - Closeout
9.6.065 - Archive Project Documentation | Oversees Archive Project Documentation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | Oversees review process; Approves action items ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | Leads review meeting; Compiles findings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | Provides field perspective; Shares observations ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | Oversees feedback process; Reviews results ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | Conducts feedback meeting; Documents responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | Uses feedback for relationship management ¦ | ¦ Business Development | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Executive Committee | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | Maintains lessons learned database; Ensures implementation ¦ | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | Documents project-specific lessons; Submits for review ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | Captures field-level learnings; Contributes to documentation ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout

## RACI Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | RACI
9.1.050 - Prepare Construction Takeoff | Oversees Prepare Construction Takeoff | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 1 - Estimating | R
9.2.005 - Review Contract for High Risk Clauses | Oversees Review Contract for High Risk Clauses | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.010 - Team Selection | Selects Project Manager and assigns or approves final team assignments; Allocates resources across projects; Resolves resource conflicts. | Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 2 - Preconstruction | A
9.2.010 - Team Selection | Identifies required roles and skill sets; Recommends team members; Coordinates with Branch Manager on availability. | Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | R
9.2.010 - Team Selection | Validates field leadership assignments; Confirms crew availability and capability | General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.010 - Team Selection | Ensures safety-qualified personnel are assigned, Reviews site-specific safety requirements. | Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.010 - Team Selection | Informed of procurement resource needs | Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 2 - Preconstruction | I
9.2.010 - Team Selection | Informed of prefab support requirements | Prefabrication Lead | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction | I
9.2.010 - Team Selection | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction | I
9.2.015 - Project Turnover Meeting | Oversees closeout for Project Turnover Meeting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.020 - Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.020 - Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | Oversees Review Contract for Unfavorable or High-Risk Clauses | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.040 - Project Manager Reviews Plans Specifications & Schedule | Coordinates scheduling for Project Manager Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.040 - Project Manager Reviews Plans Specifications & Schedule | Manages technical documentation for Project Manager Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | Coordinates scheduling for Field Supervisor Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | Manages technical documentation for Field Supervisor Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.055 - Compare Estimated vs Planned Performance | Provides estimating support for Compare Estimated vs Planned Performance | Estimator | Sec. 9.9 Estimating Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.055 - Compare Estimated vs Planned Performance | Oversees Compare Estimated vs Planned Performance | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.057 - Identify VE and Prefabrication Opportunities | Coordinates prefabrication for Identify VE and Prefabrication Opportunities | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.057 - Identify VE and Prefabrication Opportunities | Oversees Identify VE and Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.060 - Create Issue List and Begin RFI Process | Manages overall issue resolution; Prioritizes RFIs; Tracks responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | A
9.2.060 - Create Issue List and Begin RFI Process | Creates and submits RFIs; Maintains issue log; Follows up on responses ¦ | ¦ Assistant PM/Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction | R
9.2.060 - Create Issue List and Begin RFI Process | Contributes constructability issues; Reviews RFI responses for field impact ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction | C
9.2.060 - Create Issue List and Begin RFI Process | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.070 - Conduct Site Visit | Coordinates site visit; Documents findings; Integrates into project planning ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | A
9.2.070 - Conduct Site Visit | Conducts physical site inspection; Identifies constructability and logistics issues ¦ | ¦ Field Leadership | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction | R
9.2.070 - Conduct Site Visit | Assesses site safety conditions; Identifies hazards and requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction | R
9.2.070 - Conduct Site Visit | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.080 - Prepare Material Handling Plan | Oversees Prepare Material Handling Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.090 - Develop Labor Budget | Provides financial support for Develop Labor Budget | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.090 - Develop Labor Budget | Oversees Develop Labor Budget | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.100 - Prepare Layout & Sequencing Plan | Oversees Prepare Layout & Sequencing Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.110 - Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.110 - Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.120 - Establish Tracking & Control Systems | Oversees Establish Tracking & Control Systems | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.130 - Construction Execution Kickoff Meeting | Leads coordination for Construction Execution Kickoff Meeting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.140 - Develop Project Budget | Provides financial support for Develop Project Budget | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.140 - Develop Project Budget | Oversees Develop Project Budget | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.160 - Develop Procurement Plan | Manages procurement for Develop Procurement Plan | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.160 - Develop Procurement Plan | Oversees Develop Procurement Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.3.010 - Setup Office Trailer | Approves trailer location and configuration; Coordinates delivery timing ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization | A
9.3.010 - Setup Office Trailer | Oversees physical setup; Coordinates with delivery vendor; Ensures utility connections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | R
9.3.010 - Setup Office Trailer | Sets up office equipment and supplies; Establishes filing systems ¦ | ¦ Site Administrator | Sec. 9.8 Site Administration | Covered | No change required. | 3 - Mobilization | R
9.3.010 - Setup Office Trailer | Reviews placement for safety compliance; Ensures egress requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization | C
9.3.010 - Setup Office Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 3 - Mobilization | C
9.3.020 - Setup Storage Trailer | Oversees setup and organization; Establishes security protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | A
9.3.020 - Setup Storage Trailer | Coordinates physical placement; Organizes interior layout ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | R
9.3.020 - Setup Storage Trailer | Coordinates material delivery timing with storage availability ¦ | ¦ Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 3 - Mobilization | C
9.3.020 - Setup Storage Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization | C
9.3.030 - Setup Site Fencing and Access Control | Oversees fencing installation; Establishes access protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | A
9.3.030 - Setup Site Fencing and Access Control | Coordinates installation; Manages gate operations ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | R
9.3.030 - Setup Site Fencing and Access Control | Defines safety requirements; Reviews emergency egress ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization | R
9.3.030 - Setup Site Fencing and Access Control | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization | C
9.3.040 - Setup Temporary Power | Oversees installation; Ensures code compliance ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | A
9.3.040 - Setup Temporary Power | Installs temporary power system; Makes connections ¦ | ¦ Foreman/Journeyman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | R
9.3.040 - Setup Temporary Power | Reviews safety requirements; Verifies GFCI protection ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization | C
9.3.040 - Setup Temporary Power | Coordinates with utility company; Approves power plan ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization | C
9.3.040 - Setup Temporary Power | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Electrical Subcontractor | Sec. 9.2 General Directives | Covered | No change required. | 3 - Mobilization | R
9.3.050 - Setup Temporary Water | Coordinates site setup for Setup Temporary Water | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.050 - Setup Temporary Water | Oversees Setup Temporary Water | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.060 - Setup Sanitary Facilities | Coordinates site setup for Setup Sanitary Facilities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.060 - Setup Sanitary Facilities | Oversees Setup Sanitary Facilities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.070 - Setup Temporary Lighting | Coordinates site setup for Setup Temporary Lighting | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.070 - Setup Temporary Lighting | Oversees Setup Temporary Lighting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.080 - Setup Signage | Coordinates site setup for Setup Signage | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.080 - Setup Signage | Oversees Setup Signage | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.090 - Setup Security | Coordinates site setup for Setup Security | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.090 - Setup Security | Oversees Setup Security | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.100 - Setup Laydown Area | Coordinates site setup for Setup Laydown Area | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.100 - Setup Laydown Area | Oversees Setup Laydown Area | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.110 - Setup Equipment Staging | Coordinates site setup for Setup Equipment Staging | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.110 - Setup Equipment Staging | Oversees Setup Equipment Staging | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.120 - Setup Parking | Coordinates site setup for Setup Parking | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.120 - Setup Parking | Oversees Setup Parking | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.470 - Develop Site-Specific Safety Plan | Reviews for safety compliance for Develop Site-Specific Safety Plan | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 3 - Mobilization | C
9.3.470 - Develop Site-Specific Safety Plan | Oversees Develop Site-Specific Safety Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.470 - Develop Site-Specific Safety Plan | Field coordination for Develop Site-Specific Safety Plan | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | C
9.4.010 - Conduct Coordination Meetings | Leads coordination for Conduct Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.010 - Conduct Coordination Meetings | Field coordination for Conduct Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.020 - Conduct Subcontractor Coordination Meetings | Performs subcontracted work for Conduct Subcontractor Coordination Meetings | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.020 - Conduct Subcontractor Coordination Meetings | Leads coordination for Conduct Subcontractor Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.020 - Conduct Subcontractor Coordination Meetings | Field coordination for Conduct Subcontractor Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.030 - Conduct Client/Owner Meetings | Participates in client communications for Conduct Client/Owner Meetings | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution | C
9.4.030 - Conduct Client/Owner Meetings | Oversees Conduct Client/Owner Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.030 - Conduct Client/Owner Meetings | Field coordination for Conduct Client/Owner Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.040 - Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.040 - Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.040 - Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Coordinates prefabrication for Identify Value Engineering & Prefabrication Opportunities | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Oversees Identify Value Engineering & Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Field coordination for Identify Value Engineering & Prefabrication Opportunities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.050 - Conduct Prefabrication Coordination Meetings | Coordinates prefabrication for Conduct Prefabrication Coordination Meetings | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.050 - Conduct Prefabrication Coordination Meetings | Leads coordination for Conduct Prefabrication Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.050 - Conduct Prefabrication Coordination Meetings | Field coordination for Conduct Prefabrication Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.055 - Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.055 - Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.055 - Procurement of Large Feeder Wire | Field coordination for Procurement of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.060 - Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.060 - Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.060 - Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.190 - Document Filing Standards | Manages documentation for Document Filing Standards | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution | R
9.4.190 - Document Filing Standards | Oversees Document Filing Standards | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.190 - Document Filing Standards | Field coordination for Document Filing Standards | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.195 - Manage Project Documentation System | Manages documentation for Manage Project Documentation System | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution | R
9.4.195 - Manage Project Documentation System | Oversees Manage Project Documentation System | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.195 - Manage Project Documentation System | Field coordination for Manage Project Documentation System | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.200 - Manage Submittals | Manages technical documentation for Manage Submittals | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.200 - Manage Submittals | Field coordination for Manage Submittals | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.205 - Manage RFIs (Requests for Information) | Manages technical documentation for Manage RFIs (Requests for Information) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.205 - Manage RFIs (Requests for Information) | Field coordination for Manage RFIs (Requests for Information) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.210 - Manage Meeting Minutes | Manages documentation for Manage Meeting Minutes | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution | R
9.4.210 - Manage Meeting Minutes | Oversees Manage Meeting Minutes | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.210 - Manage Meeting Minutes | Field coordination for Manage Meeting Minutes | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.215 - Manage Daily Reports | Manages field operations for Manage Daily Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.215 - Manage Daily Reports | Oversees Manage Daily Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.220 - Manage Drawing Logs | Manages technical documentation for Manage Drawing Logs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.220 - Manage Drawing Logs | Field coordination for Manage Drawing Logs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.225 - Manage Specifications | Manages technical documentation for Manage Specifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.225 - Manage Specifications | Field coordination for Manage Specifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.230 - Manage Correspondence | Manages documentation for Manage Correspondence | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution | R
9.4.230 - Manage Correspondence | Oversees Manage Correspondence | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.230 - Manage Correspondence | Field coordination for Manage Correspondence | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.235 - Manage Permits | Oversees Manage Permits | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.235 - Manage Permits | Field coordination for Manage Permits | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.240 - Manage Inspection Reports | Oversees Manage Inspection Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.240 - Manage Inspection Reports | Field coordination for Manage Inspection Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.270 - Manage Project Communications | Manages communications for Manage Project Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.270 - Manage Project Communications | Field coordination for Manage Project Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.275 - Manage Internal Communications | Manages communications for Manage Internal Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.275 - Manage Internal Communications | Field coordination for Manage Internal Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.280 - Manage External Communications | Manages communications for Manage External Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.280 - Manage External Communications | Field coordination for Manage External Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.285 - Manage Client/Owner Communications | Participates in client communications for Manage Client/Owner Communications | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution | C
9.4.285 - Manage Client/Owner Communications | Manages communications for Manage Client/Owner Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.285 - Manage Client/Owner Communications | Field coordination for Manage Client/Owner Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.290 - Manage Subcontractor Communications | Performs subcontracted work for Manage Subcontractor Communications | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.290 - Manage Subcontractor Communications | Manages communications for Manage Subcontractor Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.290 - Manage Subcontractor Communications | Field coordination for Manage Subcontractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.295 - Manage Vendor Supplier Communications | Manages procurement for Manage Vendor Supplier Communications | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.295 - Manage Vendor Supplier Communications | Manages communications for Manage Vendor Supplier Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.295 - Manage Vendor Supplier Communications | Field coordination for Manage Vendor Supplier Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.300 - Manage Architect/Engineer Communications | Manages communications for Manage Architect/Engineer Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.300 - Manage Architect/Engineer Communications | Field coordination for Manage Architect/Engineer Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.305 - Manage Regulatory/Authority Communications | Manages communications for Manage Regulatory/Authority Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.305 - Manage Regulatory/Authority Communications | Field coordination for Manage Regulatory/Authority Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.310 - Manage General Contractor Communications | Manages communications for Manage General Contractor Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.310 - Manage General Contractor Communications | Field coordination for Manage General Contractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.315 - Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.315 - Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.315 - Develop Project Schedule | Field coordination for Develop Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.320 - Update Project Schedule | Coordinates scheduling for Update Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.320 - Update Project Schedule | Oversees Update Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.320 - Update Project Schedule | Field coordination for Update Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.325 - Monitor Schedule Performance | Coordinates scheduling for Monitor Schedule Performance | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.325 - Monitor Schedule Performance | Oversees Monitor Schedule Performance | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.325 - Monitor Schedule Performance | Field coordination for Monitor Schedule Performance | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.330 - Develop Schedule Recovery Plans | Coordinates scheduling for Develop Schedule Recovery Plans | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.330 - Develop Schedule Recovery Plans | Oversees Develop Schedule Recovery Plans | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.330 - Develop Schedule Recovery Plans | Field coordination for Develop Schedule Recovery Plans | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.335 - Prepare Lookahead Schedules | Coordinates scheduling for Prepare Lookahead Schedules | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.335 - Prepare Lookahead Schedules | Oversees Prepare Lookahead Schedules | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.335 - Prepare Lookahead Schedules | Field coordination for Prepare Lookahead Schedules | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.340 - Manage Resource-Loaded Schedules | Coordinates scheduling for Manage Resource-Loaded Schedules | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.340 - Manage Resource-Loaded Schedules | Oversees Manage Resource-Loaded Schedules | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.340 - Manage Resource-Loaded Schedules | Field coordination for Manage Resource-Loaded Schedules | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.345 - Conduct Schedule Review Meetings | Coordinates scheduling for Conduct Schedule Review Meetings | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.345 - Conduct Schedule Review Meetings | Oversees Conduct Schedule Review Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.345 - Conduct Schedule Review Meetings | Field coordination for Conduct Schedule Review Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.350 - Manage Schedule Change Requests | Coordinates scheduling for Manage Schedule Change Requests | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.350 - Manage Schedule Change Requests | Oversees Manage Schedule Change Requests | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.350 - Manage Schedule Change Requests | Field coordination for Manage Schedule Change Requests | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.355 - Manage Project Scope | Manages contract changes for Manage Project Scope | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.355 - Manage Project Scope | Field coordination for Manage Project Scope | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.360 - Manage Change Orders | Manages contract changes for Manage Change Orders | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.360 - Manage Change Orders | Field coordination for Manage Change Orders | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.365 - Manage Potential Change Orders (PCOs) | Manages contract changes for Manage Potential Change Orders (PCOs) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.365 - Manage Potential Change Orders (PCOs) | Field coordination for Manage Potential Change Orders (PCOs) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.370 - Manage Owner Directives | Participates in client communications for Manage Owner Directives | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution | C
9.4.370 - Manage Owner Directives | Oversees Manage Owner Directives | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.370 - Manage Owner Directives | Field coordination for Manage Owner Directives | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.375 - Manage Scope Clarifications | Manages contract changes for Manage Scope Clarifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.375 - Manage Scope Clarifications | Field coordination for Manage Scope Clarifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.380 - Manage Backcharges | Manages contract changes for Manage Backcharges | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.380 - Manage Backcharges | Field coordination for Manage Backcharges | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.385 - Manage Force Account Work | Manages contract changes for Manage Force Account Work | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.385 - Manage Force Account Work | Field coordination for Manage Force Account Work | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.390 - Manage Claims | Provides executive approval for Manage Claims | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution | A
9.4.390 - Manage Claims | Oversees Manage Claims | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.390 - Manage Claims | Field coordination for Manage Claims | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.400 - Monitor Project Costs | Provides financial support for Monitor Project Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.400 - Monitor Project Costs | Oversees Monitor Project Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.400 - Monitor Project Costs | Field coordination for Monitor Project Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.405 - Manage Cost Forecasts | Provides financial support for Manage Cost Forecasts | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.405 - Manage Cost Forecasts | Oversees Manage Cost Forecasts | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.405 - Manage Cost Forecasts | Field coordination for Manage Cost Forecasts | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.410 - Manage Cost Codes | Manages financial documentation for Manage Cost Codes | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.410 - Manage Cost Codes | Oversees Manage Cost Codes | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.410 - Manage Cost Codes | Field coordination for Manage Cost Codes | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.415 - Manage Committed Costs | Provides financial support for Manage Committed Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.415 - Manage Committed Costs | Oversees Manage Committed Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.415 - Manage Committed Costs | Field coordination for Manage Committed Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.420 - Manage Actual Costs | Provides financial support for Manage Actual Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.420 - Manage Actual Costs | Oversees Manage Actual Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.420 - Manage Actual Costs | Field coordination for Manage Actual Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.425 - Manage Job Cost Reports | Manages financial documentation for Manage Job Cost Reports | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.425 - Manage Job Cost Reports | Oversees Manage Job Cost Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.425 - Manage Job Cost Reports | Field coordination for Manage Job Cost Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.430 - Manage Profit Projections | Provides financial support for Manage Profit Projections | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.430 - Manage Profit Projections | Oversees Manage Profit Projections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.430 - Manage Profit Projections | Field coordination for Manage Profit Projections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.435 - Manage Cost-to-Complete | Provides financial support for Manage Cost-to-Complete | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.435 - Manage Cost-to-Complete | Oversees Manage Cost-to-Complete | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.435 - Manage Cost-to-Complete | Field coordination for Manage Cost-to-Complete | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.440 - Prepare Billing Schedule | Manages financial documentation for Prepare Billing Schedule | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.440 - Prepare Billing Schedule | Coordinates scheduling for Prepare Billing Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.440 - Prepare Billing Schedule | Oversees Prepare Billing Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.440 - Prepare Billing Schedule | Field coordination for Prepare Billing Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.445 - Prepare Monthly Pay Applications | Manages financial documentation for Prepare Monthly Pay Applications | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.445 - Prepare Monthly Pay Applications | Oversees Prepare Monthly Pay Applications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.445 - Prepare Monthly Pay Applications | Field coordination for Prepare Monthly Pay Applications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.450 - Track Accounts Receivable | Manages financial documentation for Track Accounts Receivable | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.450 - Track Accounts Receivable | Oversees Track Accounts Receivable | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.450 - Track Accounts Receivable | Field coordination for Track Accounts Receivable | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.455 - Manage Lien Waivers | Oversees Manage Lien Waivers | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.455 - Manage Lien Waivers | Field coordination for Manage Lien Waivers | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.460 - Manage Retainage | Manages financial documentation for Manage Retainage | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.460 - Manage Retainage | Oversees Manage Retainage | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.460 - Manage Retainage | Field coordination for Manage Retainage | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.465 - Manage Final Invoicing | Oversees Manage Final Invoicing | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.465 - Manage Final Invoicing | Field coordination for Manage Final Invoicing | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.475 - Conduct Safety Orientation | Leads safety activities for Conduct Safety Orientation | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.475 - Conduct Safety Orientation | Oversees Conduct Safety Orientation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.475 - Conduct Safety Orientation | Field coordination for Conduct Safety Orientation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.480 - Conduct Safety Inspections | Leads safety activities for Conduct Safety Inspections | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.480 - Conduct Safety Inspections | Oversees Conduct Safety Inspections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.480 - Conduct Safety Inspections | Field coordination for Conduct Safety Inspections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.485 - Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.485 - Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.485 - Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.490 - Report Safety Incidents | Leads safety activities for Report Safety Incidents | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.490 - Report Safety Incidents | Oversees Report Safety Incidents | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.490 - Report Safety Incidents | Field coordination for Report Safety Incidents | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.495 - Investigate Accidents | Leads safety activities for Investigate Accidents | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.495 - Investigate Accidents | Oversees Investigate Accidents | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.495 - Investigate Accidents | Field coordination for Investigate Accidents | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.500 - Conduct Emergency Preparedness | Leads safety activities for Conduct Emergency Preparedness | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.500 - Conduct Emergency Preparedness | Oversees Conduct Emergency Preparedness | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.500 - Conduct Emergency Preparedness | Field coordination for Conduct Emergency Preparedness | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.505 - Conduct Safety Compliance Audits | Reviews for safety compliance for Conduct Safety Compliance Audits | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.505 - Conduct Safety Compliance Audits | Oversees Conduct Safety Compliance Audits | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.505 - Conduct Safety Compliance Audits | Field coordination for Conduct Safety Compliance Audits | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.510 - Provide Safety Training | Reviews for safety compliance for Provide Safety Training | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.510 - Provide Safety Training | Oversees Provide Safety Training | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.510 - Provide Safety Training | Field coordination for Provide Safety Training | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.515 - Develop Quality Management Plan | Performs quality activities for Develop Quality Management Plan | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.515 - Develop Quality Management Plan | Oversees Develop Quality Management Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.515 - Develop Quality Management Plan | Field coordination for Develop Quality Management Plan | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.520 - Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.520 - Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.520 - Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.525 - Conduct Quality Inspections | Performs quality activities for Conduct Quality Inspections | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.525 - Conduct Quality Inspections | Oversees Conduct Quality Inspections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.525 - Conduct Quality Inspections | Field coordination for Conduct Quality Inspections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.530 - Manage Quality Testing | Provides quality oversight for Manage Quality Testing | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.530 - Manage Quality Testing | Oversees Manage Quality Testing | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.530 - Manage Quality Testing | Field coordination for Manage Quality Testing | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.535 - Manage Nonconformance Reports (NCRs) | Performs quality activities for Manage Nonconformance Reports (NCRs) | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.535 - Manage Nonconformance Reports (NCRs) | Oversees Manage Nonconformance Reports (NCRs) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.535 - Manage Nonconformance Reports (NCRs) | Field coordination for Manage Nonconformance Reports (NCRs) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.540 - Manage Quality Records | Provides quality oversight for Manage Quality Records | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.540 - Manage Quality Records | Oversees Manage Quality Records | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.540 - Manage Quality Records | Field coordination for Manage Quality Records | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.545 - Manage Punch List Quality | Provides quality oversight for Manage Punch List Quality | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.545 - Manage Punch List Quality | Oversees Manage Punch List Quality | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.545 - Manage Punch List Quality | Field coordination for Manage Punch List Quality | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.560 - Manage Manpower Allocation | Manages field operations for Manage Manpower Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.560 - Manage Manpower Allocation | Oversees Manage Manpower Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.565 - Manage Equipment Allocation | Oversees Manage Equipment Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.565 - Manage Equipment Allocation | Field coordination for Manage Equipment Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.570 - Manage Material Allocation | Oversees Manage Material Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.570 - Manage Material Allocation | Field coordination for Manage Material Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.576 - Manage Subcontractor Resources | Performs subcontracted work for Manage Subcontractor Resources | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.576 - Manage Subcontractor Resources | Oversees Manage Subcontractor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.576 - Manage Subcontractor Resources | Field coordination for Manage Subcontractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.580 - Manage Vendor Resources | Manages procurement for Manage Vendor Resources | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.580 - Manage Vendor Resources | Oversees Manage Vendor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.580 - Manage Vendor Resources | Field coordination for Manage Vendor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.585 - Plan Prefabrication Resources | Coordinates prefabrication for Plan Prefabrication Resources | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.585 - Plan Prefabrication Resources | Oversees Plan Prefabrication Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.585 - Plan Prefabrication Resources | Field coordination for Plan Prefabrication Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.590 - Manage Specialty Contractor Resources | Oversees Manage Specialty Contractor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.590 - Manage Specialty Contractor Resources | Field coordination for Manage Specialty Contractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.595 - Prepare Resource Reports | Oversees Prepare Resource Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.595 - Prepare Resource Reports | Field coordination for Prepare Resource Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.605 - Issue Purchase Orders | Manages procurement for Issue Purchase Orders | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.605 - Issue Purchase Orders | Oversees Issue Purchase Orders | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.605 - Issue Purchase Orders | Field coordination for Issue Purchase Orders | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.610 - Manage Vendor Prequalification | Manages procurement for Manage Vendor Prequalification | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.610 - Manage Vendor Prequalification | Oversees Manage Vendor Prequalification | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.610 - Manage Vendor Prequalification | Field coordination for Manage Vendor Prequalification | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.615 - Manage Vendor Evaluations | Manages procurement for Manage Vendor Evaluations | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.615 - Manage Vendor Evaluations | Oversees Manage Vendor Evaluations | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.615 - Manage Vendor Evaluations | Field coordination for Manage Vendor Evaluations | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.620 - Manage Expediting | Manages procurement for Manage Expediting | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.620 - Manage Expediting | Oversees Manage Expediting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.620 - Manage Expediting | Field coordination for Manage Expediting | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.625 - Manage Delivery Tracking | Manages procurement for Manage Delivery Tracking | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.625 - Manage Delivery Tracking | Oversees Manage Delivery Tracking | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.625 - Manage Delivery Tracking | Field coordination for Manage Delivery Tracking | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.630 - Manage Material Receiving | Manages procurement for Manage Material Receiving | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.630 - Manage Material Receiving | Oversees Manage Material Receiving | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.630 - Manage Material Receiving | Field coordination for Manage Material Receiving | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.631 - Release of Large Feeder Wire | Oversees Release of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.631 - Release of Large Feeder Wire | Field coordination for Release of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.635 - Manage Material Inspection | Oversees Manage Material Inspection | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.635 - Manage Material Inspection | Field coordination for Manage Material Inspection | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.640 - Manage Storage and Logistics | Oversees Manage Storage and Logistics | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.640 - Manage Storage and Logistics | Field coordination for Manage Storage and Logistics | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.645 - Manage Material Handling | Oversees Manage Material Handling | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.645 - Manage Material Handling | Field coordination for Manage Material Handling | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.650 - Manage Inventory | Manages procurement for Manage Inventory | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.650 - Manage Inventory | Oversees Manage Inventory | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.650 - Manage Inventory | Field coordination for Manage Inventory | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.655 - Prepare Procurement Reports | Manages procurement for Prepare Procurement Reports | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.655 - Prepare Procurement Reports | Oversees Prepare Procurement Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.655 - Prepare Procurement Reports | Field coordination for Prepare Procurement Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.660 - Manage Procurement Closeout | Manages procurement for Manage Procurement Closeout | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.660 - Manage Procurement Closeout | Oversees closeout for Manage Procurement Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.660 - Manage Procurement Closeout | Field coordination for Manage Procurement Closeout | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.665 - Reconcile Procurement Accounts | Manages procurement for Reconcile Procurement Accounts | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.665 - Reconcile Procurement Accounts | Manages financial documentation for Reconcile Procurement Accounts | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.665 - Reconcile Procurement Accounts | Oversees Reconcile Procurement Accounts | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.665 - Reconcile Procurement Accounts | Field coordination for Reconcile Procurement Accounts | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.670 - Manage Vendor Closeout | Manages procurement for Manage Vendor Closeout | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.670 - Manage Vendor Closeout | Oversees closeout for Manage Vendor Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.670 - Manage Vendor Closeout | Field coordination for Manage Vendor Closeout | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.675 - Conduct Daily Huddles | Leads crew activities for Conduct Daily Huddles | Foreman | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.675 - Conduct Daily Huddles | Oversees Conduct Daily Huddles | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.675 - Conduct Daily Huddles | Field coordination for Conduct Daily Huddles | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.680 - Conduct Weekly Foreman Meetings | Leads crew activities for Conduct Weekly Foreman Meetings | Foreman | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.680 - Conduct Weekly Foreman Meetings | Oversees Conduct Weekly Foreman Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.680 - Conduct Weekly Foreman Meetings | Field coordination for Conduct Weekly Foreman Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.690 - Track Manpower Utilization | Manages field operations for Track Manpower Utilization | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.690 - Track Manpower Utilization | Oversees Track Manpower Utilization | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.695 - Track Production Quantities | Manages field operations for Track Production Quantities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.695 - Track Production Quantities | Oversees Track Production Quantities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.700 - Track Equipment Utilization | Oversees Track Equipment Utilization | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.700 - Track Equipment Utilization | Field coordination for Track Equipment Utilization | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.705 - Manage Work Packaging | Oversees Manage Work Packaging | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.705 - Manage Work Packaging | Field coordination for Manage Work Packaging | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.710 - Manage Workface Planning | Oversees Manage Workface Planning | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.710 - Manage Workface Planning | Field coordination for Manage Workface Planning | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.715 - Manage Field Coordination | Manages field operations for Manage Field Coordination | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.715 - Manage Field Coordination | Oversees Manage Field Coordination | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.720 - Conduct Productivity Analysis | Oversees Conduct Productivity Analysis | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.720 - Conduct Productivity Analysis | Field coordination for Conduct Productivity Analysis | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.725 - Resolve Field Problems | Manages field operations for Resolve Field Problems | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.725 - Resolve Field Problems | Oversees Resolve Field Problems | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.735 - Perform Field Quality Verifications | Provides quality oversight for Perform Field Quality Verifications | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.735 - Perform Field Quality Verifications | Oversees Perform Field Quality Verifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.735 - Perform Field Quality Verifications | Field coordination for Perform Field Quality Verifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.745 - Manage Field Rework | Manages field operations for Manage Field Rework | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.745 - Manage Field Rework | Oversees Manage Field Rework | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.755 - Implement Field Productivity Improvements | Oversees Implement Field Productivity Improvements | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.755 - Implement Field Productivity Improvements | Field coordination for Implement Field Productivity Improvements | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.5.020 - Handling and/or Disposing of Excess Materials | Leads meeting coordination; Tracks commissioning progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning | A
9.5.020 - Handling and/or Disposing of Excess Materials | Conducts testing; Documents results; Identifies deficiencies ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.020 - Handling and/or Disposing of Excess Materials | Supports testing activities; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning | R
9.5.020 - Handling and/or Disposing of Excess Materials | Verifies quality requirements; Reviews test results ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | Covered | No change required. | 5 - Commissioning | C
9.5.020 - Handling and/or Disposing of Excess Materials | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | Overall commissioning management; Schedule coordination ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning | A
9.5.550 - Manage Commissioning Activities | Supports testing; Ensures systems ready; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | Executes testing protocols; Documents results ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | Verifies compliance; Reviews documentation ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.6.005 - Prepare for Turnover (Field Perspective) | Oversees closeout for Prepare for Turnover (Field Perspective) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.010 - Conduct Closeout Meetings | Leads closeout meetings; Tracks closeout progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | A
9.6.010 - Conduct Closeout Meetings | Reports field status; Coordinates punch completion ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.010 - Conduct Closeout Meetings | Participate; Complete their closeout requirements ¦ | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | R
9.6.010 - Conduct Closeout Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Client/Owner | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | I
9.6.015 - Manage Project Turnover Documentation | Oversees closeout for Manage Project Turnover Documentation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.020 - Manage Punch List Closeout | Provides quality oversight for Manage Punch List Closeout | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 6 - Closeout | C
9.6.020 - Manage Punch List Closeout | Oversees closeout for Manage Punch List Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.030 - Manage As-Built Drawings | Manages as-built process; Submits final drawings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | A
9.6.030 - Manage As-Built Drawings | Reviews markups for accuracy; Coordinates with field ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.030 - Manage As-Built Drawings | Creates field markups; Documents actual conditions ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.030 - Manage As-Built Drawings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Engineer/APM | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | R
9.6.035 - Submit Warranties | Oversees Submit Warranties | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.040 - Submit O&M Manuals | Oversees closeout for Submit O&M Manuals | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.050 - Provide Owner Training | Participates in client communications for Provide Owner Training | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 6 - Closeout | C
9.6.050 - Provide Owner Training | Oversees Provide Owner Training | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.065 - Archive Project Documentation | Manages documentation for Archive Project Documentation | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 6 - Closeout | R
9.6.065 - Archive Project Documentation | Oversees Archive Project Documentation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.070 - Conduct Post-Project Review | Oversees review process; Approves action items ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout | A
9.6.070 - Conduct Post-Project Review | Leads review meeting; Compiles findings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.070 - Conduct Post-Project Review | Provides field perspective; Shares observations ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.070 - Conduct Post-Project Review | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | C
9.6.080 - Capture Client Feedback | Oversees feedback process; Reviews results ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout | A
9.6.080 - Capture Client Feedback | Conducts feedback meeting; Documents responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.080 - Capture Client Feedback | Uses feedback for relationship management ¦ | ¦ Business Development | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | C
9.6.080 - Capture Client Feedback | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Executive Committee | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | I
9.6.085 - Document Lessons Learned | Maintains lessons learned database; Ensures implementation ¦ | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | A
9.6.085 - Document Lessons Learned | Documents project-specific lessons; Submits for review ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.085 - Document Lessons Learned | Captures field-level learnings; Contributes to documentation ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.085 - Document Lessons Learned | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout | C

## Role Alignment Matrix
SOP ID | SOP Title | Phase | Accounting | Branch Manager | Estimator | Field Supervisor | Foreman | General Superintendent | Prefabrication Lead | Project Coordinator | Project Manager | Purchasing | Quality Inspector | Safety Coordinator | Site Administrator | Subcontractors | Superintendent | ¦ Assistant PM/Project Coordinator | ¦ Branch Manager | ¦ Business Development | ¦ Client/Owner | ¦ Commissioning Agent | ¦ Electrical Subcontractor | ¦ Executive Committee | ¦ Field Leadership | ¦ Field Supervisor | ¦ Foreman | ¦ Foreman/Journeyman | ¦ General Superintendent | ¦ Operations Manager | ¦ Project Engineer/APM | ¦ Project Manager | ¦ Purchasing | ¦ Quality/QA-QC | ¦ Safety Coordinator | ¦ Site Administrator | ¦ Subcontractors
9.1.050 | 9.1.050 - Prepare Construction Takeoff | 1 - Estimating | [8 empty] | R*
9.2.005 | 9.2.005 - Review Contract for High Risk Clauses | 2 - Preconstruction | [8 empty] | A*
9.2.010 | 9.2.010 - Team Selection | 2 - Preconstruction |  | A |  |  |  | C | I | I | R | I |  | C
9.2.015 | 9.2.015 - Project Turnover Meeting | 2 - Preconstruction | [8 empty] | A*
9.2.020 | 9.2.020 - Procurement of Large Feeder Wire | 2 - Preconstruction | [8 empty] | A* | R*
9.2.030 | 9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | 2 - Preconstruction | [8 empty] | A*
9.2.040 | 9.2.040 - Project Manager Reviews Plans Specifications & Schedule | 2 - Preconstruction | [8 empty] | R* | [5 empty] | C*
9.2.050 | 9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | 2 - Preconstruction | [8 empty] | R* | [5 empty] | C*
9.2.055 | 9.2.055 - Compare Estimated vs Planned Performance | 2 - Preconstruction |  |  | C* | [5 empty] | A*
9.2.057 | 9.2.057 - Identify VE and Prefabrication Opportunities | 2 - Preconstruction | [6 empty] | R* |  | A*
9.2.060 | 9.2.060 - Create Issue List and Begin RFI Process | 2 - Preconstruction | [15 empty] | R | [7 empty] | C |  |  | C |  |  | A
9.2.070 | 9.2.070 - Conduct Site Visit | 2 - Preconstruction | [22 empty] | R |  |  |  | C |  |  | A |  |  | R
9.2.080 | 9.2.080 - Prepare Material Handling Plan | 2 - Preconstruction | [8 empty] | A*
9.2.090 | 9.2.090 - Develop Labor Budget | 2 - Preconstruction | C* | [7 empty] | A*
9.2.100 | 9.2.100 - Prepare Layout & Sequencing Plan | 2 - Preconstruction | [8 empty] | A*
9.2.110 | 9.2.110 - Develop Project Schedule | 2 - Preconstruction | [8 empty] | A* | [5 empty] | C*
9.2.120 | 9.2.120 - Establish Tracking & Control Systems | 2 - Preconstruction | [8 empty] | A*
9.2.130 | 9.2.130 - Construction Execution Kickoff Meeting | 2 - Preconstruction | [8 empty] | R*
9.2.140 | 9.2.140 - Develop Project Budget | 2 - Preconstruction | C* | [7 empty] | A*
9.2.160 | 9.2.160 - Develop Procurement Plan | 2 - Preconstruction | [8 empty] | A* | R*
9.3.010 | 9.3.010 - Setup Office Trailer | 3 - Mobilization | [23 empty] | R |  |  | C |  |  | A |  |  | C | R
9.3.020 | 9.3.020 - Setup Storage Trailer | 3 - Mobilization | [23 empty] | A | R | [5 empty] | C |  | C
9.3.030 | 9.3.030 - Setup Site Fencing and Access Control | 3 - Mobilization | [23 empty] | A | R |  |  |  |  | C |  |  | R
9.3.040 | 9.3.040 - Setup Temporary Power | 3 - Mobilization | [20 empty] | R |  |  | A |  | R |  |  |  | C |  |  | C
9.3.050 | 9.3.050 - Setup Temporary Water | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.060 | 9.3.060 - Setup Sanitary Facilities | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.070 | 9.3.070 - Setup Temporary Lighting | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.080 | 9.3.080 - Setup Signage | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.090 | 9.3.090 - Setup Security | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.100 | 9.3.100 - Setup Laydown Area | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.110 | 9.3.110 - Setup Equipment Staging | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.120 | 9.3.120 - Setup Parking | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.470 | 9.3.470 - Develop Site-Specific Safety Plan | 3 - Mobilization |  |  |  | C* |  |  |  |  | R* |  |  | C*
9.4.010 | 9.4.010 - Conduct Coordination Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.020 | 9.4.020 - Conduct Subcontractor Coordination Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | R* |  |  |  |  | R*
9.4.030 | 9.4.030 - Conduct Client/Owner Meetings | 4 - Execution |  | C* |  | C* |  |  |  |  | A*
9.4.040 | 9.4.040 - Conduct Safety Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.045 | 9.4.045 - Identify Value Engineering & Prefabrication Opportunities | 4 - Execution |  |  |  | C* |  |  | R* |  | A*
9.4.050 | 9.4.050 - Conduct Prefabrication Coordination Meetings | 4 - Execution |  |  |  | C* |  |  | R* |  | R*
9.4.055 | 9.4.055 - Procurement of Large Feeder Wire | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.060 | 9.4.060 - Conduct Quality Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.190 | 9.4.190 - Document Filing Standards | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  | R*
9.4.195 | 9.4.195 - Manage Project Documentation System | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  | R*
9.4.200 | 9.4.200 - Manage Submittals | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.205 | 9.4.205 - Manage RFIs (Requests for Information) | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.210 | 9.4.210 - Manage Meeting Minutes | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  | R*
9.4.215 | 9.4.215 - Manage Daily Reports | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.220 | 9.4.220 - Manage Drawing Logs | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.225 | 9.4.225 - Manage Specifications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.230 | 9.4.230 - Manage Correspondence | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  | R*
9.4.235 | 9.4.235 - Manage Permits | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.240 | 9.4.240 - Manage Inspection Reports | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.270 | 9.4.270 - Manage Project Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.275 | 9.4.275 - Manage Internal Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.280 | 9.4.280 - Manage External Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.285 | 9.4.285 - Manage Client/Owner Communications | 4 - Execution |  | C* |  | C* |  |  |  |  | R*
9.4.290 | 9.4.290 - Manage Subcontractor Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R* |  |  |  |  | R*
9.4.295 | 9.4.295 - Manage Vendor Supplier Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R* | R*
9.4.300 | 9.4.300 - Manage Architect/Engineer Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.305 | 9.4.305 - Manage Regulatory/Authority Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.310 | 9.4.310 - Manage General Contractor Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.315 | 9.4.315 - Develop Project Schedule | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.320 | 9.4.320 - Update Project Schedule | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.325 | 9.4.325 - Monitor Schedule Performance | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.330 | 9.4.330 - Develop Schedule Recovery Plans | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.335 | 9.4.335 - Prepare Lookahead Schedules | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.340 | 9.4.340 - Manage Resource-Loaded Schedules | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.345 | 9.4.345 - Conduct Schedule Review Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.350 | 9.4.350 - Manage Schedule Change Requests | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.355 | 9.4.355 - Manage Project Scope | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.360 | 9.4.360 - Manage Change Orders | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.365 | 9.4.365 - Manage Potential Change Orders (PCOs) | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.370 | 9.4.370 - Manage Owner Directives | 4 - Execution |  | C* |  | C* |  |  |  |  | A*
9.4.375 | 9.4.375 - Manage Scope Clarifications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.380 | 9.4.380 - Manage Backcharges | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.385 | 9.4.385 - Manage Force Account Work | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.390 | 9.4.390 - Manage Claims | 4 - Execution |  | A* |  | C* |  |  |  |  | A*
9.4.400 | 9.4.400 - Monitor Project Costs | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.405 | 9.4.405 - Manage Cost Forecasts | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.410 | 9.4.410 - Manage Cost Codes | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.415 | 9.4.415 - Manage Committed Costs | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.420 | 9.4.420 - Manage Actual Costs | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.425 | 9.4.425 - Manage Job Cost Reports | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.430 | 9.4.430 - Manage Profit Projections | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.435 | 9.4.435 - Manage Cost-to-Complete | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.440 | 9.4.440 - Prepare Billing Schedule | 4 - Execution | R* |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.445 | 9.4.445 - Prepare Monthly Pay Applications | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.450 | 9.4.450 - Track Accounts Receivable | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.455 | 9.4.455 - Manage Lien Waivers | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.460 | 9.4.460 - Manage Retainage | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.465 | 9.4.465 - Manage Final Invoicing | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.475 | 9.4.475 - Conduct Safety Orientation | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.480 | 9.4.480 - Conduct Safety Inspections | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.485 | 9.4.485 - Conduct Safety Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.490 | 9.4.490 - Report Safety Incidents | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.495 | 9.4.495 - Investigate Accidents | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.500 | 9.4.500 - Conduct Emergency Preparedness | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.505 | 9.4.505 - Conduct Safety Compliance Audits | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | C*
9.4.510 | 9.4.510 - Provide Safety Training | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | C*
9.4.515 | 9.4.515 - Develop Quality Management Plan | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.520 | 9.4.520 - Conduct Quality Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.525 | 9.4.525 - Conduct Quality Inspections | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.530 | 9.4.530 - Manage Quality Testing | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | C*
9.4.535 | 9.4.535 - Manage Nonconformance Reports (NCRs) | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.540 | 9.4.540 - Manage Quality Records | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | C*
9.4.545 | 9.4.545 - Manage Punch List Quality | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | C*
9.4.560 | 9.4.560 - Manage Manpower Allocation | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.565 | 9.4.565 - Manage Equipment Allocation | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.570 | 9.4.570 - Manage Material Allocation | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.576 | 9.4.576 - Manage Subcontractor Resources | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  |  | R*
9.4.580 | 9.4.580 - Manage Vendor Resources | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.585 | 9.4.585 - Plan Prefabrication Resources | 4 - Execution |  |  |  | C* |  |  | R* |  | A*
9.4.590 | 9.4.590 - Manage Specialty Contractor Resources | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.595 | 9.4.595 - Prepare Resource Reports | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.605 | 9.4.605 - Issue Purchase Orders | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.610 | 9.4.610 - Manage Vendor Prequalification | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.615 | 9.4.615 - Manage Vendor Evaluations | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.620 | 9.4.620 - Manage Expediting | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.625 | 9.4.625 - Manage Delivery Tracking | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.630 | 9.4.630 - Manage Material Receiving | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.631 | 9.4.631 - Release of Large Feeder Wire | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.635 | 9.4.635 - Manage Material Inspection | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.640 | 9.4.640 - Manage Storage and Logistics | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.645 | 9.4.645 - Manage Material Handling | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.650 | 9.4.650 - Manage Inventory | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.655 | 9.4.655 - Prepare Procurement Reports | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.660 | 9.4.660 - Manage Procurement Closeout | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.665 | 9.4.665 - Reconcile Procurement Accounts | 4 - Execution | R* |  |  | C* |  |  |  |  | A* | R*
9.4.670 | 9.4.670 - Manage Vendor Closeout | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.675 | 9.4.675 - Conduct Daily Huddles | 4 - Execution |  |  |  | C* | R* |  |  |  | A*
9.4.680 | 9.4.680 - Conduct Weekly Foreman Meetings | 4 - Execution |  |  |  | C* | R* |  |  |  | A*
9.4.690 | 9.4.690 - Track Manpower Utilization | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.695 | 9.4.695 - Track Production Quantities | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.700 | 9.4.700 - Track Equipment Utilization | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.705 | 9.4.705 - Manage Work Packaging | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.710 | 9.4.710 - Manage Workface Planning | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.715 | 9.4.715 - Manage Field Coordination | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.720 | 9.4.720 - Conduct Productivity Analysis | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.725 | 9.4.725 - Resolve Field Problems | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.735 | 9.4.735 - Perform Field Quality Verifications | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | C*
9.4.745 | 9.4.745 - Manage Field Rework | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.755 | 9.4.755 - Implement Field Productivity Improvements | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.5.020 | 9.5.020 - Handling and/or Disposing of Excess Materials | 5 - Commissioning | [19 empty] | R |  |  |  | R | [5 empty] | A |  | C |  |  | R
9.5.550 | 9.5.550 - Manage Commissioning Activities | 5 - Commissioning | [19 empty] | R |  |  |  | R | [5 empty] | A |  | R |  |  | R
9.6.005 | 9.6.005 - Prepare for Turnover (Field Perspective) | 6 - Closeout | [8 empty] | A*
9.6.010 | 9.6.010 - Conduct Closeout Meetings | 6 - Closeout | [18 empty] | I |  |  |  |  | R | [5 empty] | A |  |  |  |  | R
9.6.015 | 9.6.015 - Manage Project Turnover Documentation | 6 - Closeout | [8 empty] | A*
9.6.020 | 9.6.020 - Manage Punch List Closeout | 6 - Closeout | [8 empty] | A* |  | C*
9.6.030 | 9.6.030 - Manage As-Built Drawings | 6 - Closeout | [23 empty] | R | R |  |  |  | R | A
9.6.035 | 9.6.035 - Submit Warranties | 6 - Closeout | [8 empty] | A*
9.6.040 | 9.6.040 - Submit O&M Manuals | 6 - Closeout | [8 empty] | A*
9.6.050 | 9.6.050 - Provide Owner Training | 6 - Closeout |  | C* | [6 empty] | A*
9.6.065 | 9.6.065 - Archive Project Documentation | 6 - Closeout | [8 empty] | A* |  |  |  | R*
9.6.070 | 9.6.070 - Conduct Post-Project Review | 6 - Closeout | [16 empty] | A | [6 empty] | R |  |  |  | C |  | R
9.6.080 | 9.6.080 - Capture Client Feedback | 6 - Closeout | [16 empty] | A | C |  |  |  | I | [7 empty] | R
9.6.085 | 9.6.085 - Document Lessons Learned | 6 - Closeout | [16 empty] | C | [6 empty] | R |  |  |  | A |  | R