## GSL_SOP_Metadata
SOP ID | Name | SOP File Name | SOP ID | Title | Description | Phase | Category (CCC Tag) | Category Group | Roles (RACI) | Primary JD | Discipline | Revision | Effective Date | Owner | Approver | Formerly | Status | Tags / Keywords | Related SOPs | Department / Division | Last Reviewed Date | Next Review Due | Document Type
9.1.050 | 9.1.050 – Prepare Construction Takeoff | 9.1.050 – Prepare Construction Takeoff.docx | 9.1.050 | Prepare Construction Takeoff | To prepare a detailed construction takeoff that validates estimated quantities and provides the basis for procurement, labor budgeting, and execution planning. Scope This SOP applies to Project Managers and Estimators for all awarded projects be... | 1 – Estimating | General | Estimating | [Inferred] Project Manager (R) |  | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.055 – Procurement of Large Feeder Wire Reference: GSL Pre-Construction Planning – Construction Takeoff | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.055 – Procurement of Large Feeder Wire Reference: GSL Pre-Construction Planning – Construction Takeoff | 2026-01-15 | 2027-01-15 | SOP
9.2.005 | 9.2.005 – Review Contract for High Risk Clauses | 9.2.005 – Review Contract for High Risk Clauses.docx | 9.2.005 | Review Contract for High Risk Clauses | To establish a standardized process for reviewing contract terms to identify unfavorable or high-risk clauses before baseline planning begins, ensuring proper risk mitigation and approval protocols are in place. SCOPE Applies to all projects / sit... | 2 – Preconstruction | Scope and contract review | Preconstruction | [Inferred] Project Manager (A) |  | Branch Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Branch Management | 2026-01-15 | 2027-01-15 | SOP
9.2.010 | 9.2.010 – Team Selection | 9.2.010 – Team Selection.docx | 9.2.010 | Team Selection | To establish a standardized process for selecting and assembling the project team immediately after project award, ensuring the right mix of skills, experience, and availability to meet project requirements. SCOPE Applies to all projects / situati... | 2 – Preconstruction | Team selection and turnover | Preconstruction | Branch Manager (A); Project Manager (R); General Superintendent (C); Safety Coordinator (C); Purchasing (I); Prefabrication Lead (I); Project Coordinator (I) |  | Project Management / Operations | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Operations | 2026-01-15 | 2027-01-15 | SOP
9.2.015 | 9.2.015 – Project Turnover Meeting | 9.2.015 – Project Turnover Meeting.docx | 9.2.015 | Project Turnover Meeting | To ensure a consistent and documented turnover process for newly awarded projects using a standardized Smartsheet agenda to guide communication, task planning, and team alignment. Scope This SOP applies to all projects awarded through GSL's esti... | 2 – Preconstruction | Team selection and turnover | Preconstruction | [Inferred] Project Manager (A) |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.2 Related SOPs: | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.2 Related SOPs: | 2026-01-15 | 2027-01-15 | SOP
9.2.020 | 9.2.020 – Procurement of Large Feeder Wire | 9.2.020 – Procurement of Large Feeder Wire.docx | 9.2.020 | Procurement of Large Feeder Wire | To define the standardized process for the planning, procurement, and delivery of large feeder wire to ensure that project cost, schedule, and quality targets are achieved in accordance with GSL Electric’s Management Directives. 2. | 2 – Preconstruction | Procurement planning | Preconstruction | [Inferred] Purchasing (R); Project Manager (A) |  | Operations | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Operations | 2026-01-15 | 2027-01-15 | SOP
9.2.030 | 9.2.030 – Review Contract for Unfavorable or High-Risk Clauses | 9.2.030 – Review Contract for Unfavorable or High Risk Clauses.docx | 9.2.030 | Review Contract for Unfavorable or High-Risk Clauses | To ensure all project contracts are reviewed systematically for unfavorable or high-risk clauses that could affect project execution, budget, or liability, and to define mitigation measures prior to mobilization. Scope This SOP applies to all Pr... | 2 – Preconstruction | Scope and contract review | Preconstruction | [Inferred] Project Manager (A) |  | Project Management / Pre-Construction Created by: Schachinger Solutions GmbH Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Contract Review | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Pre-Construction Created by: Schachinger Solutions GmbH Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Contract Review | 2026-01-15 | 2027-01-15 | SOP
9.2.040 | 9.2.040 – Project Manager Reviews Plans Specifications & Schedule | 9.2.040 – Project Manager Reviews Plans, Specifications & Schedule.docx | 9.2.040 | Project Manager Reviews Plans Specifications & Schedule | To ensure that the Project Manager conducts a detailed review of project drawings, specifications, and schedules to confirm alignment with contract requirements and identify risks before mobilization. Scope This SOP applies to all Project Manage... | 2 – Preconstruction | Scheduling | Preconstruction | [Inferred] Superintendent (C); Project Manager (R) |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable or High-Risk Clauses; 9.41.025 – Field Supervisor Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Scope & Schedule Review | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable or High-Risk Clauses; 9.41.025 – Field Supervisor Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Scope & Schedule Review | 2026-01-15 | 2027-01-15 | SOP
9.2.050 | 9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | 9.2.050 – Field Supervisor Reviews Plans, Specifications & Schedule.docx | 9.2.050 | Field Supervisor Reviews Plans Specifications & Schedule | To ensure Field Supervisors conduct a detailed review of project drawings, specifications, and schedules with a focus on constructability, sequencing, and field logistics, supporting accurate execution planning. Scope This SOP applies to Field S... | 2 – Preconstruction | Scheduling | Preconstruction | [Inferred] Superintendent (C); Project Manager (R) |  | Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process Reference: GSL Pre-Construction Planning – Scope & Schedule Review | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process Reference: GSL Pre-Construction Planning – Scope & Schedule Review | 2026-01-15 | 2027-01-15 | SOP
9.2.055 | 9.2.055 – Compare Estimated vs Planned Performance | 9.2.055 – Compare Estimated vs Planned Performance.docx | 9.2.055 | Compare Estimated vs Planned Performance | To confirm that bid assumptions for labor, materials, and productivity align with the planned project execution strategy, ensuring accurate budgets and realistic performance goals. Scope This SOP applies to Project Managers and Estimators during... | 2 – Preconstruction | Preconstruction planning | Preconstruction | [Inferred] Estimator (C); Project Manager (A) |  | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.045 – Identify Value Engineering & Prefabrication Opportunities Reference: GSL Pre-Construction Planning – Bid vs. Execution Review | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.045 – Identify Value Engineering & Prefabrication Opportunities Reference: GSL Pre-Construction Planning – Bid vs. Execution Review | 2026-01-15 | 2027-01-15 | SOP
9.2.057 | 9.2.057 – Identify VE and Prefabrication Opportunities | 9.2.057 – Identify VE and Prefabrication Opportunities.docx | 9.2.057 | Identify VE and Prefabrication Opportunities | To define the process for identifying, developing, and documenting the project’s prefabrication strategy, allowing for improved planning, efficiency, and field execution through the use of off-site construction. Scope Applies to all projects wit... | 2 – Preconstruction | Preconstruction planning | Preconstruction | [Inferred] Prefabrication Lead (R); Project Manager (A) |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-15 | 2027-01-15 | SOP
9.2.060 | 9.2.060 – Create Issue List and Begin RFI Process | 9.2.060 – Create Issue List and Begin RFI Process.docx | 9.2.060 | Create Issue List and Begin RFI Process | To establish a standardized process for documenting project issues identified during pre-construction review and initiating the Request for Information (RFI) process to resolve them befo... | 2 – Preconstruction | Preconstruction planning | Preconstruction | ¦ Project Manager (A); ¦ Assistant PM/Project Coordinator (R); ¦ Field Supervisor (C); ¦ General Superintendent (C) |  | Project Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management | 2026-01-15 | 2027-01-15 | SOP
9.2.070 | 9.2.070 – Conduct Site Visit | 9.2.070 – Conduct Site Visit.docx | 9.2.070 | Conduct Site Visit | To establish a standardized process for conducting pre-construction site visits to assess existing conditions, identify logistical requirements, and validate planning assumptions before ... | 2 – Preconstruction | Preconstruction planning | Preconstruction | ¦ Project Manager (A); ¦ Field Leadership (R); ¦ Safety Coordinator (R); ¦ General Superintendent (C) |  | Project Management / Field Operations | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations | 2026-01-15 | 2027-01-15 | SOP
9.2.080 | 9.2.080 – Prepare Material Handling Plan | 9.2.080 – Prepare Material Handling Plan.docx | 9.2.080 | Prepare Material Handling Plan | To define the process for creating a job-specific Material Handling Plan that ensures efficient, safe, and cost-effective delivery, storage, movement, and installation of materials on-site. Scope Applies to all projects requiring material moveme... | 2 – Preconstruction | Procurement planning | Preconstruction | [Inferred] Project Manager (A) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-15 | 2027-01-15 | SOP
9.2.090 | 9.2.090 – Develop Labor Budget | 9.2.090 – Develop Labor Budget.docx | 9.2.090 | Develop Labor Budget | To establish a standardized process for creating a project-specific labor budget that reflects estimated manhours by phase and supports resource planning, cost tracking, and productivity measurement. Scope Applies to all awarded projects and mus... | 2 – Preconstruction | Budgeting | Preconstruction | [Inferred] Accounting (C); Project Manager (A) |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-15 | 2027-01-15 | SOP
9.2.100 | 9.2.100 – Prepare Layout & Sequencing Plan | 9.2.100 – Prepare Layout & Sequencing Plan.docx | 9.2.100 | Prepare Layout & Sequencing Plan | To establish a coordinated layout and sequencing plan that supports efficient installation, minimizes trade conflicts, and ensures project milestones are achieved. Scope This SOP applies to Project Managers, Field Supervisors, and General Superi... | 2 – Preconstruction | Preconstruction planning | Preconstruction | [Inferred] Project Manager (A) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.065 – Develop Labor Budget; 9.41.075 – Develop Project Schedule Reference: GSL Pre-Construction Planning – Layout & Sequencing | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.065 – Develop Labor Budget; 9.41.075 – Develop Project Schedule Reference: GSL Pre-Construction Planning – Layout & Sequencing | 2026-01-15 | 2027-01-15 | SOP
9.2.110 | 9.2.110 – Develop Project Schedule | 9.2.110 – Develop Project Schedule.docx | 9.2.110 | Develop Project Schedule | To outline the process for developing a complete project schedule that aligns field activities, procurement, prefab, and inspections to meet project milestones and client expectations. Scope Applies to all awarded projects prior to mobilization. | 2 – Preconstruction | Scheduling | Preconstruction | [Inferred] Superintendent (C); Project Manager (A) |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-15 | 2027-01-15 | SOP
9.2.120 | 9.2.120 – Establish Tracking & Control Systems | 9.2.120 – Establish Tracking & Control Systems.docx | 9.2.120 | Establish Tracking & Control Systems | To implement standardized systems for monitoring labor, materials, procurement, safety, and project performance, enabling accurate reporting and proactive management. Scope This SOP applies to Project Managers, Field Supervisors, Purchasing, and... | 2 – Preconstruction | Preconstruction planning | Preconstruction | [Inferred] Project Manager (A) |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Pre-Construction Planning – Tracking & Control | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Pre-Construction Planning – Tracking & Control | 2026-01-15 | 2027-01-15 | SOP
9.2.130 | 9.2.130 – Construction Execution Kickoff Meeting | 9.2.130 – Construction Execution Kickoff Meeting.docx | 9.2.130 | Construction Execution Kickoff Meeting | To formally launch field construction by aligning the project team, reviewing key work plans, confirming roles, and addressing critical first-week activities before installation begins. Scope Applies to all projects immediately prior to the star... | 2 – Preconstruction | Preconstruction planning | Preconstruction | [Inferred] Project Manager (R) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-15 | 2027-01-15 | SOP
9.2.140 | 9.2.140 – Develop Project Budget | 9.2.140 – Develop Project Budget.docx | 9.2.140 | Develop Project Budget | To establish a comprehensive project budget that reflects the contract value, cost codes, and anticipated expenses, serving as the baseline for cost control. Scope This SOP applies to Project Managers, Estimators, and Accounting. | 2 – Preconstruction | Budgeting | Preconstruction | [Inferred] Accounting (C); Project Manager (A) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.360 – Manage Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.360 – Manage Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-15 | 2027-01-15 | SOP
9.2.160 | 9.2.160 – Develop Procurement Plan | 9.2.160 – Develop Procurement Plan.docx | 9.2.160 | Develop Procurement Plan | To prepare a procurement plan that identifies all major materials, equipment, and subcontracted services required for the project, including lead times and responsibilities. Scope This SOP applies to Project Managers, Estimators, and Purchasing. | 2 – Preconstruction | Procurement planning | Preconstruction | [Inferred] Purchasing (R); Project Manager (A) |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.395 – Develop Project Budget; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.395 – Develop Project Budget; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.3.010 | 9.3.010 – Setup Office Trailer | 9.3.010 – Setup Office Trailer.docx | 9.3.010 | Setup Office Trailer | To establish a standardized process for setting up the project office trailer, ensuring proper placement, utilities, and functionality for project administration and team coordination. =... | 3 – Mobilization | Site mobilization | Mobilization | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Site Administrator (R); ¦ Safety Coordinator (C); ¦ General Superintendent (C) |  | Project Management / Field Operations | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations | 2026-01-15 | 2027-01-15 | SOP
9.3.020 | 9.3.020 – Setup Storage Trailer | 9.3.020 – Setup Storage Trailer.docx | 9.3.020 | Setup Storage Trailer | To establish a standardized process for setting up project storage trailers/containers, ensuring secure and organized storage for materials, tools, and equipment. =======================... | 3 – Mobilization | Site mobilization | Mobilization | ¦ Field Supervisor (A); ¦ Foreman (R); ¦ Purchasing (C); ¦ Safety Coordinator (C) |  | Field Operations | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations | 2026-01-15 | 2027-01-15 | SOP
9.3.030 | 9.3.030 – Setup Site Fencing and Access Control | 9.3.030 – Setup Site Fencing and Access Control.docx | 9.3.030 | Setup Site Fencing and Access Control | To establish a standardized process for installing site fencing and access control measures, ensuring site security and controlled entry/exit for personnel and deliveries. ==============... | 3 – Mobilization | Site mobilization | Mobilization | ¦ Field Supervisor (A); ¦ Foreman (R); ¦ Safety Coordinator (R); ¦ Project Manager (C) |  | Field Operations / Safety | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Safety | 2026-01-15 | 2027-01-15 | SOP
9.3.040 | 9.3.040 – Setup Temporary Power | 9.3.040 – Setup Temporary Power.docx | 9.3.040 | Setup Temporary Power | To establish a standardized process for installing temporary electrical power distribution, ensuring safe and adequate power for construction operations, trailers, and equipment. =======... | 3 – Mobilization | Site mobilization | Mobilization | ¦ Field Supervisor (A); ¦ Foreman/Journeyman (R); ¦ Safety Coordinator (C); ¦ Project Manager (C); ¦ Electrical Subcontractor (R) |  | Field Operations | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations | 2026-01-15 | 2027-01-15 | SOP
9.3.050 | 9.3.050 – Setup Temporary Water | 9.3.050 – Setup Temporary Water.docx | 9.3.050 | Setup Temporary Water | To provide safe, reliable temporary water supply for construction use, including dust control, concrete work, cleaning, and sanitary needs. Scope This SOP applies to Project Managers and Field Supervisors during mobilization and throughout proje... | 3 – Mobilization | Site mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer Reference: GSL Project Manager Procedures – Mobilization | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer Reference: GSL Project Manager Procedures – Mobilization | 2026-01-15 | 2027-01-15 | SOP
9.3.060 | 9.3.060 – Setup Sanitary Facilities | 9.3.060 – Setup Sanitary Facilities.docx | 9.3.060 | Setup Sanitary Facilities | To provide adequate sanitary facilities (toilets, wash stations) for workers in compliance with OSHA requirements and project specifications. Scope This SOP applies to Project Managers and Safety Coordinators during site mobilization and through... | 3 – Mobilization | Site mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer; 9.41.110 – Setup Temporary Water Reference: GSL Project Manager Procedures – Mobilization | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer; 9.41.110 – Setup Temporary Water Reference: GSL Project Manager Procedures – Mobilization | 2026-01-15 | 2027-01-15 | SOP
9.3.070 | 9.3.070 – Setup Temporary Lighting | 9.3.070 – Setup Temporary Lighting.docx | 9.3.070 | Setup Temporary Lighting | To provide adequate temporary lighting for safety, security, and productivity during construction. Scope This SOP applies to Project Managers, Field Supervisors, and Safety Coordinators during mobilization and project execution. | 3 – Mobilization | Site mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.105 – Setup Temporary Power; 9.41.110 – Setup Temporary Water; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.105 – Setup Temporary Power; 9.41.110 – Setup Temporary Water; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | 2026-01-15 | 2027-01-15 | SOP
9.3.080 | 9.3.080 – Setup Signage | 9.3.080 – Setup Signage.docx | 9.3.080 | Setup Signage | To install signage that provides safety information, site identification, and directional guidance for workers, visitors, and the public. Scope This SOP applies to Project Managers, Field Supervisors, and Safety Coordinators during mobilization. | 3 – Mobilization | Site mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | 2026-01-15 | 2027-01-15 | SOP
9.3.090 | 9.3.090 – Setup Security | 9.3.090 – Setup Security.docx | 9.3.090 | Setup Security | To establish security measures that protect personnel, equipment, and materials from theft, vandalism, and unauthorized access. Scope This SOP applies to Project Managers, Field Supervisors, and Safety Coordinators during mobilization and throug... | 3 – Mobilization | Site mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.125 – Setup Signage Reference: GSL Project Manager Procedures – Mobilization | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.125 – Setup Signage Reference: GSL Project Manager Procedures – Mobilization | 2026-01-15 | 2027-01-15 | SOP
9.3.100 | 9.3.100 – Setup Laydown Area | 9.3.100 – Setup Laydown Area.docx | 9.3.100 | Setup Laydown Area | To establish a designated laydown area for material storage and staging to support efficient project operations and site safety. Scope This SOP applies to Project Managers and Field Supervisors during mobilization. | 3 – Mobilization | Site mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.095 – Setup Storage Trailer; 9.41.100 – Setup Site Fencing and Access Control Reference: GSL Project Manager Procedures – Mobilization | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.095 – Setup Storage Trailer; 9.41.100 – Setup Site Fencing and Access Control Reference: GSL Project Manager Procedures – Mobilization | 2026-01-15 | 2027-01-15 | SOP
9.3.110 | 9.3.110 – Setup Equipment Staging | 9.3.110 – Setup Equipment Staging.docx | 9.3.110 | Setup Equipment Staging | To establish designated areas for equipment staging, ensuring safe and efficient deployment of construction equipment. Scope This SOP applies to Project Managers, Field Supervisors, and Equipment Operators during mobilization. | 3 – Mobilization | Site mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area Reference: GSL Project Manager Procedures – Mobilization | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area Reference: GSL Project Manager Procedures – Mobilization | 2026-01-15 | 2027-01-15 | SOP
9.3.120 | 9.3.120 – Setup Parking | 9.3.120 – Setup Parking.docx | 9.3.120 | Setup Parking | To designate and manage parking areas for workers, visitors, and deliveries, ensuring safety and minimizing disruption to site operations. Scope This SOP applies to Project Managers, Field Supervisors, and Safety Coordinators during mobilization. | 3 – Mobilization | Site mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Mobilization | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Mobilization | 2026-01-15 | 2027-01-15 | SOP
9.3.470 | 9.3.470 – Develop Site-Specific Safety Plan | 9.3.470 – Develop Site Specific Safety Plan.docx | 9.3.470 | Develop Site-Specific Safety Plan | To prepare and implement a site-specific safety plan (SSSP) that identifies hazards, compliance requirements, and procedures to protect workers and the public. Scope This SOP applies to Project Managers, Safety Coordinators, and Field Supervisors. | 3 – Mobilization | Safety setup | Mobilization | [Inferred] Safety Coordinator (C); Project Manager (R); Field Supervisor (C) |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-15 | 2027-01-15 | SOP
9.4.010 | 9.4.010 – Conduct Coordination Meetings | 9.4.010 – Conduct Coordination Meetings.docx | 9.4.010 | Conduct Coordination Meetings | To establish a standard process for conducting project coordination meetings to ensure alignment between all project stakeholders, resolve issues, and review progress. Scope This SOP applies to Project Managers, Field Supervisors, Subcontractors... | 4 – Execution | Coordination | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Owner/GC Coordination Meetings; 9.41.170 – Conduct Progress Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Coordination | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Owner/GC Coordination Meetings; 9.41.170 – Conduct Progress Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Coordination | 2026-01-15 | 2027-01-15 | SOP
9.4.020 | 9.4.020 – Conduct Subcontractor Coordination Meetings | 9.4.020 – Conduct Subcontractor Coordination Meetings.docx | 9.4.020 | Conduct Subcontractor Coordination Meetings | To lead regular subcontractor coordination meetings to ensure subcontractor activities align with project schedule, logistics, and safety requirements. Scope This SOP applies to Project Managers, Field Supervisors, and all subcontractors assigne... | 4 – Execution | Coordination | Execution | [Inferred] Subcontractors (R); Project Manager (R); Field Supervisor (C) |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Coordination | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Coordination | 2026-01-15 | 2027-01-15 | SOP
9.4.030 | 9.4.030 – Conduct Client/Owner Meetings | 9.4.030 – Conduct Client Owner Meetings.docx | 9.4.030 | Conduct Client/Owner Meetings | To conduct meetings with the client/owner to provide project updates, resolve issues, and ensure contractual and performance expectations are met. Scope This SOP applies to Project Managers, Branch Managers, and project teams when interfacing wi... | 4 – Execution | Coordination | Execution | [Inferred] Branch Manager (C); Project Manager (A); Field Supervisor (C) |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable Clauses; 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Project Manager Procedures – Coordination | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable Clauses; 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Project Manager Procedures – Coordination | 2026-01-15 | 2027-01-15 | SOP
9.4.040 | 9.4.040 – Conduct Safety Meetings | 9.4.040 – Conduct Safety Meetings.docx | 9.4.040 | Conduct Safety Meetings | To conduct regular safety meetings to promote awareness, communicate hazards, and reinforce compliance with OSHA and GSL safety standards. Scope This SOP applies to Project Managers, Safety Coordinators, Field Supervisors, and all on-site person... | 4 – Execution | Safety management | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.115 – Setup Sanitary Facilities; 9.41.120 – Setup Temporary Lighting Reference: GSL Project Manager Procedures – Coordination | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.115 – Setup Sanitary Facilities; 9.41.120 – Setup Temporary Lighting Reference: GSL Project Manager Procedures – Coordination | 2026-01-15 | 2027-01-15 | SOP
9.4.045 | 9.4.045 – Identify Value Engineering & Prefabrication Opportunities | 9.4.045 – Identify Value Engineering & Prefabrication Opportunities.docx | 9.4.045 | Identify Value Engineering & Prefabrication Opportunities | To identify and evaluate opportunities for value engineering (VE) and prefabrication to reduce cost, improve efficiency, and simplify work without compromising project scope or quality. Scope This SOP applies to Project Managers, Field Superviso... | 4 – Execution | Execution | Execution | [Inferred] Prefabrication Lead (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.050 – Prepare Construction Takeoff Reference: GSL Pre-Construction Planning – Value Engineering & Prefabrication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.050 – Prepare Construction Takeoff Reference: GSL Pre-Construction Planning – Value Engineering & Prefabrication | 2026-01-15 | 2027-01-15 | SOP
9.4.050 | 9.4.050 – Conduct Prefabrication Coordination Meetings | 9.4.050 – Conduct Prefabrication Coordination Meetings.docx | 9.4.050 | Conduct Prefabrication Coordination Meetings | To coordinate with the prefabrication team to align prefab deliverables with the construction schedule, manpower plan, and site logistics. Scope This SOP applies to Project Managers, Prefab Leads, and Field Supervisors during pre-construction an... | 4 – Execution | Coordination | Execution | [Inferred] Prefabrication Lead (R); Project Manager (R); Field Supervisor (C) |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.050 – Prepare Construction Takeoff; 9.41.065 – Develop Labor Budget Reference: GSL Project Manager Procedures – Coordination | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.050 – Prepare Construction Takeoff; 9.41.065 – Develop Labor Budget Reference: GSL Project Manager Procedures – Coordination | 2026-01-15 | 2027-01-15 | SOP
9.4.055 | 9.4.055 – Procurement of Large Feeder Wire | 9.4.055 – 1 Procurement of Large Feeder Wire.docx | 9.4.055 | Procurement of Large Feeder Wire | To define the standardized process for the planning, procurement, and delivery of large feeder wire to ensure that project cost, schedule, and quality targets are achieved in accordance with GSL Electric’s Management Directives. 2. | 4 – Execution | Procurement execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Operations | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Operations | 2026-01-15 | 2027-01-15 | SOP
9.4.060 | 9.4.060 – Conduct Quality Meetings | 9.4.060 – Conduct Quality Meetings.docx | 9.4.060 | Conduct Quality Meetings | To conduct regular quality meetings to ensure project work meets specifications, client requirements, and GSL standards. Scope This SOP applies to Project Managers, Field Supervisors, Safety Coordinators, and Quality Inspectors during pre-constr... | 4 – Execution | Quality management | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Quality Control Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.080 – Establish Tracking & Control Systems Reference: GSL Project Manager Procedures – Coordination | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality Control Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.080 – Establish Tracking & Control Systems Reference: GSL Project Manager Procedures – Coordination | 2026-01-15 | 2027-01-15 | SOP
9.4.190 | 9.4.190 – Document Filing Standards | 9.4.190 – A Document Filing Standards.docx | 9.4.190 | Document Filing Standards | To define standard filing responsibilities and locations for all project documentation to ensure consistency, accountability, and accessibility. Scope This SOP applies to all Project Managers, Field Foremen, Site Administrators, and Subcontracto... | 4 – Execution | Document management | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: All documentation-related SOPs (9.41.195 – 9.41.265 and beyond) Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: All documentation-related SOPs (9.41.195 – 9.41.265 and beyond) Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.195 | 9.4.195 – Manage Project Documentation System | 9.4.195 – Manage Project Documentation System.docx | 9.4.195 | Manage Project Documentation System | To establish and maintain a structured documentation system that ensures all project records are organized, accessible, and compliant with contractual and legal requirements. Scope This SOP applies to Project Managers, Site Administrators, and F... | 4 – Execution | Document management | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.005 – Team Selection; 9.41.010 – Project Turnover Meeting; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.005 – Team Selection; 9.41.010 – Project Turnover Meeting; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.200 | 9.4.200 – Manage Submittals | 9.4.200 – Manage Submittals.docx | 9.4.200 | Manage Submittals | To establish a standard process for preparing, submitting, tracking, and closing out all project submittals to ensure compliance with specifications and schedule. Scope This SOP applies to Project Managers, Purchasing, and Subcontractors. | 4 – Execution | Document management | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.050 – Prepare Construction Takeoff; 9.41.055 – Procurement of Large Feeder Wire; 9.41.075 – Develop Project Schedule; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.050 – Prepare Construction Takeoff; 9.41.055 – Procurement of Large Feeder Wire; 9.41.075 – Develop Project Schedule; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.205 | 9.4.205 – Manage RFIs (Requests for Information) | 9.4.205 – Manage RF Is (Requests for Information).docx | 9.4.205 | Manage RFIs (Requests for Information) | To standardize the RFI process to ensure issues are documented, submitted, tracked, and resolved in a timely manner. Scope This SOP applies to Project Managers, Field Supervisors, and Subcontractors. | 4 – Execution | Document management | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Pre-Construction Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Pre-Construction Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.210 | 9.4.210 – Manage Meeting Minutes | 9.4.210 – Manage Meeting Minutes.docx | 9.4.210 | Manage Meeting Minutes | To standardize the recording, distribution, and archiving of meeting minutes to ensure accountability and continuity. Scope This SOP applies to Project Managers, Site Administrators, and meeting participants. | 4 – Execution | Coordination | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Client/Owner Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Client/Owner Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.215 | 9.4.215 – Manage Daily Reports | 9.4.215 – Manage Daily Reports.docx | 9.4.215 | Manage Daily Reports | To document daily site conditions, manpower, equipment, progress, and incidents. Scope This SOP applies to Field Supervisors, Project Managers, and Safety Coordinators. | 4 – Execution | Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.080 – Establish Tracking & Control Systems; 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.080 – Establish Tracking & Control Systems; 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.220 | 9.4.220 – Manage Drawing Logs | 9.4.220 – Manage Drawing Logs.docx | 9.4.220 | Manage Drawing Logs | To maintain an accurate and up-to-date drawing log, ensuring the field team works from the latest approved drawings. Scope This SOP applies to Project Managers, Site Administrators, and Field Supervisors. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.225 | 9.4.225 – Manage Specifications | 9.4.225 – Manage Specifications.docx | 9.4.225 | Manage Specifications | To ensure specifications are properly logged, tracked, distributed, and accessible to all team members. Scope This SOP applies to Project Managers, Site Administrators, and Field Supervisors. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.200 – Manage Submittals; 9.41.220 – Manage Drawing Logs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.200 – Manage Submittals; 9.41.220 – Manage Drawing Logs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.230 | 9.4.230 – Manage Correspondence | 9.4.230 – Manage Correspondence.docx | 9.4.230 | Manage Correspondence | To log, track, and store all project-related correspondence for accountability and claims protection. Scope This SOP applies to Project Managers, Site Administrators, and Field Foremen. | 4 – Execution | Execution | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.205 – Manage RFIs; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.205 – Manage RFIs; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.235 | 9.4.235 – Manage Permits | 9.4.235 – Manage Permits.docx | 9.4.235 | Manage Permits | To obtain, track, and maintain all project permits and inspection records required by law and contract. Scope This SOP applies to Project Managers, Safety Coordinators, and Site Administrators. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Safety / Compliance Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Safety / Compliance Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.240 | 9.4.240 – Manage Inspection Reports | 9.4.240 – Manage Inspection Reports.docx | 9.4.240 | Manage Inspection Reports | To ensure inspection reports (safety, quality, and compliance) are logged, distributed, and archived to support accountability and corrective actions. Scope This SOP applies to Project Managers, Safety Coordinators, Quality Inspectors, and Site ... | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Quality / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.235 – Manage Permits; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.235 – Manage Permits; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-15 | 2027-01-15 | SOP
9.4.270 | 9.4.270 – Manage Project Communications | 9.4.270 – Manage Project Communications.docx | 9.4.270 | Manage Project Communications | To establish a consistent process for managing all project-related communications to ensure clarity, accountability, and traceability. Scope This SOP applies to Project Managers, Field Foremen, and Site Administrators. | 4 – Execution | Communications | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-15 | 2027-01-15 | SOP
9.4.275 | 9.4.275 – Manage Internal Communications | 9.4.275 – Manage Internal Communications.docx | 9.4.275 | Manage Internal Communications | To ensure timely and accurate communication within the GSL project team to support coordination and decision-making. Scope This SOP applies to Project Managers, Field Foremen, Superintendents, and Site Administrators. | 4 – Execution | Communications | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.165 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.165 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-15 | 2027-01-15 | SOP
9.4.280 | 9.4.280 – Manage External Communications | 9.4.280 – Manage External Communications.docx | 9.4.280 | Manage External Communications | To establish guidelines for all communications with clients, owners, architects, engineers, subcontractors, and vendors. Scope This SOP applies to Project Managers, Site Administrators, and Field Foremen. | 4 – Execution | Communications | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-15 | 2027-01-15 | SOP
9.4.285 | 9.4.285 – Manage Client/Owner Communications | 9.4.285 – Manage Client Owner Communications.docx | 9.4.285 | Manage Client/Owner Communications | To establish guidelines for consistent and professional communications with the client/owner, ensuring contractual obligations, updates, and issues are clearly documented. Scope This SOP applies to Project Managers, Branch Managers, and Site Adm... | 4 – Execution | Communications | Execution | [Inferred] Branch Manager (C); Project Manager (R); Field Supervisor (C) |  | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-15 | 2027-01-15 | SOP
9.4.290 | 9.4.290 – Manage Subcontractor Communications | 9.4.290 – Manage Subcontractor Communications.docx | 9.4.290 | Manage Subcontractor Communications | To establish a standard process for documenting and tracking communications with subcontractors to ensure clarity, accountability, and compliance. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 – Execution | Communications | Execution | [Inferred] Subcontractors (R); Project Manager (R); Field Supervisor (C) |  | Project Management / Subcontractor Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Subcontractor Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-15 | 2027-01-15 | SOP
9.4.295 | 9.4.295 – Manage Vendor Supplier Communications | 9.4.295 – Manage Vendor Supplier Communications.docx | 9.4.295 | Manage Vendor Supplier Communications | To document and manage all communications with vendors and suppliers to ensure purchase orders, delivery schedules, and technical data are accurate and traceable. Scope This SOP applies to Project Managers, Purchasing, and Site Administrators. | 4 – Execution | Communications | Execution | [Inferred] Purchasing (R); Project Manager (R); Field Supervisor (C) |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.200 – Manage Submittals; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.200 – Manage Submittals; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-15 | 2027-01-15 | SOP
9.4.300 | 9.4.300 – Manage Architect/Engineer Communications | 9.4.300 – Manage Architect Engineer Communications.docx | 9.4.300 | Manage Architect/Engineer Communications | To document and manage all communications with architects and engineers to ensure design clarifications, RFIs, and revisions are properly tracked. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 – Execution | Communications | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-15 | 2027-01-15 | SOP
9.4.305 | 9.4.305 – Manage Regulatory/Authority Communications | 9.4.305 – Manage Regulatory Authority Communications.docx | 9.4.305 | Manage Regulatory/Authority Communications | To document and manage all communications with architects and engineers to ensure design clarifications, RFIs, and revisions are properly tracked. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 – Execution | Communications | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-15 | 2027-01-15 | SOP
9.4.310 | 9.4.310 – Manage General Contractor Communications | 9.4.310 – Manage General Contractor Communications.docx | 9.4.310 | Manage General Contractor Communications | To manage communications with the General Contractor (GC) to ensure coordination, contractual compliance, and documentation of all directives. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 – Execution | Communications | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.150 – Conduct Project Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.150 – Conduct Project Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-15 | 2027-01-15 | SOP
9.4.315 | 9.4.315 – Develop Project Schedule | 9.4.315 – Develop Project Schedule.docx | 9.4.315 | Develop Project Schedule | To establish a baseline project schedule that reflects contractual milestones, critical path activities, and resource requirements. Scope This SOP applies to Project Managers, Superintendents, and Scheduling Coordinators. | 4 – Execution | Schedule management | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.010 – Project Turnover Meeting; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.010 – Project Turnover Meeting; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-15 | 2027-01-15 | SOP
9.4.320 | 9.4.320 – Update Project Schedule | 9.4.320 – Update Project Schedule.docx | 9.4.320 | Update Project Schedule | To update the project schedule regularly, reflecting actual progress, changes, and delays, ensuring alignment with field execution. Scope This SOP applies to Project Managers, Superintendents, and Site Administrators. | 4 – Execution | Schedule management | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.150 – Conduct Project Coordination Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.150 – Conduct Project Coordination Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-15 | 2027-01-15 | SOP
9.4.325 | 9.4.325 – Monitor Schedule Performance | 9.4.325 – Monitor Schedule Performance.docx | 9.4.325 | Monitor Schedule Performance | To monitor schedule performance by comparing baseline, updated schedules, and actual field progress to identify variances and risks. Scope This SOP applies to Project Managers, Superintendents, and Branch Managers. | 4 – Execution | Schedule management | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-15 | 2027-01-15 | SOP
9.4.330 | 9.4.330 – Develop Schedule Recovery Plans | 9.4.330 – Develop Schedule Recovery Plans.docx | 9.4.330 | Develop Schedule Recovery Plans | To create corrective action plans when project schedules deviate from baseline or milestones are at risk. Scope This SOP applies to Project Managers, Superintendents, and Branch Managers. | 4 – Execution | Schedule management | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.325 – Monitor Schedule Performance; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.325 – Monitor Schedule Performance; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-15 | 2027-01-15 | SOP
9.4.335 | 9.4.335 – Prepare Lookahead Schedules | 9.4.335 – Prepare Lookahead Schedules.docx | 9.4.335 | Prepare Lookahead Schedules | To prepare short-term lookahead schedules that detail upcoming work and resource requirements to guide daily and weekly field activities. Scope This SOP applies to Project Managers, Superintendents, and Field Foremen. | 4 – Execution | Schedule management | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-15 | 2027-01-15 | SOP
9.4.340 | 9.4.340 – Manage Resource-Loaded Schedules | 9.4.340 – Manage Resource Loaded Schedules.docx | 9.4.340 | Manage Resource-Loaded Schedules | To integrate labor, equipment, and material resources into the project schedule to provide realistic forecasts and improve resource management. Scope This SOP applies to Project Managers, Superintendents, and Branch Managers. | 4 – Execution | Schedule management | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-15 | 2027-01-15 | SOP
9.4.345 | 9.4.345 – Conduct Schedule Review Meetings | 9.4.345 – Conduct Schedule Review Meetings.docx | 9.4.345 | Conduct Schedule Review Meetings | To review the project schedule with stakeholders at regular intervals, ensuring alignment between planned activities and field performance. Scope This SOP applies to Project Managers, Superintendents, Field Foremen, and Branch Managers. | 4 – Execution | Schedule management | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-15 | 2027-01-15 | SOP
9.4.350 | 9.4.350 – Manage Schedule Change Requests | 9.4.350 – Manage Schedule Change Requests.docx | 9.4.350 | Manage Schedule Change Requests | To evaluate, document, and process schedule change requests to ensure all modifications are justified, approved, and properly incorporated into the project schedule. Scope This SOP applies to Project Managers, Branch Managers, and Site Administr... | 4 – Execution | Schedule management | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Scheduling / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Scheduling / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-15 | 2027-01-15 | SOP
9.4.355 | 9.4.355 – Manage Project Scope | 9.4.355 – Manage Project Scope.docx | 9.4.355 | Manage Project Scope | To define, communicate, and control the contractual scope of work, ensuring all team members and subcontractors understand project requirements. Scope This SOP applies to Project Managers, Estimators, and Field Supervisors. | 4 – Execution | Scope management | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.315 – Develop Project Schedule; 9.41.350 – Manage Schedule Change Requests; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.315 – Develop Project Schedule; 9.41.350 – Manage Schedule Change Requests; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-15 | 2027-01-15 | SOP
9.4.360 | 9.4.360 – Manage Change Orders | 9.4.360 – Manage Change Orders.docx | 9.4.360 | Manage Change Orders | To establish a consistent company-wide procedure for identifying, pricing, approving, documenting, and billing all contract changes (RFQs, Field Change Directives, and disputed changes) in alignment with GSL Electric’s Management Directives for Pr... | 4 – Execution | Scope management | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Operations | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Operations | 2026-01-15 | 2027-01-15 | SOP
9.4.365 | 9.4.365 – Manage Potential Change Orders (PCOs) | 9.4.365 – Manage Potential Change Orders (PCOs).docx | 9.4.365 | Manage Potential Change Orders (PCOs) | To identify, log, and track potential change orders (PCOs) before they become formal change orders, allowing proactive risk management. Scope This SOP applies to Project Managers, Estimators, and Site Administrators. | 4 – Execution | Scope management | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-15 | 2027-01-15 | SOP
9.4.370 | 9.4.370 – Manage Owner Directives | 9.4.370 – Manage Owner Directives.docx | 9.4.370 | Manage Owner Directives | To document and manage all owner directives that modify or clarify the scope of work, ensuring contractual and financial impacts are tracked. Scope This SOP applies to Project Managers, Site Administrators, and Estimators. | 4 – Execution | Execution | Execution | [Inferred] Branch Manager (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-15 | 2027-01-15 | SOP
9.4.375 | 9.4.375 – Manage Scope Clarifications | 9.4.375 – Manage Scope Clarifications.docx | 9.4.375 | Manage Scope Clarifications | To capture, track, and communicate scope clarifications arising during design interpretation, RFIs, or owner/GC discussions. Scope This SOP applies to Project Managers, Estimators, and Field Supervisors. | 4 – Execution | Scope management | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.205 – Manage RFIs; 9.41.370 – Manage Owner Directives; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.205 – Manage RFIs; 9.41.370 – Manage Owner Directives; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-15 | 2027-01-15 | SOP
9.4.380 | 9.4.380 – Manage Backcharges | 9.4.380 – Manage Backcharges.docx | 9.4.380 | Manage Backcharges | To document, track, and process backcharges applied to subcontractors or vendors for work not performed, damaged, or corrected by GSL. Scope This SOP applies to Project Managers, Accounting, and Site Administrators. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.290 – Manage Subcontractor Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.290 – Manage Subcontractor Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-15 | 2027-01-15 | SOP
9.4.385 | 9.4.385 – Manage Force Account Work | 9.4.385 – Manage Force Account Work.docx | 9.4.385 | Manage Force Account Work | To document, track, and bill for force account work performed outside the contract scope but directed by the owner or GC. Scope This SOP applies to Project Managers, Field Supervisors, and Accounting. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) |  | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.380 – Manage Backcharges; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.380 – Manage Backcharges; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-15 | 2027-01-15 | SOP
9.4.390 | 9.4.390 – Manage Claims | 9.4.390 – Manage Claims.docx | 9.4.390 | Manage Claims | To document, prepare, and submit claims for additional time, cost, or damages arising from circumstances outside GSL’s control. Scope This SOP applies to Project Managers, Branch Managers, Estimators, and Legal Counsel. | 4 – Execution | Execution | Execution | [Inferred] Branch Manager (A); Project Manager (A); Field Supervisor (C) |  | Project Management / Contract Administration / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.370 – Manage Owner Directives; 9.41.385 – Manage Force Account Work; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Contract Administration / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.370 – Manage Owner Directives; 9.41.385 – Manage Force Account Work; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-15 | 2027-01-15 | SOP
9.4.400 | 9.4.400 – Monitor Project Costs | 9.4.400 – Monitor Project Costs.docx | 9.4.400 | Monitor Project Costs | To monitor actual costs against the project budget, ensuring variances are detected early and corrective actions are taken. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 – Execution | Cost management | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.405 – Manage Cost Forecasts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.405 – Manage Cost Forecasts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-15 | 2027-01-15 | SOP
9.4.405 | 9.4.405 – Manage Cost Forecasts | 9.4.405 – Manage Cost Forecasts.docx | 9.4.405 | Manage Cost Forecasts | To forecast final project costs based on current performance and anticipated trends, ensuring management has accurate projections. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 – Execution | Cost management | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-15 | 2027-01-15 | SOP
9.4.410 | 9.4.410 – Manage Cost Codes | 9.4.410 – Manage Cost Codes.docx | 9.4.410 | Manage Cost Codes | To standardize and maintain cost codes for consistent budgeting, tracking, and reporting across projects. Scope This SOP applies to Project Managers, Estimators, and Accounting. | 4 – Execution | Cost management | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-15 | 2027-01-15 | SOP
9.4.415 | 9.4.415 – Manage Committed Costs | 9.4.415 – Manage Committed Costs.docx | 9.4.415 | Manage Committed Costs | To track and manage committed costs (purchase orders, subcontracts, and other financial commitments) against the project budget. Scope This SOP applies to Project Managers, Purchasing, and Accounting. | 4 – Execution | Cost management | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-15 | 2027-01-15 | SOP
9.4.420 | 9.4.420 – Manage Actual Costs | 9.4.420 – Manage Actual Costs.docx | 9.4.420 | Manage Actual Costs | To record, verify, and report actual costs incurred on the project for accurate financial tracking and reporting. Scope This SOP applies to Project Managers, Accounting, and Site Administrators. | 4 – Execution | Cost management | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-15 | 2027-01-15 | SOP
9.4.425 | 9.4.425 – Manage Job Cost Reports | 9.4.425 – Manage Job Cost Reports.docx | 9.4.425 | Manage Job Cost Reports | To prepare and distribute job cost reports that compare actual and committed costs to the budget, ensuring management visibility of project financial status. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 – Execution | Cost management | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-15 | 2027-01-15 | SOP
9.4.430 | 9.4.430 – Manage Profit Projections | 9.4.430 – Manage Profit Projections.docx | 9.4.430 | Manage Profit Projections | To project project-level and portfolio-level profitability by comparing revenue, costs, and forecasts. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 – Execution | Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-15 | 2027-01-15 | SOP
9.4.435 | 9.4.435 – Manage Cost-to-Complete | 9.4.435 – Manage Cost to Complete.docx | 9.4.435 | Manage Cost-to-Complete | To calculate and monitor cost-to-complete (CTC) values, ensuring accurate forecasting of final project costs and profitability. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 – Execution | Cost management | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.420 – Manage Actual Costs; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.420 – Manage Actual Costs; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-15 | 2027-01-15 | SOP
9.4.440 | 9.4.440 – Prepare Billing Schedule | 9.4.440 – Prepare Billing Schedule.docx | 9.4.440 | Prepare Billing Schedule | To develop a billing schedule that aligns with the project contract, milestones, and cash flow requirements. Scope This SOP applies to Project Managers and Accounting. | 4 – Execution | Schedule management | Execution | [Inferred] Accounting (R); Superintendent (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-15 | 2027-01-15 | SOP
9.4.445 | 9.4.445 – Prepare Monthly Pay Applications | 9.4.445 – Prepare Monthly Pay Applications.docx | 9.4.445 | Prepare Monthly Pay Applications | To prepare monthly pay applications in accordance with the contract, ensuring accurate billing of work performed and materials stored. Scope This SOP applies to Project Managers, Field Supervisors, and Accounting. | 4 – Execution | Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.440 – Prepare Billing Schedule; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.440 – Prepare Billing Schedule; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-15 | 2027-01-15 | SOP
9.4.450 | 9.4.450 – Track Accounts Receivable | 9.4.450 – Track Accounts Receivable.docx | 9.4.450 | Track Accounts Receivable | To track accounts receivable (AR) from submitted invoices and pay applications, ensuring timely collection of payments. Scope This SOP applies to Accounting, Project Managers, and Branch Managers. | 4 – Execution | Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) |  | Accounting / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Accounting / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-15 | 2027-01-15 | SOP
9.4.455 | 9.4.455 – Manage Lien Waivers | 9.4.455 – Manage Lien Waivers.docx | 9.4.455 | Manage Lien Waivers | To collect, verify, and submit lien waivers in compliance with contract requirements and to protect against payment disputes. Scope This SOP applies to Project Managers, Accounting, and Subcontractors. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-15 | 2027-01-15 | SOP
9.4.460 | 9.4.460 – Manage Retainage | 9.4.460 – Manage Retainage.docx | 9.4.460 | Manage Retainage | To track retainage withheld on pay applications and ensure proper release at substantial completion and final project closeout. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 – Execution | Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.465 – Manage Final Invoicing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.465 – Manage Final Invoicing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-15 | 2027-01-15 | SOP
9.4.465 | 9.4.465 – Manage Final Invoicing | 9.4.465 – Manage Final Invoicing.docx | 9.4.465 | Manage Final Invoicing | To prepare and submit the final invoice for project payment, ensuring all conditions precedent to final payment are satisfied. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.455 – Manage Lien Waivers; 9.41.460 – Manage Retainage; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.455 – Manage Lien Waivers; 9.41.460 – Manage Retainage; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-15 | 2027-01-15 | SOP
9.4.475 | 9.4.475 – Conduct Safety Orientation | 9.4.475 – Conduct Safety Orientation.docx | 9.4.475 | Conduct Safety Orientation | To provide safety orientation for all employees, subcontractors, and visitors before they begin work on-site. Scope This SOP applies to Safety Coordinators, Project Managers, and Field Supervisors. | 4 – Execution | Safety management | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) |  | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-15 | 2027-01-15 | SOP
9.4.480 | 9.4.480 – Conduct Safety Inspections | 9.4.480 – Conduct Safety Inspections.docx | 9.4.480 | Conduct Safety Inspections | To conduct regular safety inspections of the jobsite, identify hazards, and verify compliance with OSHA and company standards. Scope This SOP applies to Safety Coordinators, Field Supervisors, and Project Managers. | 4 – Execution | Safety management | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) |  | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-15 | 2027-01-15 | SOP
9.4.485 | 9.4.485 – Conduct Safety Meetings | 9.4.485 – Conduct Safety Meetings.docx | 9.4.485 | Conduct Safety Meetings | To conduct regular safety meetings (toolbox talks and formal sessions) to communicate safety policies, hazards, and corrective actions. Scope This SOP applies to Safety Coordinators, Project Managers, and Field Supervisors. | 4 – Execution | Safety management | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-15 | 2027-01-15 | SOP
9.4.490 | 9.4.490 – Report Safety Incidents | 9.4.490 – Report Safety Incidents.docx | 9.4.490 | Report Safety Incidents | To report all safety incidents, including near misses, injuries, and property damage, in a timely and consistent manner. Scope This SOP applies to all employees, subcontractors, Project Managers, and Safety Coordinators. | 4 – Execution | Safety management | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.485 – Conduct Safety Meetings; 9.41.495 – Investigate Accidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.485 – Conduct Safety Meetings; 9.41.495 – Investigate Accidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-15 | 2027-01-15 | SOP
9.4.495 | 9.4.495 – Investigate Accidents | 9.4.495 – Investigate Accidents.docx | 9.4.495 | Investigate Accidents | To investigate accidents and near misses to identify root causes, prevent recurrence, and comply with regulatory requirements. Scope This SOP applies to Project Managers, Safety Coordinators, Field Supervisors, and Branch Managers. | 4 – Execution | Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) |  | Safety / Project Management / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.490 – Report Safety Incidents; 9.41.485 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Project Management / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.490 – Report Safety Incidents; 9.41.485 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-15 | 2027-01-15 | SOP
9.4.500 | 9.4.500 – Conduct Emergency Preparedness | 9.4.500 – Conduct Emergency Preparedness.docx | 9.4.500 | Conduct Emergency Preparedness | To establish and maintain emergency preparedness procedures to ensure a safe and effective response to jobsite emergencies. Scope This SOP applies to Safety Coordinators, Project Managers, Field Supervisors, and all jobsite personnel. | 4 – Execution | Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.490 – Report Safety Incidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.490 – Report Safety Incidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-15 | 2027-01-15 | SOP
9.4.505 | 9.4.505 – Conduct Safety Compliance Audits | 9.4.505 – Conduct Safety Compliance Audits.docx | 9.4.505 | Conduct Safety Compliance Audits | To conduct safety compliance audits that verify adherence to OSHA standards, contract requirements, and company policies. Scope This SOP applies to Safety Coordinators, Project Managers, and Branch Managers. | 4 – Execution | Safety management | Execution | [Inferred] Safety Coordinator (C); Project Manager (A); Field Supervisor (C) |  | Safety / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.480 – Conduct Safety Inspections; 9.41.495 – Investigate Accidents; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.480 – Conduct Safety Inspections; 9.41.495 – Investigate Accidents; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-15 | 2027-01-15 | SOP
9.4.510 | 9.4.510 – Provide Safety Training | 9.4.510 – Provide Safety Training.docx | 9.4.510 | Provide Safety Training | To provide ongoing safety training for employees and subcontractors, ensuring compliance with regulatory standards and company policies. Scope This SOP applies to Safety Coordinators, Project Managers, and HR. | 4 – Execution | Safety management | Execution | [Inferred] Safety Coordinator (C); Project Manager (A); Field Supervisor (C) |  | Safety / Human Resources Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.475 – Conduct Safety Orientation; 9.41.485 – Conduct Safety Meetings; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Human Resources Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.475 – Conduct Safety Orientation; 9.41.485 – Conduct Safety Meetings; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-15 | 2027-01-15 | SOP
9.4.515 | 9.4.515 – Develop Quality Management Plan | 9.4.515 – Develop Quality Management Plan.docx | 9.4.515 | Develop Quality Management Plan | To develop a project-specific Quality Management Plan (QMP) that defines standards, responsibilities, inspections, and acceptance criteria. Scope This SOP applies to Project Managers, Quality Inspectors, and Field Supervisors. | 4 – Execution | Quality management | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-15 | 2027-01-15 | SOP
9.4.520 | 9.4.520 – Conduct Quality Meetings | 9.4.520 – Conduct Quality Meetings.docx | 9.4.520 | Conduct Quality Meetings | To conduct regular quality meetings to review standards, discuss issues, and ensure compliance with project requirements. Scope This SOP applies to Project Managers, Quality Inspectors, Field Supervisors, and Subcontractors. | 4 – Execution | Quality management | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.175 – Conduct Quality Meetings; 9.41.515 – Develop Quality Management Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.175 – Conduct Quality Meetings; 9.41.515 – Develop Quality Management Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-15 | 2027-01-15 | SOP
9.4.525 | 9.4.525 – Conduct Quality Inspections | 9.4.525 – Conduct Quality Inspections.docx | 9.4.525 | Conduct Quality Inspections | To perform inspections that verify work complies with contract documents, specifications, and quality standards. Scope This SOP applies to Quality Inspectors, Project Managers, and Field Supervisors. | 4 – Execution | Quality management | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) |  | Safety / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.515 – Develop Quality Management Plan; 9.41.520 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Safety / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.515 – Develop Quality Management Plan; 9.41.520 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-15 | 2027-01-15 | SOP
9.4.530 | 9.4.530 – Manage Quality Testing | 9.4.530 – Manage Quality Testing.docx | 9.4.530 | Manage Quality Testing | To perform and document quality testing in accordance with project specifications, codes, and standards. Scope This SOP applies to Quality Inspectors, Testing Agencies, and Project Managers. | 4 – Execution | Quality management | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.525 – Conduct Quality Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.525 – Conduct Quality Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-15 | 2027-01-15 | SOP
9.4.535 | 9.4.535 – Manage Nonconformance Reports (NCRs) | 9.4.535 – Manage Nonconformance Reports (NC Rs).docx | 9.4.535 | Manage Nonconformance Reports (NCRs) | To identify, document, and resolve nonconforming work in a consistent and traceable manner. Scope This SOP applies to Project Managers, Quality Inspectors, and Field Supervisors. | 4 – Execution | Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.530 – Manage Quality Testing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.530 – Manage Quality Testing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-15 | 2027-01-15 | SOP
9.4.540 | 9.4.540 – Manage Quality Records | 9.4.540 – Manage Quality Records.docx | 9.4.540 | Manage Quality Records | To establish a system for maintaining and archiving quality records that demonstrate compliance with project and contractual requirements. Scope This SOP applies to Project Managers, Site Administrators, and Quality Inspectors. | 4 – Execution | Quality management | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.530 – Manage Quality Testing; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.530 – Manage Quality Testing; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-15 | 2027-01-15 | SOP
9.4.545 | 9.4.545 – Manage Punch List Quality | 9.4.545 – Manage Punch List Quality.docx | 9.4.545 | Manage Punch List Quality | To ensure punch list items are documented, corrected, and verified for quality compliance prior to project closeout. Scope This SOP applies to Project Managers, Field Supervisors, Subcontractors, and Quality Inspectors. | 4 – Execution | Quality management | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.245 – Manage Punch Lists; 9.41.525 – Conduct Quality Inspections; 9.41.540 – Manage Quality Records; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.245 – Manage Punch Lists; 9.41.525 – Conduct Quality Inspections; 9.41.540 – Manage Quality Records; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-15 | 2027-01-15 | SOP
9.4.560 | 9.4.560 – Manage Manpower Allocation | 9.4.560 – Manage Manpower Allocation.docx | 9.4.560 | Manage Manpower Allocation | To allocate manpower efficiently across projects, ensuring sufficient labor resources are available to meet schedule and productivity requirements. Scope This SOP applies to Project Managers, Superintendents, and Field Supervisors. | 4 – Execution | Resource management | Execution | [Inferred] Field Supervisor (R); Project Manager (A) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-15 | 2027-01-15 | SOP
9.4.565 | 9.4.565 – Manage Equipment Allocation | 9.4.565 – Manage Equipment Allocation.docx | 9.4.565 | Manage Equipment Allocation | To allocate, track, and maintain equipment resources across projects to ensure availability and cost efficiency. Scope This SOP applies to Project Managers, Superintendents, and Equipment Managers. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-15 | 2027-01-15 | SOP
9.4.570 | 9.4.570 – Manage Material Allocation | 9.4.570 – Manage Material Allocation.docx | 9.4.570 | Manage Material Allocation | To manage allocation and delivery of materials to ensure availability at the right time and location while minimizing waste and storage costs. Scope This SOP applies to Project Managers, Purchasing, and Field Supervisors. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.565 – Manage Equipment Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.565 – Manage Equipment Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-15 | 2027-01-15 | SOP
9.4.576 | 9.4.576 – Manage Subcontractor Resources | 9.4.576 – Manage Subcontractor Resources.docx | 9.4.576 | Manage Subcontractor Resources | To manage subcontractor manpower, equipment, and material resources to ensure their availability aligns with project requirements and schedules. Scope This SOP applies to Project Managers, Field Supervisors, and Subcontractors. | 4 – Execution | Resource management | Execution | [Inferred] Subcontractors (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.415 – Manage Committed Costs; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.415 – Manage Committed Costs; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-15 | 2027-01-15 | SOP
9.4.580 | 9.4.580 – Manage Vendor Resources | 9.4.580 – Manage Vendor Resources.docx | 9.4.580 | Manage Vendor Resources | To coordinate vendor-provided resources (materials, deliveries, technical support) to ensure timely project execution. Scope This SOP applies to Project Managers, Purchasing, and Vendors. | 4 – Execution | Procurement execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.295 – Manage Vendor / Supplier Communications; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.295 – Manage Vendor / Supplier Communications; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-15 | 2027-01-15 | SOP
9.4.585 | 9.4.585 – Plan Prefabrication Resources | 9.4.585 – Plan Prefabrication Resources.docx | 9.4.585 | Plan Prefabrication Resources | To plan prefabrication resources (labor, space, tools, and materials) to optimize efficiency, reduce jobsite congestion, and improve quality. Scope This SOP applies to Project Managers, Prefabrication Managers, and Field Supervisors. | 4 – Execution | Resource management | Execution | [Inferred] Prefabrication Lead (R); Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-15 | 2027-01-15 | SOP
9.4.590 | 9.4.590 – Manage Specialty Contractor Resources | 9.4.590 – Manage Specialty Contractor Resources.docx | 9.4.590 | Manage Specialty Contractor Resources | To manage specialty contractor resources (e.g. | 4 – Execution | Resource management | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.575 – Manage Subcontractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.575 – Manage Subcontractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-15 | 2027-01-15 | SOP
9.4.595 | 9.4.595 – Prepare Resource Reports | 9.4.595 – Prepare Resource Reports.docx | 9.4.595 | Prepare Resource Reports | To prepare weekly and monthly resource reports that summarize manpower, equipment, material, and subcontractor usage across the project. Scope This SOP applies to Project Managers, Superintendents, and Branch Managers. | 4 – Execution | Resource management | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.590 – Manage Specialty Contractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.590 – Manage Specialty Contractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-15 | 2027-01-15 | SOP
9.4.605 | 9.4.605 – Issue Purchase Orders | 9.4.605 – Issue Purchase Orders.docx | 9.4.605 | Issue Purchase Orders | To issue purchase orders (POs) for materials and equipment, ensuring accuracy, cost compliance, and delivery coordination. Scope This SOP applies to Purchasing, Project Managers, and Accounting. | 4 – Execution | Procurement execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.415 – Manage Committed Costs; 9.41.600 – Develop Procurement Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.415 – Manage Committed Costs; 9.41.600 – Develop Procurement Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.610 | 9.4.610 – Manage Vendor Prequalification | 9.4.610 – Manage Vendor Prequalification.docx | 9.4.610 | Manage Vendor Prequalification | To prequalify vendors and suppliers based on financial stability, safety record, quality performance, and capacity. Scope This SOP applies to Purchasing, Project Managers, and Branch Managers. | 4 – Execution | Procurement execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Procurement / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.290 – Manage Subcontractor Communications; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Procurement / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.290 – Manage Subcontractor Communications; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.615 | 9.4.615 – Manage Vendor Evaluations | 9.4.615 – Manage Vendor Evaluations.docx | 9.4.615 | Manage Vendor Evaluations | To evaluate vendor performance on each project, focusing on quality, timeliness, cost compliance, and communication. Scope This SOP applies to Project Managers, Purchasing, and Branch Managers. | 4 – Execution | Procurement execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.620 | 9.4.620 – Manage Expediting | 9.4.620 – Manage Expediting.docx | 9.4.620 | Manage Expediting | To expedite vendor and supplier commitments to ensure timely delivery of critical materials and equipment. Scope This SOP applies to Purchasing, Project Managers, and Vendors. | 4 – Execution | Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.625 | 9.4.625 – Manage Delivery Tracking | 9.4.625 – Manage Delivery Tracking.docx | 9.4.625 | Manage Delivery Tracking | To track vendor and supplier deliveries, ensuring that materials and equipment arrive on schedule and in good condition. Scope This SOP applies to Purchasing, Project Managers, and Field Supervisors. | 4 – Execution | Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.620 – Manage Expediting; 9.41.570 – Manage Material Allocation; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.620 – Manage Expediting; 9.41.570 – Manage Material Allocation; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.630 | 9.4.630 – Manage Material Receiving | 9.4.630 – Manage Material Receiving.docx | 9.4.630 | Manage Material Receiving | To ensure materials and equipment received on-site are verified for accuracy, quality, and compliance with purchase orders. Scope This SOP applies to Field Supervisors, Project Managers, and Purchasing. | 4 – Execution | Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Field Operations / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.625 – Manage Delivery Tracking; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.625 – Manage Delivery Tracking; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.631 | 9.4.631 – Release of Large Feeder Wire | 9.4.631 – Release of Large Feeder Wire.docx | 9.4.631 | Release of Large Feeder Wire | Standardizes the process for verifying, releasing, and tracking large feeder wire after procurement to ensure accuracy, proper sequencing, and timely delivery. Scope Applies to all large feeder wire (1 AWG and larger) released from vendor storag... | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Field Leadership / Purchasing | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Leadership / Purchasing | 2026-01-15 | 2027-01-15 | SOP
9.4.635 | 9.4.635 – Manage Material Inspection | 9.4.635 – Manage Material Inspection.docx | 9.4.635 | Manage Material Inspection | To inspect materials and equipment for compliance with specifications, submittals, and quality requirements before installation. Scope This SOP applies to Field Supervisors, Quality Inspectors, and Project Managers. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Field Operations / Quality / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.530 – Manage Quality Testing; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Quality / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.530 – Manage Quality Testing; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.640 | 9.4.640 – Manage Storage and Logistics | 9.4.640 – Manage Storage and Logistics.docx | 9.4.640 | Manage Storage and Logistics | To manage storage and logistics of materials and equipment to ensure availability, protection, and efficient handling on-site. Scope This SOP applies to Project Managers, Field Supervisors, and Warehouse/Logistics Personnel. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.570 – Manage Material Allocation; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.570 – Manage Material Allocation; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.645 | 9.4.645 – Manage Material Handling | 9.4.645 – Manage Material Handling.docx | 9.4.645 | Manage Material Handling | To safely and efficiently handle materials on-site, minimizing waste, damage, and productivity loss. Scope This SOP applies to Field Supervisors, Warehouse/Logistics Personnel, and Project Managers. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Field Operations / Logistics / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Logistics / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.650 | 9.4.650 – Manage Inventory | 9.4.650 – Manage Inventory.docx | 9.4.650 | Manage Inventory | To maintain accurate inventory records of materials, tools, and equipment to ensure availability and accountability. Scope This SOP applies to Field Supervisors, Site Administrators, and Project Managers. | 4 – Execution | Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Field Operations / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.645 – Manage Material Handling; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.645 – Manage Material Handling; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.655 | 9.4.655 – Prepare Procurement Reports | 9.4.655 – Prepare Procurement Reports.docx | 9.4.655 | Prepare Procurement Reports | To prepare weekly and monthly procurement reports that summarize commitments, deliveries, and outstanding issues. Scope This SOP applies to Purchasing, Project Managers, and Branch Managers. | 4 – Execution | Procurement execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Procurement / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.650 – Manage Inventory; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Procurement / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.650 – Manage Inventory; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.660 | 9.4.660 – Manage Procurement Closeout | 9.4.660 – Manage Procurement Closeout.docx | 9.4.660 | Manage Procurement Closeout | To close out all procurement activities by confirming that purchase orders, deliveries, and invoices are complete and reconciled. Scope This SOP applies to Project Managers, Purchasing, and Accounting. | 4 – Execution | Procurement execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.465 – Manage Final Invoicing; 9.41.650 – Manage Inventory; 9.41.655 – Prepare Procurement Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.465 – Manage Final Invoicing; 9.41.650 – Manage Inventory; 9.41.655 – Prepare Procurement Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.665 | 9.4.665 – Reconcile Procurement Accounts | 9.4.665 – Reconcile Procurement Accounts.docx | 9.4.665 | Reconcile Procurement Accounts | To reconcile procurement accounts by confirming all commitments, invoices, and payments match and that no outstanding liabilities remain. Scope This SOP applies to Accounting, Project Managers, and Purchasing. | 4 – Execution | Procurement execution | Execution | [Inferred] Purchasing (R); Accounting (R); Project Manager (A); Field Supervisor (C) |  | Accounting / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.420 – Manage Actual Costs; 9.41.660 – Manage Procurement Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Accounting / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.420 – Manage Actual Costs; 9.41.660 – Manage Procurement Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.670 | 9.4.670 – Manage Vendor Closeout | 9.4.670 – Manage Vendor Closeout.docx | 9.4.670 | Manage Vendor Closeout | To formally close out vendor accounts by verifying completion of work, receipt of materials, and settlement of all financial obligations. Scope This SOP applies to Purchasing, Project Managers, and Accounting. | 4 – Execution | Procurement execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) |  | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.615 – Manage Vendor Evaluations; 9.41.660 – Manage Procurement Closeout; 9.41.665 – Reconcile Procurement Accounts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.615 – Manage Vendor Evaluations; 9.41.660 – Manage Procurement Closeout; 9.41.665 – Reconcile Procurement Accounts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-15 | 2027-01-15 | SOP
9.4.675 | 9.4.675 – Conduct Daily Huddles | 9.4.675 – Conduct Daily Huddles.docx | 9.4.675 | Conduct Daily Huddles | To conduct daily field huddles with crews to communicate work plans, hazards, and coordination needs. Scope This SOP applies to Field Supervisors, Foremen, and Project Managers. | 4 – Execution | Execution | Execution | [Inferred] Foreman (R); Project Manager (A); Field Supervisor (C) |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.680 | 9.4.680 – Conduct Weekly Foreman Meetings | 9.4.680 – Conduct Weekly Foreman Meetings.docx | 9.4.680 | Conduct Weekly Foreman Meetings | To conduct weekly foreman meetings to review schedule, manpower, coordination issues, and site logistics. Scope This SOP applies to Project Managers, Field Supervisors, and Foremen. | 4 – Execution | Coordination | Execution | [Inferred] Foreman (R); Project Manager (A); Field Supervisor (C) |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.690 | 9.4.690 – Track Manpower Utilization | 9.4.690 – Track Manpower Utilization.docx | 9.4.690 | Track Manpower Utilization | To track manpower utilization daily to ensure labor is allocated effectively and productivity targets are met. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 – Execution | Resource management | Execution | [Inferred] Field Supervisor (R); Project Manager (A) |  | Field Operations / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.695 | 9.4.695 – Track Production Quantities | 9.4.695 – Track Production Quantities.docx | 9.4.695 | Track Production Quantities | To track production quantities of installed work daily to measure productivity and progress against plan. Scope This SOP applies to Field Supervisors, Foremen, and Project Managers. | 4 – Execution | Field operations | Execution | [Inferred] Field Supervisor (R); Project Manager (A) |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.400 – Monitor Project Costs; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.400 – Monitor Project Costs; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.700 | 9.4.700 – Track Equipment Utilization | 9.4.700 – Track Equipment Utilization.docx | 9.4.700 | Track Equipment Utilization | To track equipment usage daily to ensure proper allocation, cost control, and productivity. Scope This SOP applies to Field Supervisors, Equipment Managers, and Project Managers. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.565 – Manage Equipment Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.565 – Manage Equipment Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.705 | 9.4.705 – Manage Work Packaging | 9.4.705 – Manage Work Packaging.docx | 9.4.705 | Manage Work Packaging | To break down project scope into manageable work packages for efficient planning, assignment, and tracking. Scope This SOP applies to Project Managers, Field Supervisors, and Foremen. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.335 – Prepare Lookahead Schedules; 9.41.695 – Track Production Quantities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.335 – Prepare Lookahead Schedules; 9.41.695 – Track Production Quantities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.710 | 9.4.710 – Manage Workface Planning | 9.4.710 – Manage Workface Planning.docx | 9.4.710 | Manage Workface Planning | To implement workface planning (WFP) by providing crews with all information, materials, and tools needed before starting field tasks. Scope This SOP applies to Project Managers, Field Supervisors, and Foremen. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.705 – Manage Work Packaging; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.705 – Manage Work Packaging; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.715 | 9.4.715 – Manage Field Coordination | 9.4.715 – Manage Field Coordination.docx | 9.4.715 | Manage Field Coordination | To coordinate daily field activities across crews and subcontractors, ensuring work is sequenced properly and conflicts are resolved. Scope This SOP applies to Project Managers, Field Supervisors, and Subcontractors. | 4 – Execution | Coordination | Execution | [Inferred] Field Supervisor (R); Project Manager (A) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.680 – Conduct Weekly Foreman Meetings; 9.41.705 – Manage Work Packaging; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.680 – Conduct Weekly Foreman Meetings; 9.41.705 – Manage Work Packaging; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.720 | 9.4.720 – Conduct Productivity Analysis | 9.4.720 – Conduct Productivity Analysis.docx | 9.4.720 | Conduct Productivity Analysis | To analyze field productivity by comparing actual labor hours and production against planned values, enabling corrective action. Scope This SOP applies to Project Managers, Field Supervisors, and Accounting. | 4 – Execution | Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.695 – Track Production Quantities; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.695 – Track Production Quantities; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.725 | 9.4.725 – Resolve Field Problems | 9.4.725 – Resolve Field Problems.docx | 9.4.725 | Resolve Field Problems | To resolve field problems promptly to avoid delays, rework, or safety risks. Scope This SOP applies to Field Supervisors, Project Managers, and Quality Inspectors. | 4 – Execution | Field operations | Execution | [Inferred] Field Supervisor (R); Project Manager (A) |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.715 – Manage Field Coordination; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.715 – Manage Field Coordination; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.735 | 9.4.735 – Perform Field Quality Verifications | 9.4.735 – Perform Field Quality Verifications.docx | 9.4.735 | Perform Field Quality Verifications | To perform ongoing quality verifications in the field to ensure work is performed according to drawings, specifications, and approved submittals. Scope This SOP applies to Field Supervisors, Quality Inspectors, and Project Managers. | 4 – Execution | Quality management | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) |  | Field Operations / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.535 – Manage Nonconformance Reports; 9.41.720 – Conduct Productivity Analysis; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.535 – Manage Nonconformance Reports; 9.41.720 – Conduct Productivity Analysis; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.745 | 9.4.745 – Manage Field Rework | 9.4.745 – Manage Field Rework.docx | 9.4.745 | Manage Field Rework | To manage field rework systematically so deficiencies are corrected efficiently, minimizing cost and schedule impacts. Scope This SOP applies to Project Managers, Field Supervisors, Foremen, and Quality Inspectors. | 4 – Execution | Field operations | Execution | [Inferred] Field Supervisor (R); Project Manager (A) |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.535 – Manage Nonconformance Reports; 9.41.725 – Resolve Field Problems; 9.41.735 – Perform Field Quality Verifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.535 – Manage Nonconformance Reports; 9.41.725 – Resolve Field Problems; 9.41.735 – Perform Field Quality Verifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.4.755 | 9.4.755 – Implement Field Productivity Improvements | 9.4.755 – Implement Field Productivity Improvements.docx | 9.4.755 | Implement Field Productivity Improvements | To identify, implement, and monitor productivity improvement measures in field operations. Scope This SOP applies to Project Managers, Field Supervisors, and Foremen. | 4 – Execution | Field operations | Execution | [Inferred] Project Manager (A); Field Supervisor (C) |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.720 – Conduct Productivity Analysis; 9.41.695 – Track Production Quantities; 9.41.585 – Plan Prefabrication Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.720 – Conduct Productivity Analysis; 9.41.695 – Track Production Quantities; 9.41.585 – Plan Prefabrication Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.5.020 | 9.5.020 – Handling and/or Disposing of Excess Materials | 9.5.020 – Handling and or Disposing of Excess Materials.docx | 9.5.020 | Handling and/or Disposing of Excess Materials | To establish a standardized process for conducting commissioning meetings, ensuring proper coordination between all parties during the testing, verification, and turnover phases of the p... | 5 – Commissioning | Commissioning | Commissioning | ¦ Project Manager (A); ¦ Commissioning Agent (R); ¦ Field Supervisor (R); ¦ Quality/QA-QC (C); ¦ Subcontractors (R) |  | Project Management / Quality | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality | 2026-01-15 | 2027-01-15 | SOP
9.5.550 | 9.5.550 – Manage Commissioning Activities | 9.5.550 – Manage Commissioning Activities.docx | 9.5.550 | Manage Commissioning Activities | To establish a standardized process for managing all commissioning activities, ensuring systematic testing, verification, and documentation of electrical systems prior to owner turnover.... | 5 – Commissioning | Commissioning | Commissioning | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Commissioning Agent (R); ¦ Quality/QA-QC (R); ¦ Subcontractors (R) |  | Project Management / Quality | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality | 2026-01-15 | 2027-01-15 | SOP
9.6.005 | 9.6.005 – Prepare for Turnover (Field Perspective) | 9.6.005 – Prepare for Turnover (Field Perspective).docx | 9.6.005 | Prepare for Turnover (Field Perspective) | To prepare field operations for turnover by ensuring punch lists, as-builts, and corrective actions are completed and verified. Scope This SOP applies to Field Supervisors, Foremen, and Project Managers. | 6 – Closeout | Project closeout | Closeout | [Inferred] Project Manager (A) |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.555 – Manage Project Turnover Documentation; 9.41.730 – Manage As-Built Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.555 – Manage Project Turnover Documentation; 9.41.730 – Manage As-Built Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-15 | 2027-01-15 | SOP
9.6.010 | 9.6.010 – Conduct Closeout Meetings | 9.6.010 – Conduct Closeout Meetings.docx | 9.6.010 | Conduct Closeout Meetings | To establish a standardized process for conducting project closeout meetings, ensuring proper coordination of all closeout activities and successful project completion. =================... | 6 – Closeout | Project closeout | Closeout | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Subcontractors (R); ¦ Client/Owner (I) |  | Project Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management | 2026-01-15 | 2027-01-15 | SOP
9.6.015 | 9.6.015 – Manage Project Turnover Documentation | 9.6.015 – Manage Project Turnover Documentation.docx | 9.6.015 | Manage Project Turnover Documentation | To compile, review, and submit all turnover documentation to the Owner/GC, ensuring contractual requirements are satisfied. Scope This SOP applies to Project Managers, Site Administrators, and Branch Managers. | 6 – Closeout | Project closeout | Closeout | [Inferred] Project Manager (A) |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.545 – Manage Punch List Quality; 9.41.550 – Manage Commissioning Activities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.545 – Manage Punch List Quality; 9.41.550 – Manage Commissioning Activities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-15 | 2027-01-15 | SOP
9.6.020 | 9.6.020 – Manage Punch List Closeout | 9.6.020 – Manage Punch List Closeout.docx | 9.6.020 | Manage Punch List Closeout | To complete and verify punch list items before project turnover. Scope This SOP applies to Project Managers, Field Supervisors, Quality Inspectors, and Subcontractors. | 6 – Closeout | Project closeout | Closeout | [Inferred] Quality Inspector (C); Project Manager (A) |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.760 – Prepare for Turnover (Field Perspective); 9.41.555 – Manage Project Turnover Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.760 – Prepare for Turnover (Field Perspective); 9.41.555 – Manage Project Turnover Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-15 | 2027-01-15 | SOP
9.6.030 | 9.6.030 – Manage As-Built Drawings | 9.6.030 – Manage As Built Drawings.docx | 9.6.030 | Manage As-Built Drawings | To establish a standardized process for managing as-built drawings, ensuring accurate documentation of installed conditions for owner records and future maintenance. ====================... | 6 – Closeout | Project closeout | Closeout | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Foreman (R); ¦ Project Engineer/APM (R) |  | Project Management / Field Operations | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Field Operations | 2026-01-15 | 2027-01-15 | SOP
9.6.035 | 9.6.035 – Submit Warranties | 9.6.035 – Submit Warranties.docx | 9.6.035 | Submit Warranties | To collect, verify, and submit warranties to the Owner/GC as part of turnover documentation. Scope This SOP applies to Project Managers, Site Administrators, and Subcontractors. | 6 – Closeout | Project closeout | Closeout | [Inferred] Project Manager (A) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.770 – Manage Punch List Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.770 – Manage Punch List Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-15 | 2027-01-15 | SOP
9.6.040 | 9.6.040 – Submit O&M Manuals | 9.6.040 – Submit O&M Manuals.docx | 9.6.040 | Submit O&M Manuals | To submit Operations & Maintenance (O&M) manuals for equipment and systems in compliance with contract requirements. Scope This SOP applies to Project Managers, Site Administrators, and Vendors/Subcontractors. | 6 – Closeout | Project closeout | Closeout | [Inferred] Project Manager (A) |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.550 – Manage Commissioning Activities; 9.41.775 – Submit Warranties; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.550 – Manage Commissioning Activities; 9.41.775 – Submit Warranties; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-15 | 2027-01-15 | SOP
9.6.050 | 9.6.050 – Provide Owner Training | 9.6.050 – Provide Owner Training.docx | 9.6.050 | Provide Owner Training | To provide Owner training on systems and equipment to ensure proper operation and maintenance after turnover. Scope This SOP applies to Project Managers, Vendors, Subcontractors, and the Owner/GC. | 6 – Closeout | Project closeout | Closeout | [Inferred] Branch Manager (C); Project Manager (A) |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.550 – Manage Commissioning Activities; 9.41.780 – Submit O&M Manuals; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.550 – Manage Commissioning Activities; 9.41.780 – Submit O&M Manuals; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-15 | 2027-01-15 | SOP
9.6.065 | 9.6.065 – Archive Project Documentation | 9.6.065 – Archive Project Documentation.docx | 9.6.065 | Archive Project Documentation | To archive all project documentation for future reference, audits, and warranty compliance. Scope This SOP applies to Project Managers, Site Administrators, and Branch Managers. | 6 – Closeout | Project closeout | Closeout | [Inferred] Site Administrator (R); Project Manager (A) |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.265 – Manage Closeout Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.265 – Manage Closeout Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-15 | 2027-01-15 | SOP
9.6.070 | 9.6.070 – Conduct Post-Project Review | 9.6.070 – Conduct Post Project Review.docx | 9.6.070 | Conduct Post-Project Review | To establish a standardized process for conducting post-project reviews, evaluating project performance, and identifying successes and areas for improvement. ============================... | 6 – Closeout | Project closeout | Closeout | ¦ Branch Manager (A); ¦ Project Manager (R); ¦ Field Supervisor (R); ¦ Operations Manager (C) |  | Project Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management | 2026-01-15 | 2027-01-15 | SOP
9.6.080 | 9.6.080 – Capture Client Feedback | 9.6.080 – Capture Client Feedback.docx | 9.6.080 | Capture Client Feedback | To establish a standardized process for capturing client feedback at project completion, enabling continuous improvement and strengthening client relationships. =========================... | 6 – Closeout | Project closeout | Closeout | ¦ Branch Manager (A); ¦ Project Manager (R); ¦ Business Development (C); ¦ Executive Committee (I) |  | Project Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management | 2026-01-15 | 2027-01-15 | SOP
9.6.085 | 9.6.085 – Document Lessons Learned | 9.6.085 – Document Lessons Learned.docx | 9.6.085 | Document Lessons Learned | To establish a standardized process for documenting lessons learned throughout and at the completion of projects, creating an organizational knowledge base for continuous improvement. ==... | 6 – Closeout | Project closeout | Closeout | ¦ Operations Manager (A); ¦ Project Manager (R); ¦ Field Supervisor (R); ¦ Branch Manager (C) |  | Project Management | 1.0 | 2026-01-15 | Operations | Branch Manager |  | Approved |  |  | Project Management | 2026-01-15 | 2027-01-15 | SOP

## Sheet2
| Management Directives |  | Job Descriptions
Position | Policy Manual, 9.2 Management Directives | File Path | Policy Manual, 7.2 Job Descriptions | File Path
Apprentice | Policy Manual, 9.2 Management Directives |  | Policy Manual, 7.2.1 Apprentice Electrician
Journeyman | Policy Manual, 9.2 Management Directives |  | Policy Manual, 7.2.2 Journeyman Electrician
Leadman | Policy Manual, 9.3 Management Directives |  | Policy Manual, 7.2.3 Lead Journeyman
Foreman | Policy Manual, 9.3 Management Directives |  | Policy Manual, 7.2.4 Foreman
Field Supervisor | Policy Manual, 9.3 Management Directives |  | Policy Manual, 7.2.5 Field Supervisor
General Superintendent | Policy Manual, 9.4 Management Directives |  | Policy Manual, 7.2.6 General Superintendent
Project Manager | Policy Manual, 9.5 Management Directives |  | Policy Manual, 7.2.7 Project Manager
Branch Manager | Policy Manual, 9.6 Management Directives |  | Policy Manual, 7.2.8 Branch Manager
Estimator | Policy Manual, 9.9 Management Directives |  | Policy Manual, 7.2.9 Estimator
Purchasing | Policy Manual, 9.10 Management Directives |  | Policy Manual, 7.2.10 Purchasing Agent
Accounting | Policy Manual, 9.11 Management Directives |  | Policy Manual, 7.2.11 Accounting
Site Administrator | Policy Manual, 9.8 Management Directives |  | Policy Manual, 7.2.12 Site Administrator
Quality Inspector | Policy Manual, 9.13 Management Directives |  | Policy Manual, 7.2.13 Quality Inspector
Safety Coordinator | Policy Manual, 9.7 Management Directives |  | Policy Manual, 7.2.14 Safety Coordinator
Prefabrication Lead | Policy Manual, 9.12 Management Directives |  | Policy Manual, 7.2.15 Prefabrication Lead

## Coverage Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category
9.1.050 – Prepare Construction Takeoff | Oversees Prepare Construction Takeoff | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | General
9.2.005 – Review Contract for High Risk Clauses | Oversees Review Contract for High Risk Clauses | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope and contract review
9.2.010 – Team Selection | Selects Project Manager and assigns or approves final team assignments; Allocates resources across projects; Resolves resource conflicts. | Branch Manager | Sec. 9.6 Branch Management | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | Identifies required roles and skill sets; Recommends team members; Coordinates with Branch Manager on availability. | Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | Validates field leadership assignments; Confirms crew availability and capability | General Superintendent | Sec. 9.4 GS Directives | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | Ensures safety-qualified personnel are assigned, Reviews site-specific safety requirements. | Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | Informed of procurement resource needs | Purchasing | Sec. 9.10 Purchasing Directives | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | Informed of prefab support requirements | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | Project Coordinator | Sec. 9.2 General Directives | ✔ Covered | No change required. | Team selection and turnover
9.2.015 – Project Turnover Meeting | Oversees closeout for Project Turnover Meeting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Team selection and turnover
9.2.020 – Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning
9.2.020 – Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning
9.2.030 – Review Contract for Unfavorable or High-Risk Clauses | Oversees Review Contract for Unfavorable or High-Risk Clauses | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope and contract review
9.2.040 – Project Manager Reviews Plans Specifications & Schedule | Coordinates scheduling for Project Manager Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling
9.2.040 – Project Manager Reviews Plans Specifications & Schedule | Manages technical documentation for Project Manager Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling
9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | Coordinates scheduling for Field Supervisor Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling
9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | Manages technical documentation for Field Supervisor Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling
9.2.055 – Compare Estimated vs Planned Performance | Provides estimating support for Compare Estimated vs Planned Performance | Estimator | Sec. 9.9 Estimating Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning
9.2.055 – Compare Estimated vs Planned Performance | Oversees Compare Estimated vs Planned Performance | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning
9.2.057 – Identify VE and Prefabrication Opportunities | Coordinates prefabrication for Identify VE and Prefabrication Opportunities | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning
9.2.057 – Identify VE and Prefabrication Opportunities | Oversees Identify VE and Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning
9.2.060 – Create Issue List and Begin RFI Process | Manages overall issue resolution; Prioritizes RFIs; Tracks responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Preconstruction planning
9.2.060 – Create Issue List and Begin RFI Process | Creates and submits RFIs; Maintains issue log; Follows up on responses ¦ | ¦ Assistant PM/Project Coordinator | Sec. 9.2 General Directives | ✔ Covered | No change required. | Preconstruction planning
9.2.060 – Create Issue List and Begin RFI Process | Contributes constructability issues; Reviews RFI responses for field impact ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Preconstruction planning
9.2.060 – Create Issue List and Begin RFI Process | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 GS Directives | ✔ Covered | No change required. | Preconstruction planning
9.2.070 – Conduct Site Visit | Coordinates site visit; Documents findings; Integrates into project planning ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Preconstruction planning
9.2.070 – Conduct Site Visit | Conducts physical site inspection; Identifies constructability and logistics issues ¦ | ¦ Field Leadership | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Preconstruction planning
9.2.070 – Conduct Site Visit | Assesses site safety conditions; Identifies hazards and requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Preconstruction planning
9.2.070 – Conduct Site Visit | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 GS Directives | ✔ Covered | No change required. | Preconstruction planning
9.2.080 – Prepare Material Handling Plan | Oversees Prepare Material Handling Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning
9.2.090 – Develop Labor Budget | Provides financial support for Develop Labor Budget | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting
9.2.090 – Develop Labor Budget | Oversees Develop Labor Budget | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting
9.2.100 – Prepare Layout & Sequencing Plan | Oversees Prepare Layout & Sequencing Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning
9.2.110 – Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling
9.2.110 – Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling
9.2.120 – Establish Tracking & Control Systems | Oversees Establish Tracking & Control Systems | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning
9.2.130 – Construction Execution Kickoff Meeting | Leads coordination for Construction Execution Kickoff Meeting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning
9.2.140 – Develop Project Budget | Provides financial support for Develop Project Budget | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting
9.2.140 – Develop Project Budget | Oversees Develop Project Budget | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting
9.2.160 – Develop Procurement Plan | Manages procurement for Develop Procurement Plan | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning
9.2.160 – Develop Procurement Plan | Oversees Develop Procurement Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning
9.3.010 – Setup Office Trailer | Approves trailer location and configuration; Coordinates delivery timing ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Site mobilization
9.3.010 – Setup Office Trailer | Oversees physical setup; Coordinates with delivery vendor; Ensures utility connections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization
9.3.010 – Setup Office Trailer | Sets up office equipment and supplies; Establishes filing systems ¦ | ¦ Site Administrator | Sec. 9.8 Site Administration | ✔ Covered | No change required. | Site mobilization
9.3.010 – Setup Office Trailer | Reviews placement for safety compliance; Ensures egress requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Site mobilization
9.3.010 – Setup Office Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 GS Directives | ✔ Covered | No change required. | Site mobilization
9.3.020 – Setup Storage Trailer | Oversees setup and organization; Establishes security protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization
9.3.020 – Setup Storage Trailer | Coordinates physical placement; Organizes interior layout ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization
9.3.020 – Setup Storage Trailer | Coordinates material delivery timing with storage availability ¦ | ¦ Purchasing | Sec. 9.10 Purchasing Directives | ✔ Covered | No change required. | Site mobilization
9.3.020 – Setup Storage Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Site mobilization
9.3.030 – Setup Site Fencing and Access Control | Oversees fencing installation; Establishes access protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization
9.3.030 – Setup Site Fencing and Access Control | Coordinates installation; Manages gate operations ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization
9.3.030 – Setup Site Fencing and Access Control | Defines safety requirements; Reviews emergency egress ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Site mobilization
9.3.030 – Setup Site Fencing and Access Control | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Site mobilization
9.3.040 – Setup Temporary Power | Oversees installation; Ensures code compliance ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization
9.3.040 – Setup Temporary Power | Installs temporary power system; Makes connections ¦ | ¦ Foreman/Journeyman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization
9.3.040 – Setup Temporary Power | Reviews safety requirements; Verifies GFCI protection ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Site mobilization
9.3.040 – Setup Temporary Power | Coordinates with utility company; Approves power plan ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Site mobilization
9.3.040 – Setup Temporary Power | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Electrical Subcontractor | Contract Requirements | ✔ Covered | No change required. | Site mobilization
9.3.050 – Setup Temporary Water | Coordinates site setup for Setup Temporary Water | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.050 – Setup Temporary Water | Oversees Setup Temporary Water | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.060 – Setup Sanitary Facilities | Coordinates site setup for Setup Sanitary Facilities | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.060 – Setup Sanitary Facilities | Oversees Setup Sanitary Facilities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.070 – Setup Temporary Lighting | Coordinates site setup for Setup Temporary Lighting | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.070 – Setup Temporary Lighting | Oversees Setup Temporary Lighting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.080 – Setup Signage | Coordinates site setup for Setup Signage | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.080 – Setup Signage | Oversees Setup Signage | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.090 – Setup Security | Coordinates site setup for Setup Security | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.090 – Setup Security | Oversees Setup Security | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.100 – Setup Laydown Area | Coordinates site setup for Setup Laydown Area | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.100 – Setup Laydown Area | Oversees Setup Laydown Area | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.110 – Setup Equipment Staging | Coordinates site setup for Setup Equipment Staging | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.110 – Setup Equipment Staging | Oversees Setup Equipment Staging | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.120 – Setup Parking | Coordinates site setup for Setup Parking | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.120 – Setup Parking | Oversees Setup Parking | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization
9.3.470 – Develop Site-Specific Safety Plan | Reviews for safety compliance for Develop Site-Specific Safety Plan | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety setup
9.3.470 – Develop Site-Specific Safety Plan | Oversees Develop Site-Specific Safety Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety setup
9.3.470 – Develop Site-Specific Safety Plan | Field coordination for Develop Site-Specific Safety Plan | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety setup
9.4.010 – Conduct Coordination Meetings | Leads coordination for Conduct Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.010 – Conduct Coordination Meetings | Field coordination for Conduct Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.020 – Conduct Subcontractor Coordination Meetings | Performs subcontracted work for Conduct Subcontractor Coordination Meetings | Subcontractors | Contract Requirements | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.020 – Conduct Subcontractor Coordination Meetings | Leads coordination for Conduct Subcontractor Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.020 – Conduct Subcontractor Coordination Meetings | Field coordination for Conduct Subcontractor Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.030 – Conduct Client/Owner Meetings | Participates in client communications for Conduct Client/Owner Meetings | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.030 – Conduct Client/Owner Meetings | Oversees Conduct Client/Owner Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.030 – Conduct Client/Owner Meetings | Field coordination for Conduct Client/Owner Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.040 – Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.040 – Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.040 – Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Coordinates prefabrication for Identify Value Engineering & Prefabrication Opportunities | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Oversees Identify Value Engineering & Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Field coordination for Identify Value Engineering & Prefabrication Opportunities | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.050 – Conduct Prefabrication Coordination Meetings | Coordinates prefabrication for Conduct Prefabrication Coordination Meetings | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.050 – Conduct Prefabrication Coordination Meetings | Leads coordination for Conduct Prefabrication Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.050 – Conduct Prefabrication Coordination Meetings | Field coordination for Conduct Prefabrication Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.055 – Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.055 – Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.055 – Procurement of Large Feeder Wire | Field coordination for Procurement of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.060 – Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.060 – Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.060 – Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.190 – Document Filing Standards | Manages documentation for Document Filing Standards | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.190 – Document Filing Standards | Oversees Document Filing Standards | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.190 – Document Filing Standards | Field coordination for Document Filing Standards | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.195 – Manage Project Documentation System | Manages documentation for Manage Project Documentation System | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.195 – Manage Project Documentation System | Oversees Manage Project Documentation System | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.195 – Manage Project Documentation System | Field coordination for Manage Project Documentation System | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.200 – Manage Submittals | Manages technical documentation for Manage Submittals | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.200 – Manage Submittals | Field coordination for Manage Submittals | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.205 – Manage RFIs (Requests for Information) | Manages technical documentation for Manage RFIs (Requests for Information) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.205 – Manage RFIs (Requests for Information) | Field coordination for Manage RFIs (Requests for Information) | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management
9.4.210 – Manage Meeting Minutes | Manages documentation for Manage Meeting Minutes | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.210 – Manage Meeting Minutes | Oversees Manage Meeting Minutes | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.210 – Manage Meeting Minutes | Field coordination for Manage Meeting Minutes | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.215 – Manage Daily Reports | Manages field operations for Manage Daily Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.215 – Manage Daily Reports | Oversees Manage Daily Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.220 – Manage Drawing Logs | Manages technical documentation for Manage Drawing Logs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.220 – Manage Drawing Logs | Field coordination for Manage Drawing Logs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.225 – Manage Specifications | Manages technical documentation for Manage Specifications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.225 – Manage Specifications | Field coordination for Manage Specifications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.230 – Manage Correspondence | Manages documentation for Manage Correspondence | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.230 – Manage Correspondence | Oversees Manage Correspondence | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.230 – Manage Correspondence | Field coordination for Manage Correspondence | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.235 – Manage Permits | Oversees Manage Permits | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.235 – Manage Permits | Field coordination for Manage Permits | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.240 – Manage Inspection Reports | Oversees Manage Inspection Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.240 – Manage Inspection Reports | Field coordination for Manage Inspection Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.270 – Manage Project Communications | Manages communications for Manage Project Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.270 – Manage Project Communications | Field coordination for Manage Project Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.275 – Manage Internal Communications | Manages communications for Manage Internal Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.275 – Manage Internal Communications | Field coordination for Manage Internal Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.280 – Manage External Communications | Manages communications for Manage External Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.280 – Manage External Communications | Field coordination for Manage External Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.285 – Manage Client/Owner Communications | Participates in client communications for Manage Client/Owner Communications | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.285 – Manage Client/Owner Communications | Manages communications for Manage Client/Owner Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.285 – Manage Client/Owner Communications | Field coordination for Manage Client/Owner Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.290 – Manage Subcontractor Communications | Performs subcontracted work for Manage Subcontractor Communications | Subcontractors | Contract Requirements | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.290 – Manage Subcontractor Communications | Manages communications for Manage Subcontractor Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.290 – Manage Subcontractor Communications | Field coordination for Manage Subcontractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.295 – Manage Vendor Supplier Communications | Manages procurement for Manage Vendor Supplier Communications | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.295 – Manage Vendor Supplier Communications | Manages communications for Manage Vendor Supplier Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.295 – Manage Vendor Supplier Communications | Field coordination for Manage Vendor Supplier Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.300 – Manage Architect/Engineer Communications | Manages communications for Manage Architect/Engineer Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.300 – Manage Architect/Engineer Communications | Field coordination for Manage Architect/Engineer Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.305 – Manage Regulatory/Authority Communications | Manages communications for Manage Regulatory/Authority Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.305 – Manage Regulatory/Authority Communications | Field coordination for Manage Regulatory/Authority Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.310 – Manage General Contractor Communications | Manages communications for Manage General Contractor Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.310 – Manage General Contractor Communications | Field coordination for Manage General Contractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications
9.4.315 – Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.315 – Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.315 – Develop Project Schedule | Field coordination for Develop Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.320 – Update Project Schedule | Coordinates scheduling for Update Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.320 – Update Project Schedule | Oversees Update Project Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.320 – Update Project Schedule | Field coordination for Update Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.325 – Monitor Schedule Performance | Coordinates scheduling for Monitor Schedule Performance | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.325 – Monitor Schedule Performance | Oversees Monitor Schedule Performance | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.325 – Monitor Schedule Performance | Field coordination for Monitor Schedule Performance | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.330 – Develop Schedule Recovery Plans | Coordinates scheduling for Develop Schedule Recovery Plans | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.330 – Develop Schedule Recovery Plans | Oversees Develop Schedule Recovery Plans | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.330 – Develop Schedule Recovery Plans | Field coordination for Develop Schedule Recovery Plans | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.335 – Prepare Lookahead Schedules | Coordinates scheduling for Prepare Lookahead Schedules | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.335 – Prepare Lookahead Schedules | Oversees Prepare Lookahead Schedules | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.335 – Prepare Lookahead Schedules | Field coordination for Prepare Lookahead Schedules | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.340 – Manage Resource-Loaded Schedules | Coordinates scheduling for Manage Resource-Loaded Schedules | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.340 – Manage Resource-Loaded Schedules | Oversees Manage Resource-Loaded Schedules | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.340 – Manage Resource-Loaded Schedules | Field coordination for Manage Resource-Loaded Schedules | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.345 – Conduct Schedule Review Meetings | Coordinates scheduling for Conduct Schedule Review Meetings | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.345 – Conduct Schedule Review Meetings | Oversees Conduct Schedule Review Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.345 – Conduct Schedule Review Meetings | Field coordination for Conduct Schedule Review Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.350 – Manage Schedule Change Requests | Coordinates scheduling for Manage Schedule Change Requests | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.350 – Manage Schedule Change Requests | Oversees Manage Schedule Change Requests | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.350 – Manage Schedule Change Requests | Field coordination for Manage Schedule Change Requests | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.355 – Manage Project Scope | Manages contract changes for Manage Project Scope | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management
9.4.355 – Manage Project Scope | Field coordination for Manage Project Scope | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management
9.4.360 – Manage Change Orders | Manages contract changes for Manage Change Orders | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management
9.4.360 – Manage Change Orders | Field coordination for Manage Change Orders | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management
9.4.365 – Manage Potential Change Orders (PCOs) | Manages contract changes for Manage Potential Change Orders (PCOs) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management
9.4.365 – Manage Potential Change Orders (PCOs) | Field coordination for Manage Potential Change Orders (PCOs) | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management
9.4.370 – Manage Owner Directives | Participates in client communications for Manage Owner Directives | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.370 – Manage Owner Directives | Oversees Manage Owner Directives | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.370 – Manage Owner Directives | Field coordination for Manage Owner Directives | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.375 – Manage Scope Clarifications | Manages contract changes for Manage Scope Clarifications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management
9.4.375 – Manage Scope Clarifications | Field coordination for Manage Scope Clarifications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management
9.4.380 – Manage Backcharges | Manages contract changes for Manage Backcharges | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.380 – Manage Backcharges | Field coordination for Manage Backcharges | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.385 – Manage Force Account Work | Manages contract changes for Manage Force Account Work | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.385 – Manage Force Account Work | Field coordination for Manage Force Account Work | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.390 – Manage Claims | Provides executive approval for Manage Claims | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.390 – Manage Claims | Oversees Manage Claims | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.390 – Manage Claims | Field coordination for Manage Claims | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.400 – Monitor Project Costs | Provides financial support for Monitor Project Costs | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.400 – Monitor Project Costs | Oversees Monitor Project Costs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.400 – Monitor Project Costs | Field coordination for Monitor Project Costs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.405 – Manage Cost Forecasts | Provides financial support for Manage Cost Forecasts | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.405 – Manage Cost Forecasts | Oversees Manage Cost Forecasts | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.405 – Manage Cost Forecasts | Field coordination for Manage Cost Forecasts | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.410 – Manage Cost Codes | Manages financial documentation for Manage Cost Codes | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.410 – Manage Cost Codes | Oversees Manage Cost Codes | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.410 – Manage Cost Codes | Field coordination for Manage Cost Codes | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.415 – Manage Committed Costs | Provides financial support for Manage Committed Costs | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.415 – Manage Committed Costs | Oversees Manage Committed Costs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.415 – Manage Committed Costs | Field coordination for Manage Committed Costs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.420 – Manage Actual Costs | Provides financial support for Manage Actual Costs | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.420 – Manage Actual Costs | Oversees Manage Actual Costs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.420 – Manage Actual Costs | Field coordination for Manage Actual Costs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.425 – Manage Job Cost Reports | Manages financial documentation for Manage Job Cost Reports | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.425 – Manage Job Cost Reports | Oversees Manage Job Cost Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.425 – Manage Job Cost Reports | Field coordination for Manage Job Cost Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.430 – Manage Profit Projections | Provides financial support for Manage Profit Projections | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.430 – Manage Profit Projections | Oversees Manage Profit Projections | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.430 – Manage Profit Projections | Field coordination for Manage Profit Projections | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.435 – Manage Cost-to-Complete | Provides financial support for Manage Cost-to-Complete | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.435 – Manage Cost-to-Complete | Oversees Manage Cost-to-Complete | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.435 – Manage Cost-to-Complete | Field coordination for Manage Cost-to-Complete | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management
9.4.440 – Prepare Billing Schedule | Manages financial documentation for Prepare Billing Schedule | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.440 – Prepare Billing Schedule | Coordinates scheduling for Prepare Billing Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.440 – Prepare Billing Schedule | Oversees Prepare Billing Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.440 – Prepare Billing Schedule | Field coordination for Prepare Billing Schedule | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management
9.4.445 – Prepare Monthly Pay Applications | Manages financial documentation for Prepare Monthly Pay Applications | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.445 – Prepare Monthly Pay Applications | Oversees Prepare Monthly Pay Applications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.445 – Prepare Monthly Pay Applications | Field coordination for Prepare Monthly Pay Applications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.450 – Track Accounts Receivable | Manages financial documentation for Track Accounts Receivable | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.450 – Track Accounts Receivable | Oversees Track Accounts Receivable | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.450 – Track Accounts Receivable | Field coordination for Track Accounts Receivable | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.455 – Manage Lien Waivers | Oversees Manage Lien Waivers | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.455 – Manage Lien Waivers | Field coordination for Manage Lien Waivers | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.460 – Manage Retainage | Manages financial documentation for Manage Retainage | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.460 – Manage Retainage | Oversees Manage Retainage | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.460 – Manage Retainage | Field coordination for Manage Retainage | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.465 – Manage Final Invoicing | Oversees Manage Final Invoicing | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.465 – Manage Final Invoicing | Field coordination for Manage Final Invoicing | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.475 – Conduct Safety Orientation | Leads safety activities for Conduct Safety Orientation | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.475 – Conduct Safety Orientation | Oversees Conduct Safety Orientation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.475 – Conduct Safety Orientation | Field coordination for Conduct Safety Orientation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.480 – Conduct Safety Inspections | Leads safety activities for Conduct Safety Inspections | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.480 – Conduct Safety Inspections | Oversees Conduct Safety Inspections | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.480 – Conduct Safety Inspections | Field coordination for Conduct Safety Inspections | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.485 – Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.485 – Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.485 – Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.490 – Report Safety Incidents | Leads safety activities for Report Safety Incidents | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.490 – Report Safety Incidents | Oversees Report Safety Incidents | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.490 – Report Safety Incidents | Field coordination for Report Safety Incidents | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.495 – Investigate Accidents | Leads safety activities for Investigate Accidents | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.495 – Investigate Accidents | Oversees Investigate Accidents | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.495 – Investigate Accidents | Field coordination for Investigate Accidents | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.500 – Conduct Emergency Preparedness | Leads safety activities for Conduct Emergency Preparedness | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.500 – Conduct Emergency Preparedness | Oversees Conduct Emergency Preparedness | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.500 – Conduct Emergency Preparedness | Field coordination for Conduct Emergency Preparedness | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.505 – Conduct Safety Compliance Audits | Reviews for safety compliance for Conduct Safety Compliance Audits | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.505 – Conduct Safety Compliance Audits | Oversees Conduct Safety Compliance Audits | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.505 – Conduct Safety Compliance Audits | Field coordination for Conduct Safety Compliance Audits | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.510 – Provide Safety Training | Reviews for safety compliance for Provide Safety Training | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.510 – Provide Safety Training | Oversees Provide Safety Training | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.510 – Provide Safety Training | Field coordination for Provide Safety Training | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management
9.4.515 – Develop Quality Management Plan | Performs quality activities for Develop Quality Management Plan | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.515 – Develop Quality Management Plan | Oversees Develop Quality Management Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.515 – Develop Quality Management Plan | Field coordination for Develop Quality Management Plan | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.520 – Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.520 – Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.520 – Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.525 – Conduct Quality Inspections | Performs quality activities for Conduct Quality Inspections | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.525 – Conduct Quality Inspections | Oversees Conduct Quality Inspections | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.525 – Conduct Quality Inspections | Field coordination for Conduct Quality Inspections | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.530 – Manage Quality Testing | Provides quality oversight for Manage Quality Testing | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.530 – Manage Quality Testing | Oversees Manage Quality Testing | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.530 – Manage Quality Testing | Field coordination for Manage Quality Testing | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.535 – Manage Nonconformance Reports (NCRs) | Performs quality activities for Manage Nonconformance Reports (NCRs) | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.535 – Manage Nonconformance Reports (NCRs) | Oversees Manage Nonconformance Reports (NCRs) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.535 – Manage Nonconformance Reports (NCRs) | Field coordination for Manage Nonconformance Reports (NCRs) | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.540 – Manage Quality Records | Provides quality oversight for Manage Quality Records | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.540 – Manage Quality Records | Oversees Manage Quality Records | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.540 – Manage Quality Records | Field coordination for Manage Quality Records | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.545 – Manage Punch List Quality | Provides quality oversight for Manage Punch List Quality | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.545 – Manage Punch List Quality | Oversees Manage Punch List Quality | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.545 – Manage Punch List Quality | Field coordination for Manage Punch List Quality | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.560 – Manage Manpower Allocation | Manages field operations for Manage Manpower Allocation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.560 – Manage Manpower Allocation | Oversees Manage Manpower Allocation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.565 – Manage Equipment Allocation | Oversees Manage Equipment Allocation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.565 – Manage Equipment Allocation | Field coordination for Manage Equipment Allocation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.570 – Manage Material Allocation | Oversees Manage Material Allocation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.570 – Manage Material Allocation | Field coordination for Manage Material Allocation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.576 – Manage Subcontractor Resources | Performs subcontracted work for Manage Subcontractor Resources | Subcontractors | Contract Requirements | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.576 – Manage Subcontractor Resources | Oversees Manage Subcontractor Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.576 – Manage Subcontractor Resources | Field coordination for Manage Subcontractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.580 – Manage Vendor Resources | Manages procurement for Manage Vendor Resources | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.580 – Manage Vendor Resources | Oversees Manage Vendor Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.580 – Manage Vendor Resources | Field coordination for Manage Vendor Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.585 – Plan Prefabrication Resources | Coordinates prefabrication for Plan Prefabrication Resources | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.585 – Plan Prefabrication Resources | Oversees Plan Prefabrication Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.585 – Plan Prefabrication Resources | Field coordination for Plan Prefabrication Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.590 – Manage Specialty Contractor Resources | Oversees Manage Specialty Contractor Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.590 – Manage Specialty Contractor Resources | Field coordination for Manage Specialty Contractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.595 – Prepare Resource Reports | Oversees Prepare Resource Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.595 – Prepare Resource Reports | Field coordination for Prepare Resource Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.605 – Issue Purchase Orders | Manages procurement for Issue Purchase Orders | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.605 – Issue Purchase Orders | Oversees Issue Purchase Orders | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.605 – Issue Purchase Orders | Field coordination for Issue Purchase Orders | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.610 – Manage Vendor Prequalification | Manages procurement for Manage Vendor Prequalification | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.610 – Manage Vendor Prequalification | Oversees Manage Vendor Prequalification | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.610 – Manage Vendor Prequalification | Field coordination for Manage Vendor Prequalification | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.615 – Manage Vendor Evaluations | Manages procurement for Manage Vendor Evaluations | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.615 – Manage Vendor Evaluations | Oversees Manage Vendor Evaluations | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.615 – Manage Vendor Evaluations | Field coordination for Manage Vendor Evaluations | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.620 – Manage Expediting | Manages procurement for Manage Expediting | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.620 – Manage Expediting | Oversees Manage Expediting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.620 – Manage Expediting | Field coordination for Manage Expediting | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.625 – Manage Delivery Tracking | Manages procurement for Manage Delivery Tracking | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.625 – Manage Delivery Tracking | Oversees Manage Delivery Tracking | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.625 – Manage Delivery Tracking | Field coordination for Manage Delivery Tracking | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.630 – Manage Material Receiving | Manages procurement for Manage Material Receiving | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.630 – Manage Material Receiving | Oversees Manage Material Receiving | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.630 – Manage Material Receiving | Field coordination for Manage Material Receiving | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.631 – Release of Large Feeder Wire | Oversees Release of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.631 – Release of Large Feeder Wire | Field coordination for Release of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.635 – Manage Material Inspection | Oversees Manage Material Inspection | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.635 – Manage Material Inspection | Field coordination for Manage Material Inspection | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.640 – Manage Storage and Logistics | Oversees Manage Storage and Logistics | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.640 – Manage Storage and Logistics | Field coordination for Manage Storage and Logistics | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.645 – Manage Material Handling | Oversees Manage Material Handling | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.645 – Manage Material Handling | Field coordination for Manage Material Handling | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.650 – Manage Inventory | Manages procurement for Manage Inventory | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.650 – Manage Inventory | Oversees Manage Inventory | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.650 – Manage Inventory | Field coordination for Manage Inventory | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.655 – Prepare Procurement Reports | Manages procurement for Prepare Procurement Reports | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.655 – Prepare Procurement Reports | Oversees Prepare Procurement Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.655 – Prepare Procurement Reports | Field coordination for Prepare Procurement Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.660 – Manage Procurement Closeout | Manages procurement for Manage Procurement Closeout | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.660 – Manage Procurement Closeout | Oversees closeout for Manage Procurement Closeout | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.660 – Manage Procurement Closeout | Field coordination for Manage Procurement Closeout | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.665 – Reconcile Procurement Accounts | Manages procurement for Reconcile Procurement Accounts | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.665 – Reconcile Procurement Accounts | Manages financial documentation for Reconcile Procurement Accounts | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.665 – Reconcile Procurement Accounts | Oversees Reconcile Procurement Accounts | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.665 – Reconcile Procurement Accounts | Field coordination for Reconcile Procurement Accounts | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.670 – Manage Vendor Closeout | Manages procurement for Manage Vendor Closeout | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.670 – Manage Vendor Closeout | Oversees closeout for Manage Vendor Closeout | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.670 – Manage Vendor Closeout | Field coordination for Manage Vendor Closeout | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution
9.4.675 – Conduct Daily Huddles | Leads crew activities for Conduct Daily Huddles | Foreman | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.675 – Conduct Daily Huddles | Oversees Conduct Daily Huddles | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.675 – Conduct Daily Huddles | Field coordination for Conduct Daily Huddles | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.680 – Conduct Weekly Foreman Meetings | Leads crew activities for Conduct Weekly Foreman Meetings | Foreman | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.680 – Conduct Weekly Foreman Meetings | Oversees Conduct Weekly Foreman Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.680 – Conduct Weekly Foreman Meetings | Field coordination for Conduct Weekly Foreman Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.690 – Track Manpower Utilization | Manages field operations for Track Manpower Utilization | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.690 – Track Manpower Utilization | Oversees Track Manpower Utilization | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management
9.4.695 – Track Production Quantities | Manages field operations for Track Production Quantities | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations
9.4.695 – Track Production Quantities | Oversees Track Production Quantities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations
9.4.700 – Track Equipment Utilization | Oversees Track Equipment Utilization | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.700 – Track Equipment Utilization | Field coordination for Track Equipment Utilization | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.705 – Manage Work Packaging | Oversees Manage Work Packaging | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.705 – Manage Work Packaging | Field coordination for Manage Work Packaging | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.710 – Manage Workface Planning | Oversees Manage Workface Planning | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.710 – Manage Workface Planning | Field coordination for Manage Workface Planning | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.715 – Manage Field Coordination | Manages field operations for Manage Field Coordination | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.715 – Manage Field Coordination | Oversees Manage Field Coordination | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination
9.4.720 – Conduct Productivity Analysis | Oversees Conduct Productivity Analysis | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.720 – Conduct Productivity Analysis | Field coordination for Conduct Productivity Analysis | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution
9.4.725 – Resolve Field Problems | Manages field operations for Resolve Field Problems | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations
9.4.725 – Resolve Field Problems | Oversees Resolve Field Problems | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations
9.4.735 – Perform Field Quality Verifications | Provides quality oversight for Perform Field Quality Verifications | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.735 – Perform Field Quality Verifications | Oversees Perform Field Quality Verifications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.735 – Perform Field Quality Verifications | Field coordination for Perform Field Quality Verifications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management
9.4.745 – Manage Field Rework | Manages field operations for Manage Field Rework | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations
9.4.745 – Manage Field Rework | Oversees Manage Field Rework | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations
9.4.755 – Implement Field Productivity Improvements | Oversees Implement Field Productivity Improvements | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations
9.4.755 – Implement Field Productivity Improvements | Field coordination for Implement Field Productivity Improvements | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations
9.5.020 – Handling and/or Disposing of Excess Materials | Leads meeting coordination; Tracks commissioning progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Commissioning
9.5.020 – Handling and/or Disposing of Excess Materials | Conducts testing; Documents results; Identifies deficiencies ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | ✔ Covered | No change required. | Commissioning
9.5.020 – Handling and/or Disposing of Excess Materials | Supports testing activities; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Commissioning
9.5.020 – Handling and/or Disposing of Excess Materials | Verifies quality requirements; Reviews test results ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | ✔ Covered | No change required. | Commissioning
9.5.020 – Handling and/or Disposing of Excess Materials | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Contract Requirements | ✔ Covered | No change required. | Commissioning
9.5.550 – Manage Commissioning Activities | Overall commissioning management; Schedule coordination ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Commissioning
9.5.550 – Manage Commissioning Activities | Supports testing; Ensures systems ready; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Commissioning
9.5.550 – Manage Commissioning Activities | Executes testing protocols; Documents results ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | ✔ Covered | No change required. | Commissioning
9.5.550 – Manage Commissioning Activities | Verifies compliance; Reviews documentation ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | ✔ Covered | No change required. | Commissioning
9.5.550 – Manage Commissioning Activities | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Contract Requirements | ✔ Covered | No change required. | Commissioning
9.6.005 – Prepare for Turnover (Field Perspective) | Oversees closeout for Prepare for Turnover (Field Perspective) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.010 – Conduct Closeout Meetings | Leads closeout meetings; Tracks closeout progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout
9.6.010 – Conduct Closeout Meetings | Reports field status; Coordinates punch completion ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout
9.6.010 – Conduct Closeout Meetings | Participate; Complete their closeout requirements ¦ | ¦ Subcontractors | Contract Requirements | ✔ Covered | No change required. | Project closeout
9.6.010 – Conduct Closeout Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Client/Owner | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout
9.6.015 – Manage Project Turnover Documentation | Oversees closeout for Manage Project Turnover Documentation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.020 – Manage Punch List Closeout | Provides quality oversight for Manage Punch List Closeout | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.020 – Manage Punch List Closeout | Oversees closeout for Manage Punch List Closeout | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.030 – Manage As-Built Drawings | Manages as-built process; Submits final drawings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout
9.6.030 – Manage As-Built Drawings | Reviews markups for accuracy; Coordinates with field ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout
9.6.030 – Manage As-Built Drawings | Creates field markups; Documents actual conditions ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout
9.6.030 – Manage As-Built Drawings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Engineer/APM | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout
9.6.035 – Submit Warranties | Oversees Submit Warranties | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.040 – Submit O&M Manuals | Oversees closeout for Submit O&M Manuals | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.050 – Provide Owner Training | Participates in client communications for Provide Owner Training | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.050 – Provide Owner Training | Oversees Provide Owner Training | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.065 – Archive Project Documentation | Manages documentation for Archive Project Documentation | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.065 – Archive Project Documentation | Oversees Archive Project Documentation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout
9.6.070 – Conduct Post-Project Review | Oversees review process; Approves action items ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | ✔ Covered | No change required. | Project closeout
9.6.070 – Conduct Post-Project Review | Leads review meeting; Compiles findings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout
9.6.070 – Conduct Post-Project Review | Provides field perspective; Shares observations ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout
9.6.070 – Conduct Post-Project Review | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Operations Manager | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout
9.6.080 – Capture Client Feedback | Oversees feedback process; Reviews results ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | ✔ Covered | No change required. | Project closeout
9.6.080 – Capture Client Feedback | Conducts feedback meeting; Documents responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout
9.6.080 – Capture Client Feedback | Uses feedback for relationship management ¦ | ¦ Business Development | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout
9.6.080 – Capture Client Feedback | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Executive Committee | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout
9.6.085 – Document Lessons Learned | Maintains lessons learned database; Ensures implementation ¦ | ¦ Operations Manager | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout
9.6.085 – Document Lessons Learned | Documents project-specific lessons; Submits for review ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout
9.6.085 – Document Lessons Learned | Captures field-level learnings; Contributes to documentation ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout
9.6.085 – Document Lessons Learned | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Branch Manager | Sec. 9.6 Branch Management | ✔ Covered | No change required. | Project closeout

## RACI Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | RACI
9.1.050 – Prepare Construction Takeoff | Oversees Prepare Construction Takeoff | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | General | R
9.2.005 – Review Contract for High Risk Clauses | Oversees Review Contract for High Risk Clauses | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope and contract review | A
9.2.010 – Team Selection | Selects Project Manager and assigns or approves final team assignments; Allocates resources across projects; Resolves resource conflicts. | Branch Manager | Sec. 9.6 Branch Management | ✔ Covered | No change required. | Team selection and turnover | A
9.2.010 – Team Selection | Identifies required roles and skill sets; Recommends team members; Coordinates with Branch Manager on availability. | Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Team selection and turnover | R
9.2.010 – Team Selection | Validates field leadership assignments; Confirms crew availability and capability | General Superintendent | Sec. 9.4 GS Directives | ✔ Covered | No change required. | Team selection and turnover | C
9.2.010 – Team Selection | Ensures safety-qualified personnel are assigned, Reviews site-specific safety requirements. | Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Team selection and turnover | C
9.2.010 – Team Selection | Informed of procurement resource needs | Purchasing | Sec. 9.10 Purchasing Directives | ✔ Covered | No change required. | Team selection and turnover | I
9.2.010 – Team Selection | Informed of prefab support requirements | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ✔ Covered | No change required. | Team selection and turnover | I
9.2.010 – Team Selection | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | Project Coordinator | Sec. 9.2 General Directives | ✔ Covered | No change required. | Team selection and turnover | I
9.2.015 – Project Turnover Meeting | Oversees closeout for Project Turnover Meeting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Team selection and turnover | A
9.2.020 – Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | R
9.2.020 – Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | A
9.2.030 – Review Contract for Unfavorable or High-Risk Clauses | Oversees Review Contract for Unfavorable or High-Risk Clauses | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope and contract review | A
9.2.040 – Project Manager Reviews Plans Specifications & Schedule | Coordinates scheduling for Project Manager Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | C
9.2.040 – Project Manager Reviews Plans Specifications & Schedule | Manages technical documentation for Project Manager Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | R
9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | Coordinates scheduling for Field Supervisor Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | C
9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | Manages technical documentation for Field Supervisor Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | R
9.2.055 – Compare Estimated vs Planned Performance | Provides estimating support for Compare Estimated vs Planned Performance | Estimator | Sec. 9.9 Estimating Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | C
9.2.055 – Compare Estimated vs Planned Performance | Oversees Compare Estimated vs Planned Performance | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | A
9.2.057 – Identify VE and Prefabrication Opportunities | Coordinates prefabrication for Identify VE and Prefabrication Opportunities | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | R
9.2.057 – Identify VE and Prefabrication Opportunities | Oversees Identify VE and Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | A
9.2.060 – Create Issue List and Begin RFI Process | Manages overall issue resolution; Prioritizes RFIs; Tracks responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Preconstruction planning | A
9.2.060 – Create Issue List and Begin RFI Process | Creates and submits RFIs; Maintains issue log; Follows up on responses ¦ | ¦ Assistant PM/Project Coordinator | Sec. 9.2 General Directives | ✔ Covered | No change required. | Preconstruction planning | R
9.2.060 – Create Issue List and Begin RFI Process | Contributes constructability issues; Reviews RFI responses for field impact ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Preconstruction planning | C
9.2.060 – Create Issue List and Begin RFI Process | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 GS Directives | ✔ Covered | No change required. | Preconstruction planning | C
9.2.070 – Conduct Site Visit | Coordinates site visit; Documents findings; Integrates into project planning ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Preconstruction planning | A
9.2.070 – Conduct Site Visit | Conducts physical site inspection; Identifies constructability and logistics issues ¦ | ¦ Field Leadership | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Preconstruction planning | R
9.2.070 – Conduct Site Visit | Assesses site safety conditions; Identifies hazards and requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Preconstruction planning | R
9.2.070 – Conduct Site Visit | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 GS Directives | ✔ Covered | No change required. | Preconstruction planning | C
9.2.080 – Prepare Material Handling Plan | Oversees Prepare Material Handling Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | A
9.2.090 – Develop Labor Budget | Provides financial support for Develop Labor Budget | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting | C
9.2.090 – Develop Labor Budget | Oversees Develop Labor Budget | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting | A
9.2.100 – Prepare Layout & Sequencing Plan | Oversees Prepare Layout & Sequencing Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | A
9.2.110 – Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | C
9.2.110 – Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | A
9.2.120 – Establish Tracking & Control Systems | Oversees Establish Tracking & Control Systems | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | A
9.2.130 – Construction Execution Kickoff Meeting | Leads coordination for Construction Execution Kickoff Meeting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | R
9.2.140 – Develop Project Budget | Provides financial support for Develop Project Budget | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting | C
9.2.140 – Develop Project Budget | Oversees Develop Project Budget | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting | A
9.2.160 – Develop Procurement Plan | Manages procurement for Develop Procurement Plan | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | R
9.2.160 – Develop Procurement Plan | Oversees Develop Procurement Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | A
9.3.010 – Setup Office Trailer | Approves trailer location and configuration; Coordinates delivery timing ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Site mobilization | A
9.3.010 – Setup Office Trailer | Oversees physical setup; Coordinates with delivery vendor; Ensures utility connections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization | R
9.3.010 – Setup Office Trailer | Sets up office equipment and supplies; Establishes filing systems ¦ | ¦ Site Administrator | Sec. 9.8 Site Administration | ✔ Covered | No change required. | Site mobilization | R
9.3.010 – Setup Office Trailer | Reviews placement for safety compliance; Ensures egress requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Site mobilization | C
9.3.010 – Setup Office Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 GS Directives | ✔ Covered | No change required. | Site mobilization | C
9.3.020 – Setup Storage Trailer | Oversees setup and organization; Establishes security protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization | A
9.3.020 – Setup Storage Trailer | Coordinates physical placement; Organizes interior layout ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization | R
9.3.020 – Setup Storage Trailer | Coordinates material delivery timing with storage availability ¦ | ¦ Purchasing | Sec. 9.10 Purchasing Directives | ✔ Covered | No change required. | Site mobilization | C
9.3.020 – Setup Storage Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Site mobilization | C
9.3.030 – Setup Site Fencing and Access Control | Oversees fencing installation; Establishes access protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization | A
9.3.030 – Setup Site Fencing and Access Control | Coordinates installation; Manages gate operations ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization | R
9.3.030 – Setup Site Fencing and Access Control | Defines safety requirements; Reviews emergency egress ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Site mobilization | R
9.3.030 – Setup Site Fencing and Access Control | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Site mobilization | C
9.3.040 – Setup Temporary Power | Oversees installation; Ensures code compliance ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization | A
9.3.040 – Setup Temporary Power | Installs temporary power system; Makes connections ¦ | ¦ Foreman/Journeyman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Site mobilization | R
9.3.040 – Setup Temporary Power | Reviews safety requirements; Verifies GFCI protection ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | ✔ Covered | No change required. | Site mobilization | C
9.3.040 – Setup Temporary Power | Coordinates with utility company; Approves power plan ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Site mobilization | C
9.3.040 – Setup Temporary Power | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Electrical Subcontractor | Contract Requirements | ✔ Covered | No change required. | Site mobilization | R
9.3.050 – Setup Temporary Water | Coordinates site setup for Setup Temporary Water | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.050 – Setup Temporary Water | Oversees Setup Temporary Water | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.060 – Setup Sanitary Facilities | Coordinates site setup for Setup Sanitary Facilities | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.060 – Setup Sanitary Facilities | Oversees Setup Sanitary Facilities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.070 – Setup Temporary Lighting | Coordinates site setup for Setup Temporary Lighting | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.070 – Setup Temporary Lighting | Oversees Setup Temporary Lighting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.080 – Setup Signage | Coordinates site setup for Setup Signage | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.080 – Setup Signage | Oversees Setup Signage | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.090 – Setup Security | Coordinates site setup for Setup Security | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.090 – Setup Security | Oversees Setup Security | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.100 – Setup Laydown Area | Coordinates site setup for Setup Laydown Area | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.100 – Setup Laydown Area | Oversees Setup Laydown Area | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.110 – Setup Equipment Staging | Coordinates site setup for Setup Equipment Staging | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.110 – Setup Equipment Staging | Oversees Setup Equipment Staging | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.120 – Setup Parking | Coordinates site setup for Setup Parking | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.120 – Setup Parking | Oversees Setup Parking | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | R
9.3.470 – Develop Site-Specific Safety Plan | Reviews for safety compliance for Develop Site-Specific Safety Plan | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety setup | C
9.3.470 – Develop Site-Specific Safety Plan | Oversees Develop Site-Specific Safety Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety setup | R
9.3.470 – Develop Site-Specific Safety Plan | Field coordination for Develop Site-Specific Safety Plan | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety setup | C
9.4.010 – Conduct Coordination Meetings | Leads coordination for Conduct Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | R
9.4.010 – Conduct Coordination Meetings | Field coordination for Conduct Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | C
9.4.020 – Conduct Subcontractor Coordination Meetings | Performs subcontracted work for Conduct Subcontractor Coordination Meetings | Subcontractors | Contract Requirements | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | R
9.4.020 – Conduct Subcontractor Coordination Meetings | Leads coordination for Conduct Subcontractor Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | R
9.4.020 – Conduct Subcontractor Coordination Meetings | Field coordination for Conduct Subcontractor Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | C
9.4.030 – Conduct Client/Owner Meetings | Participates in client communications for Conduct Client/Owner Meetings | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | C
9.4.030 – Conduct Client/Owner Meetings | Oversees Conduct Client/Owner Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | A
9.4.030 – Conduct Client/Owner Meetings | Field coordination for Conduct Client/Owner Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | C
9.4.040 – Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | R
9.4.040 – Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | A
9.4.040 – Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | C
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Coordinates prefabrication for Identify Value Engineering & Prefabrication Opportunities | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Oversees Identify Value Engineering & Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Field coordination for Identify Value Engineering & Prefabrication Opportunities | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.050 – Conduct Prefabrication Coordination Meetings | Coordinates prefabrication for Conduct Prefabrication Coordination Meetings | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | R
9.4.050 – Conduct Prefabrication Coordination Meetings | Leads coordination for Conduct Prefabrication Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | R
9.4.050 – Conduct Prefabrication Coordination Meetings | Field coordination for Conduct Prefabrication Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | C
9.4.055 – Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.055 – Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | A
9.4.055 – Procurement of Large Feeder Wire | Field coordination for Procurement of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | C
9.4.060 – Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | R
9.4.060 – Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | A
9.4.060 – Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.190 – Document Filing Standards | Manages documentation for Document Filing Standards | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | R
9.4.190 – Document Filing Standards | Oversees Document Filing Standards | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | A
9.4.190 – Document Filing Standards | Field coordination for Document Filing Standards | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | C
9.4.195 – Manage Project Documentation System | Manages documentation for Manage Project Documentation System | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | R
9.4.195 – Manage Project Documentation System | Oversees Manage Project Documentation System | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | A
9.4.195 – Manage Project Documentation System | Field coordination for Manage Project Documentation System | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | C
9.4.200 – Manage Submittals | Manages technical documentation for Manage Submittals | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | R
9.4.200 – Manage Submittals | Field coordination for Manage Submittals | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | C
9.4.205 – Manage RFIs (Requests for Information) | Manages technical documentation for Manage RFIs (Requests for Information) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | R
9.4.205 – Manage RFIs (Requests for Information) | Field coordination for Manage RFIs (Requests for Information) | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | C
9.4.210 – Manage Meeting Minutes | Manages documentation for Manage Meeting Minutes | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | R
9.4.210 – Manage Meeting Minutes | Oversees Manage Meeting Minutes | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | A
9.4.210 – Manage Meeting Minutes | Field coordination for Manage Meeting Minutes | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | C
9.4.215 – Manage Daily Reports | Manages field operations for Manage Daily Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.215 – Manage Daily Reports | Oversees Manage Daily Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.220 – Manage Drawing Logs | Manages technical documentation for Manage Drawing Logs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.220 – Manage Drawing Logs | Field coordination for Manage Drawing Logs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.225 – Manage Specifications | Manages technical documentation for Manage Specifications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.225 – Manage Specifications | Field coordination for Manage Specifications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.230 – Manage Correspondence | Manages documentation for Manage Correspondence | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.230 – Manage Correspondence | Oversees Manage Correspondence | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.230 – Manage Correspondence | Field coordination for Manage Correspondence | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.235 – Manage Permits | Oversees Manage Permits | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.235 – Manage Permits | Field coordination for Manage Permits | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.240 – Manage Inspection Reports | Oversees Manage Inspection Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.240 – Manage Inspection Reports | Field coordination for Manage Inspection Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.270 – Manage Project Communications | Manages communications for Manage Project Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.270 – Manage Project Communications | Field coordination for Manage Project Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.275 – Manage Internal Communications | Manages communications for Manage Internal Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.275 – Manage Internal Communications | Field coordination for Manage Internal Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.280 – Manage External Communications | Manages communications for Manage External Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.280 – Manage External Communications | Field coordination for Manage External Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.285 – Manage Client/Owner Communications | Participates in client communications for Manage Client/Owner Communications | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.285 – Manage Client/Owner Communications | Manages communications for Manage Client/Owner Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.285 – Manage Client/Owner Communications | Field coordination for Manage Client/Owner Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.290 – Manage Subcontractor Communications | Performs subcontracted work for Manage Subcontractor Communications | Subcontractors | Contract Requirements | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.290 – Manage Subcontractor Communications | Manages communications for Manage Subcontractor Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.290 – Manage Subcontractor Communications | Field coordination for Manage Subcontractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.295 – Manage Vendor Supplier Communications | Manages procurement for Manage Vendor Supplier Communications | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.295 – Manage Vendor Supplier Communications | Manages communications for Manage Vendor Supplier Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.295 – Manage Vendor Supplier Communications | Field coordination for Manage Vendor Supplier Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.300 – Manage Architect/Engineer Communications | Manages communications for Manage Architect/Engineer Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.300 – Manage Architect/Engineer Communications | Field coordination for Manage Architect/Engineer Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.305 – Manage Regulatory/Authority Communications | Manages communications for Manage Regulatory/Authority Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.305 – Manage Regulatory/Authority Communications | Field coordination for Manage Regulatory/Authority Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.310 – Manage General Contractor Communications | Manages communications for Manage General Contractor Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | R
9.4.310 – Manage General Contractor Communications | Field coordination for Manage General Contractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | C
9.4.315 – Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.315 – Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | A
9.4.315 – Develop Project Schedule | Field coordination for Develop Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.320 – Update Project Schedule | Coordinates scheduling for Update Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.320 – Update Project Schedule | Oversees Update Project Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | A
9.4.320 – Update Project Schedule | Field coordination for Update Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.325 – Monitor Schedule Performance | Coordinates scheduling for Monitor Schedule Performance | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.325 – Monitor Schedule Performance | Oversees Monitor Schedule Performance | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | A
9.4.325 – Monitor Schedule Performance | Field coordination for Monitor Schedule Performance | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.330 – Develop Schedule Recovery Plans | Coordinates scheduling for Develop Schedule Recovery Plans | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.330 – Develop Schedule Recovery Plans | Oversees Develop Schedule Recovery Plans | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | A
9.4.330 – Develop Schedule Recovery Plans | Field coordination for Develop Schedule Recovery Plans | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.335 – Prepare Lookahead Schedules | Coordinates scheduling for Prepare Lookahead Schedules | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.335 – Prepare Lookahead Schedules | Oversees Prepare Lookahead Schedules | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | A
9.4.335 – Prepare Lookahead Schedules | Field coordination for Prepare Lookahead Schedules | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.340 – Manage Resource-Loaded Schedules | Coordinates scheduling for Manage Resource-Loaded Schedules | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.340 – Manage Resource-Loaded Schedules | Oversees Manage Resource-Loaded Schedules | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | A
9.4.340 – Manage Resource-Loaded Schedules | Field coordination for Manage Resource-Loaded Schedules | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.345 – Conduct Schedule Review Meetings | Coordinates scheduling for Conduct Schedule Review Meetings | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.345 – Conduct Schedule Review Meetings | Oversees Conduct Schedule Review Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | A
9.4.345 – Conduct Schedule Review Meetings | Field coordination for Conduct Schedule Review Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.350 – Manage Schedule Change Requests | Coordinates scheduling for Manage Schedule Change Requests | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.350 – Manage Schedule Change Requests | Oversees Manage Schedule Change Requests | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | A
9.4.350 – Manage Schedule Change Requests | Field coordination for Manage Schedule Change Requests | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.355 – Manage Project Scope | Manages contract changes for Manage Project Scope | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | R
9.4.355 – Manage Project Scope | Field coordination for Manage Project Scope | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | C
9.4.360 – Manage Change Orders | Manages contract changes for Manage Change Orders | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | R
9.4.360 – Manage Change Orders | Field coordination for Manage Change Orders | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | C
9.4.365 – Manage Potential Change Orders (PCOs) | Manages contract changes for Manage Potential Change Orders (PCOs) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | R
9.4.365 – Manage Potential Change Orders (PCOs) | Field coordination for Manage Potential Change Orders (PCOs) | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | C
9.4.370 – Manage Owner Directives | Participates in client communications for Manage Owner Directives | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.370 – Manage Owner Directives | Oversees Manage Owner Directives | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.370 – Manage Owner Directives | Field coordination for Manage Owner Directives | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.375 – Manage Scope Clarifications | Manages contract changes for Manage Scope Clarifications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | R
9.4.375 – Manage Scope Clarifications | Field coordination for Manage Scope Clarifications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | C
9.4.380 – Manage Backcharges | Manages contract changes for Manage Backcharges | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.380 – Manage Backcharges | Field coordination for Manage Backcharges | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.385 – Manage Force Account Work | Manages contract changes for Manage Force Account Work | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.385 – Manage Force Account Work | Field coordination for Manage Force Account Work | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.390 – Manage Claims | Provides executive approval for Manage Claims | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.390 – Manage Claims | Oversees Manage Claims | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.390 – Manage Claims | Field coordination for Manage Claims | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.400 – Monitor Project Costs | Provides financial support for Monitor Project Costs | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.400 – Monitor Project Costs | Oversees Monitor Project Costs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | A
9.4.400 – Monitor Project Costs | Field coordination for Monitor Project Costs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.405 – Manage Cost Forecasts | Provides financial support for Manage Cost Forecasts | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.405 – Manage Cost Forecasts | Oversees Manage Cost Forecasts | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | A
9.4.405 – Manage Cost Forecasts | Field coordination for Manage Cost Forecasts | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.410 – Manage Cost Codes | Manages financial documentation for Manage Cost Codes | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | R
9.4.410 – Manage Cost Codes | Oversees Manage Cost Codes | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | A
9.4.410 – Manage Cost Codes | Field coordination for Manage Cost Codes | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.415 – Manage Committed Costs | Provides financial support for Manage Committed Costs | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.415 – Manage Committed Costs | Oversees Manage Committed Costs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | A
9.4.415 – Manage Committed Costs | Field coordination for Manage Committed Costs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.420 – Manage Actual Costs | Provides financial support for Manage Actual Costs | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.420 – Manage Actual Costs | Oversees Manage Actual Costs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | A
9.4.420 – Manage Actual Costs | Field coordination for Manage Actual Costs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.425 – Manage Job Cost Reports | Manages financial documentation for Manage Job Cost Reports | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | R
9.4.425 – Manage Job Cost Reports | Oversees Manage Job Cost Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | A
9.4.425 – Manage Job Cost Reports | Field coordination for Manage Job Cost Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.430 – Manage Profit Projections | Provides financial support for Manage Profit Projections | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.430 – Manage Profit Projections | Oversees Manage Profit Projections | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.430 – Manage Profit Projections | Field coordination for Manage Profit Projections | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.435 – Manage Cost-to-Complete | Provides financial support for Manage Cost-to-Complete | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.435 – Manage Cost-to-Complete | Oversees Manage Cost-to-Complete | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | A
9.4.435 – Manage Cost-to-Complete | Field coordination for Manage Cost-to-Complete | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | C
9.4.440 – Prepare Billing Schedule | Manages financial documentation for Prepare Billing Schedule | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | R
9.4.440 – Prepare Billing Schedule | Coordinates scheduling for Prepare Billing Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.440 – Prepare Billing Schedule | Oversees Prepare Billing Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | A
9.4.440 – Prepare Billing Schedule | Field coordination for Prepare Billing Schedule | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | C
9.4.445 – Prepare Monthly Pay Applications | Manages financial documentation for Prepare Monthly Pay Applications | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.445 – Prepare Monthly Pay Applications | Oversees Prepare Monthly Pay Applications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.445 – Prepare Monthly Pay Applications | Field coordination for Prepare Monthly Pay Applications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.450 – Track Accounts Receivable | Manages financial documentation for Track Accounts Receivable | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.450 – Track Accounts Receivable | Oversees Track Accounts Receivable | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.450 – Track Accounts Receivable | Field coordination for Track Accounts Receivable | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.455 – Manage Lien Waivers | Oversees Manage Lien Waivers | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.455 – Manage Lien Waivers | Field coordination for Manage Lien Waivers | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.460 – Manage Retainage | Manages financial documentation for Manage Retainage | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.460 – Manage Retainage | Oversees Manage Retainage | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.460 – Manage Retainage | Field coordination for Manage Retainage | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.465 – Manage Final Invoicing | Oversees Manage Final Invoicing | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.465 – Manage Final Invoicing | Field coordination for Manage Final Invoicing | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.475 – Conduct Safety Orientation | Leads safety activities for Conduct Safety Orientation | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | R
9.4.475 – Conduct Safety Orientation | Oversees Conduct Safety Orientation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | A
9.4.475 – Conduct Safety Orientation | Field coordination for Conduct Safety Orientation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | C
9.4.480 – Conduct Safety Inspections | Leads safety activities for Conduct Safety Inspections | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | R
9.4.480 – Conduct Safety Inspections | Oversees Conduct Safety Inspections | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | A
9.4.480 – Conduct Safety Inspections | Field coordination for Conduct Safety Inspections | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | C
9.4.485 – Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | R
9.4.485 – Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | A
9.4.485 – Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | C
9.4.490 – Report Safety Incidents | Leads safety activities for Report Safety Incidents | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | R
9.4.490 – Report Safety Incidents | Oversees Report Safety Incidents | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | A
9.4.490 – Report Safety Incidents | Field coordination for Report Safety Incidents | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | C
9.4.495 – Investigate Accidents | Leads safety activities for Investigate Accidents | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.495 – Investigate Accidents | Oversees Investigate Accidents | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.495 – Investigate Accidents | Field coordination for Investigate Accidents | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.500 – Conduct Emergency Preparedness | Leads safety activities for Conduct Emergency Preparedness | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.500 – Conduct Emergency Preparedness | Oversees Conduct Emergency Preparedness | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.500 – Conduct Emergency Preparedness | Field coordination for Conduct Emergency Preparedness | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.505 – Conduct Safety Compliance Audits | Reviews for safety compliance for Conduct Safety Compliance Audits | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | C
9.4.505 – Conduct Safety Compliance Audits | Oversees Conduct Safety Compliance Audits | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | A
9.4.505 – Conduct Safety Compliance Audits | Field coordination for Conduct Safety Compliance Audits | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | C
9.4.510 – Provide Safety Training | Reviews for safety compliance for Provide Safety Training | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | C
9.4.510 – Provide Safety Training | Oversees Provide Safety Training | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | A
9.4.510 – Provide Safety Training | Field coordination for Provide Safety Training | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | C
9.4.515 – Develop Quality Management Plan | Performs quality activities for Develop Quality Management Plan | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | R
9.4.515 – Develop Quality Management Plan | Oversees Develop Quality Management Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | A
9.4.515 – Develop Quality Management Plan | Field coordination for Develop Quality Management Plan | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.520 – Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | R
9.4.520 – Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | A
9.4.520 – Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.525 – Conduct Quality Inspections | Performs quality activities for Conduct Quality Inspections | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | R
9.4.525 – Conduct Quality Inspections | Oversees Conduct Quality Inspections | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | A
9.4.525 – Conduct Quality Inspections | Field coordination for Conduct Quality Inspections | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.530 – Manage Quality Testing | Provides quality oversight for Manage Quality Testing | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.530 – Manage Quality Testing | Oversees Manage Quality Testing | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | A
9.4.530 – Manage Quality Testing | Field coordination for Manage Quality Testing | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.535 – Manage Nonconformance Reports (NCRs) | Performs quality activities for Manage Nonconformance Reports (NCRs) | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.535 – Manage Nonconformance Reports (NCRs) | Oversees Manage Nonconformance Reports (NCRs) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.535 – Manage Nonconformance Reports (NCRs) | Field coordination for Manage Nonconformance Reports (NCRs) | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.540 – Manage Quality Records | Provides quality oversight for Manage Quality Records | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.540 – Manage Quality Records | Oversees Manage Quality Records | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | A
9.4.540 – Manage Quality Records | Field coordination for Manage Quality Records | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.545 – Manage Punch List Quality | Provides quality oversight for Manage Punch List Quality | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.545 – Manage Punch List Quality | Oversees Manage Punch List Quality | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | A
9.4.545 – Manage Punch List Quality | Field coordination for Manage Punch List Quality | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.560 – Manage Manpower Allocation | Manages field operations for Manage Manpower Allocation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | R
9.4.560 – Manage Manpower Allocation | Oversees Manage Manpower Allocation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | A
9.4.565 – Manage Equipment Allocation | Oversees Manage Equipment Allocation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.565 – Manage Equipment Allocation | Field coordination for Manage Equipment Allocation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.570 – Manage Material Allocation | Oversees Manage Material Allocation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.570 – Manage Material Allocation | Field coordination for Manage Material Allocation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.576 – Manage Subcontractor Resources | Performs subcontracted work for Manage Subcontractor Resources | Subcontractors | Contract Requirements | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | R
9.4.576 – Manage Subcontractor Resources | Oversees Manage Subcontractor Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | A
9.4.576 – Manage Subcontractor Resources | Field coordination for Manage Subcontractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | C
9.4.580 – Manage Vendor Resources | Manages procurement for Manage Vendor Resources | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.580 – Manage Vendor Resources | Oversees Manage Vendor Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | A
9.4.580 – Manage Vendor Resources | Field coordination for Manage Vendor Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | C
9.4.585 – Plan Prefabrication Resources | Coordinates prefabrication for Plan Prefabrication Resources | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | R
9.4.585 – Plan Prefabrication Resources | Oversees Plan Prefabrication Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | A
9.4.585 – Plan Prefabrication Resources | Field coordination for Plan Prefabrication Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | C
9.4.590 – Manage Specialty Contractor Resources | Oversees Manage Specialty Contractor Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | A
9.4.590 – Manage Specialty Contractor Resources | Field coordination for Manage Specialty Contractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | C
9.4.595 – Prepare Resource Reports | Oversees Prepare Resource Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | A
9.4.595 – Prepare Resource Reports | Field coordination for Prepare Resource Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | C
9.4.605 – Issue Purchase Orders | Manages procurement for Issue Purchase Orders | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.605 – Issue Purchase Orders | Oversees Issue Purchase Orders | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | A
9.4.605 – Issue Purchase Orders | Field coordination for Issue Purchase Orders | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | C
9.4.610 – Manage Vendor Prequalification | Manages procurement for Manage Vendor Prequalification | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.610 – Manage Vendor Prequalification | Oversees Manage Vendor Prequalification | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | A
9.4.610 – Manage Vendor Prequalification | Field coordination for Manage Vendor Prequalification | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | C
9.4.615 – Manage Vendor Evaluations | Manages procurement for Manage Vendor Evaluations | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.615 – Manage Vendor Evaluations | Oversees Manage Vendor Evaluations | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | A
9.4.615 – Manage Vendor Evaluations | Field coordination for Manage Vendor Evaluations | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | C
9.4.620 – Manage Expediting | Manages procurement for Manage Expediting | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.620 – Manage Expediting | Oversees Manage Expediting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.620 – Manage Expediting | Field coordination for Manage Expediting | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.625 – Manage Delivery Tracking | Manages procurement for Manage Delivery Tracking | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.625 – Manage Delivery Tracking | Oversees Manage Delivery Tracking | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.625 – Manage Delivery Tracking | Field coordination for Manage Delivery Tracking | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.630 – Manage Material Receiving | Manages procurement for Manage Material Receiving | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.630 – Manage Material Receiving | Oversees Manage Material Receiving | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.630 – Manage Material Receiving | Field coordination for Manage Material Receiving | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.631 – Release of Large Feeder Wire | Oversees Release of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.631 – Release of Large Feeder Wire | Field coordination for Release of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.635 – Manage Material Inspection | Oversees Manage Material Inspection | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.635 – Manage Material Inspection | Field coordination for Manage Material Inspection | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.640 – Manage Storage and Logistics | Oversees Manage Storage and Logistics | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.640 – Manage Storage and Logistics | Field coordination for Manage Storage and Logistics | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.645 – Manage Material Handling | Oversees Manage Material Handling | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.645 – Manage Material Handling | Field coordination for Manage Material Handling | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.650 – Manage Inventory | Manages procurement for Manage Inventory | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.650 – Manage Inventory | Oversees Manage Inventory | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.650 – Manage Inventory | Field coordination for Manage Inventory | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.655 – Prepare Procurement Reports | Manages procurement for Prepare Procurement Reports | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.655 – Prepare Procurement Reports | Oversees Prepare Procurement Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | A
9.4.655 – Prepare Procurement Reports | Field coordination for Prepare Procurement Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | C
9.4.660 – Manage Procurement Closeout | Manages procurement for Manage Procurement Closeout | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.660 – Manage Procurement Closeout | Oversees closeout for Manage Procurement Closeout | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | A
9.4.660 – Manage Procurement Closeout | Field coordination for Manage Procurement Closeout | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | C
9.4.665 – Reconcile Procurement Accounts | Manages procurement for Reconcile Procurement Accounts | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.665 – Reconcile Procurement Accounts | Manages financial documentation for Reconcile Procurement Accounts | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.665 – Reconcile Procurement Accounts | Oversees Reconcile Procurement Accounts | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | A
9.4.665 – Reconcile Procurement Accounts | Field coordination for Reconcile Procurement Accounts | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | C
9.4.670 – Manage Vendor Closeout | Manages procurement for Manage Vendor Closeout | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | R
9.4.670 – Manage Vendor Closeout | Oversees closeout for Manage Vendor Closeout | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | A
9.4.670 – Manage Vendor Closeout | Field coordination for Manage Vendor Closeout | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | C
9.4.675 – Conduct Daily Huddles | Leads crew activities for Conduct Daily Huddles | Foreman | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | R
9.4.675 – Conduct Daily Huddles | Oversees Conduct Daily Huddles | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.675 – Conduct Daily Huddles | Field coordination for Conduct Daily Huddles | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.680 – Conduct Weekly Foreman Meetings | Leads crew activities for Conduct Weekly Foreman Meetings | Foreman | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | R
9.4.680 – Conduct Weekly Foreman Meetings | Oversees Conduct Weekly Foreman Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | A
9.4.680 – Conduct Weekly Foreman Meetings | Field coordination for Conduct Weekly Foreman Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | C
9.4.690 – Track Manpower Utilization | Manages field operations for Track Manpower Utilization | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | R
9.4.690 – Track Manpower Utilization | Oversees Track Manpower Utilization | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | A
9.4.695 – Track Production Quantities | Manages field operations for Track Production Quantities | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | R
9.4.695 – Track Production Quantities | Oversees Track Production Quantities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | A
9.4.700 – Track Equipment Utilization | Oversees Track Equipment Utilization | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.700 – Track Equipment Utilization | Field coordination for Track Equipment Utilization | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.705 – Manage Work Packaging | Oversees Manage Work Packaging | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.705 – Manage Work Packaging | Field coordination for Manage Work Packaging | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.710 – Manage Workface Planning | Oversees Manage Workface Planning | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.710 – Manage Workface Planning | Field coordination for Manage Workface Planning | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.715 – Manage Field Coordination | Manages field operations for Manage Field Coordination | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | R
9.4.715 – Manage Field Coordination | Oversees Manage Field Coordination | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | A
9.4.720 – Conduct Productivity Analysis | Oversees Conduct Productivity Analysis | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | A
9.4.720 – Conduct Productivity Analysis | Field coordination for Conduct Productivity Analysis | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | C
9.4.725 – Resolve Field Problems | Manages field operations for Resolve Field Problems | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | R
9.4.725 – Resolve Field Problems | Oversees Resolve Field Problems | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | A
9.4.735 – Perform Field Quality Verifications | Provides quality oversight for Perform Field Quality Verifications | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.735 – Perform Field Quality Verifications | Oversees Perform Field Quality Verifications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | A
9.4.735 – Perform Field Quality Verifications | Field coordination for Perform Field Quality Verifications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | C
9.4.745 – Manage Field Rework | Manages field operations for Manage Field Rework | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | R
9.4.745 – Manage Field Rework | Oversees Manage Field Rework | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | A
9.4.755 – Implement Field Productivity Improvements | Oversees Implement Field Productivity Improvements | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | A
9.4.755 – Implement Field Productivity Improvements | Field coordination for Implement Field Productivity Improvements | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | C
9.5.020 – Handling and/or Disposing of Excess Materials | Leads meeting coordination; Tracks commissioning progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Commissioning | A
9.5.020 – Handling and/or Disposing of Excess Materials | Conducts testing; Documents results; Identifies deficiencies ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | ✔ Covered | No change required. | Commissioning | R
9.5.020 – Handling and/or Disposing of Excess Materials | Supports testing activities; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Commissioning | R
9.5.020 – Handling and/or Disposing of Excess Materials | Verifies quality requirements; Reviews test results ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | ✔ Covered | No change required. | Commissioning | C
9.5.020 – Handling and/or Disposing of Excess Materials | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Contract Requirements | ✔ Covered | No change required. | Commissioning | R
9.5.550 – Manage Commissioning Activities | Overall commissioning management; Schedule coordination ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Commissioning | A
9.5.550 – Manage Commissioning Activities | Supports testing; Ensures systems ready; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Commissioning | R
9.5.550 – Manage Commissioning Activities | Executes testing protocols; Documents results ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | ✔ Covered | No change required. | Commissioning | R
9.5.550 – Manage Commissioning Activities | Verifies compliance; Reviews documentation ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | ✔ Covered | No change required. | Commissioning | R
9.5.550 – Manage Commissioning Activities | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Contract Requirements | ✔ Covered | No change required. | Commissioning | R
9.6.005 – Prepare for Turnover (Field Perspective) | Oversees closeout for Prepare for Turnover (Field Perspective) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | A
9.6.010 – Conduct Closeout Meetings | Leads closeout meetings; Tracks closeout progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout | A
9.6.010 – Conduct Closeout Meetings | Reports field status; Coordinates punch completion ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout | R
9.6.010 – Conduct Closeout Meetings | Participate; Complete their closeout requirements ¦ | ¦ Subcontractors | Contract Requirements | ✔ Covered | No change required. | Project closeout | R
9.6.010 – Conduct Closeout Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Client/Owner | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout | I
9.6.015 – Manage Project Turnover Documentation | Oversees closeout for Manage Project Turnover Documentation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | A
9.6.020 – Manage Punch List Closeout | Provides quality oversight for Manage Punch List Closeout | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | C
9.6.020 – Manage Punch List Closeout | Oversees closeout for Manage Punch List Closeout | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | A
9.6.030 – Manage As-Built Drawings | Manages as-built process; Submits final drawings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout | A
9.6.030 – Manage As-Built Drawings | Reviews markups for accuracy; Coordinates with field ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout | R
9.6.030 – Manage As-Built Drawings | Creates field markups; Documents actual conditions ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout | R
9.6.030 – Manage As-Built Drawings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Engineer/APM | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout | R
9.6.035 – Submit Warranties | Oversees Submit Warranties | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | A
9.6.040 – Submit O&M Manuals | Oversees closeout for Submit O&M Manuals | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | A
9.6.050 – Provide Owner Training | Participates in client communications for Provide Owner Training | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | C
9.6.050 – Provide Owner Training | Oversees Provide Owner Training | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | A
9.6.065 – Archive Project Documentation | Manages documentation for Archive Project Documentation | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | R
9.6.065 – Archive Project Documentation | Oversees Archive Project Documentation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | A
9.6.070 – Conduct Post-Project Review | Oversees review process; Approves action items ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | ✔ Covered | No change required. | Project closeout | A
9.6.070 – Conduct Post-Project Review | Leads review meeting; Compiles findings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout | R
9.6.070 – Conduct Post-Project Review | Provides field perspective; Shares observations ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout | R
9.6.070 – Conduct Post-Project Review | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Operations Manager | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout | C
9.6.080 – Capture Client Feedback | Oversees feedback process; Reviews results ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | ✔ Covered | No change required. | Project closeout | A
9.6.080 – Capture Client Feedback | Conducts feedback meeting; Documents responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout | R
9.6.080 – Capture Client Feedback | Uses feedback for relationship management ¦ | ¦ Business Development | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout | C
9.6.080 – Capture Client Feedback | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Executive Committee | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout | I
9.6.085 – Document Lessons Learned | Maintains lessons learned database; Ensures implementation ¦ | ¦ Operations Manager | Sec. 9.2 General Directives | ✔ Covered | No change required. | Project closeout | A
9.6.085 – Document Lessons Learned | Documents project-specific lessons; Submits for review ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | ✔ Covered | No change required. | Project closeout | R
9.6.085 – Document Lessons Learned | Captures field-level learnings; Contributes to documentation ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project closeout | R
9.6.085 – Document Lessons Learned | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Branch Manager | Sec. 9.6 Branch Management | ✔ Covered | No change required. | Project closeout | C

## Redline Recs
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | Redline Proposal
9.1.050 – Prepare Construction Takeoff | Oversees Prepare Construction Takeoff | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | General | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.2.005 – Review Contract for High Risk Clauses | Oversees Review Contract for High Risk Clauses | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope and contract review | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.015 – Project Turnover Meeting | Oversees closeout for Project Turnover Meeting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Team selection and turnover | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.020 – Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.2.020 – Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.030 – Review Contract for Unfavorable or High-Risk Clauses | Oversees Review Contract for Unfavorable or High-Risk Clauses | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope and contract review | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.040 – Project Manager Reviews Plans Specifications & Schedule | Coordinates scheduling for Project Manager Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.2.040 – Project Manager Reviews Plans Specifications & Schedule | Manages technical documentation for Project Manager Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | Coordinates scheduling for Field Supervisor Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | Manages technical documentation for Field Supervisor Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.2.055 – Compare Estimated vs Planned Performance | Provides estimating support for Compare Estimated vs Planned Performance | Estimator | Sec. 9.9 Estimating Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | Add explicit C assignment for Estimator in Sec. 9.9 Estimating Directives
9.2.055 – Compare Estimated vs Planned Performance | Oversees Compare Estimated vs Planned Performance | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.057 – Identify VE and Prefabrication Opportunities | Coordinates prefabrication for Identify VE and Prefabrication Opportunities | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | Add explicit R assignment for Prefabrication Lead in Sec. 9.12 Prefabrication Directives
9.2.057 – Identify VE and Prefabrication Opportunities | Oversees Identify VE and Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.080 – Prepare Material Handling Plan | Oversees Prepare Material Handling Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.090 – Develop Labor Budget | Provides financial support for Develop Labor Budget | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting | Add explicit C assignment for Accounting in Sec. 9.11 Accounting Directives
9.2.090 – Develop Labor Budget | Oversees Develop Labor Budget | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.100 – Prepare Layout & Sequencing Plan | Oversees Prepare Layout & Sequencing Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.110 – Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.2.110 – Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scheduling | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.120 – Establish Tracking & Control Systems | Oversees Establish Tracking & Control Systems | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.130 – Construction Execution Kickoff Meeting | Leads coordination for Construction Execution Kickoff Meeting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Preconstruction planning | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.2.140 – Develop Project Budget | Provides financial support for Develop Project Budget | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting | Add explicit C assignment for Accounting in Sec. 9.11 Accounting Directives
9.2.140 – Develop Project Budget | Oversees Develop Project Budget | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Budgeting | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.2.160 – Develop Procurement Plan | Manages procurement for Develop Procurement Plan | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.2.160 – Develop Procurement Plan | Oversees Develop Procurement Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement planning | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.3.050 – Setup Temporary Water | Coordinates site setup for Setup Temporary Water | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.3.050 – Setup Temporary Water | Oversees Setup Temporary Water | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.3.060 – Setup Sanitary Facilities | Coordinates site setup for Setup Sanitary Facilities | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.3.060 – Setup Sanitary Facilities | Oversees Setup Sanitary Facilities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.3.070 – Setup Temporary Lighting | Coordinates site setup for Setup Temporary Lighting | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.3.070 – Setup Temporary Lighting | Oversees Setup Temporary Lighting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.3.080 – Setup Signage | Coordinates site setup for Setup Signage | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.3.080 – Setup Signage | Oversees Setup Signage | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.3.090 – Setup Security | Coordinates site setup for Setup Security | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.3.090 – Setup Security | Oversees Setup Security | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.3.100 – Setup Laydown Area | Coordinates site setup for Setup Laydown Area | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.3.100 – Setup Laydown Area | Oversees Setup Laydown Area | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.3.110 – Setup Equipment Staging | Coordinates site setup for Setup Equipment Staging | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.3.110 – Setup Equipment Staging | Oversees Setup Equipment Staging | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.3.120 – Setup Parking | Coordinates site setup for Setup Parking | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.3.120 – Setup Parking | Oversees Setup Parking | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Site mobilization | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.3.470 – Develop Site-Specific Safety Plan | Reviews for safety compliance for Develop Site-Specific Safety Plan | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety setup | Add explicit C assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.3.470 – Develop Site-Specific Safety Plan | Oversees Develop Site-Specific Safety Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety setup | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.3.470 – Develop Site-Specific Safety Plan | Field coordination for Develop Site-Specific Safety Plan | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety setup | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.010 – Conduct Coordination Meetings | Leads coordination for Conduct Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.010 – Conduct Coordination Meetings | Field coordination for Conduct Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.020 – Conduct Subcontractor Coordination Meetings | Performs subcontracted work for Conduct Subcontractor Coordination Meetings | Subcontractors | Contract Requirements | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit R assignment for Subcontractors in Contract Requirements
9.4.020 – Conduct Subcontractor Coordination Meetings | Leads coordination for Conduct Subcontractor Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.020 – Conduct Subcontractor Coordination Meetings | Field coordination for Conduct Subcontractor Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.030 – Conduct Client/Owner Meetings | Participates in client communications for Conduct Client/Owner Meetings | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit C assignment for Branch Manager in Sec. 9.6 Branch Management
9.4.030 – Conduct Client/Owner Meetings | Oversees Conduct Client/Owner Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.030 – Conduct Client/Owner Meetings | Field coordination for Conduct Client/Owner Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.040 – Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit R assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.4.040 – Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.040 – Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Coordinates prefabrication for Identify Value Engineering & Prefabrication Opportunities | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Prefabrication Lead in Sec. 9.12 Prefabrication Directives
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Oversees Identify Value Engineering & Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Field coordination for Identify Value Engineering & Prefabrication Opportunities | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.050 – Conduct Prefabrication Coordination Meetings | Coordinates prefabrication for Conduct Prefabrication Coordination Meetings | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit R assignment for Prefabrication Lead in Sec. 9.12 Prefabrication Directives
9.4.050 – Conduct Prefabrication Coordination Meetings | Leads coordination for Conduct Prefabrication Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.050 – Conduct Prefabrication Coordination Meetings | Field coordination for Conduct Prefabrication Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.055 – Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.055 – Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.055 – Procurement of Large Feeder Wire | Field coordination for Procurement of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.060 – Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit R assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.4.060 – Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.060 – Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.190 – Document Filing Standards | Manages documentation for Document Filing Standards | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit R assignment for Site Administrator in Sec. 9.8 Site Administration
9.4.190 – Document Filing Standards | Oversees Document Filing Standards | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.190 – Document Filing Standards | Field coordination for Document Filing Standards | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.195 – Manage Project Documentation System | Manages documentation for Manage Project Documentation System | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit R assignment for Site Administrator in Sec. 9.8 Site Administration
9.4.195 – Manage Project Documentation System | Oversees Manage Project Documentation System | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.195 – Manage Project Documentation System | Field coordination for Manage Project Documentation System | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.200 – Manage Submittals | Manages technical documentation for Manage Submittals | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.200 – Manage Submittals | Field coordination for Manage Submittals | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.205 – Manage RFIs (Requests for Information) | Manages technical documentation for Manage RFIs (Requests for Information) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.205 – Manage RFIs (Requests for Information) | Field coordination for Manage RFIs (Requests for Information) | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Document management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.210 – Manage Meeting Minutes | Manages documentation for Manage Meeting Minutes | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit R assignment for Site Administrator in Sec. 9.8 Site Administration
9.4.210 – Manage Meeting Minutes | Oversees Manage Meeting Minutes | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.210 – Manage Meeting Minutes | Field coordination for Manage Meeting Minutes | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.215 – Manage Daily Reports | Manages field operations for Manage Daily Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.215 – Manage Daily Reports | Oversees Manage Daily Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.220 – Manage Drawing Logs | Manages technical documentation for Manage Drawing Logs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.220 – Manage Drawing Logs | Field coordination for Manage Drawing Logs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.225 – Manage Specifications | Manages technical documentation for Manage Specifications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.225 – Manage Specifications | Field coordination for Manage Specifications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.230 – Manage Correspondence | Manages documentation for Manage Correspondence | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Site Administrator in Sec. 9.8 Site Administration
9.4.230 – Manage Correspondence | Oversees Manage Correspondence | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.230 – Manage Correspondence | Field coordination for Manage Correspondence | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.235 – Manage Permits | Oversees Manage Permits | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.235 – Manage Permits | Field coordination for Manage Permits | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.240 – Manage Inspection Reports | Oversees Manage Inspection Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.240 – Manage Inspection Reports | Field coordination for Manage Inspection Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.270 – Manage Project Communications | Manages communications for Manage Project Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.270 – Manage Project Communications | Field coordination for Manage Project Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.275 – Manage Internal Communications | Manages communications for Manage Internal Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.275 – Manage Internal Communications | Field coordination for Manage Internal Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.280 – Manage External Communications | Manages communications for Manage External Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.280 – Manage External Communications | Field coordination for Manage External Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.285 – Manage Client/Owner Communications | Participates in client communications for Manage Client/Owner Communications | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Branch Manager in Sec. 9.6 Branch Management
9.4.285 – Manage Client/Owner Communications | Manages communications for Manage Client/Owner Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.285 – Manage Client/Owner Communications | Field coordination for Manage Client/Owner Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.290 – Manage Subcontractor Communications | Performs subcontracted work for Manage Subcontractor Communications | Subcontractors | Contract Requirements | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Subcontractors in Contract Requirements
9.4.290 – Manage Subcontractor Communications | Manages communications for Manage Subcontractor Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.290 – Manage Subcontractor Communications | Field coordination for Manage Subcontractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.295 – Manage Vendor Supplier Communications | Manages procurement for Manage Vendor Supplier Communications | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.295 – Manage Vendor Supplier Communications | Manages communications for Manage Vendor Supplier Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.295 – Manage Vendor Supplier Communications | Field coordination for Manage Vendor Supplier Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.300 – Manage Architect/Engineer Communications | Manages communications for Manage Architect/Engineer Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.300 – Manage Architect/Engineer Communications | Field coordination for Manage Architect/Engineer Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.305 – Manage Regulatory/Authority Communications | Manages communications for Manage Regulatory/Authority Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.305 – Manage Regulatory/Authority Communications | Field coordination for Manage Regulatory/Authority Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.310 – Manage General Contractor Communications | Manages communications for Manage General Contractor Communications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.310 – Manage General Contractor Communications | Field coordination for Manage General Contractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Communications | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.315 – Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.4.315 – Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.315 – Develop Project Schedule | Field coordination for Develop Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.320 – Update Project Schedule | Coordinates scheduling for Update Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.4.320 – Update Project Schedule | Oversees Update Project Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.320 – Update Project Schedule | Field coordination for Update Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.325 – Monitor Schedule Performance | Coordinates scheduling for Monitor Schedule Performance | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.4.325 – Monitor Schedule Performance | Oversees Monitor Schedule Performance | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.325 – Monitor Schedule Performance | Field coordination for Monitor Schedule Performance | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.330 – Develop Schedule Recovery Plans | Coordinates scheduling for Develop Schedule Recovery Plans | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.4.330 – Develop Schedule Recovery Plans | Oversees Develop Schedule Recovery Plans | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.330 – Develop Schedule Recovery Plans | Field coordination for Develop Schedule Recovery Plans | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.335 – Prepare Lookahead Schedules | Coordinates scheduling for Prepare Lookahead Schedules | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.4.335 – Prepare Lookahead Schedules | Oversees Prepare Lookahead Schedules | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.335 – Prepare Lookahead Schedules | Field coordination for Prepare Lookahead Schedules | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.340 – Manage Resource-Loaded Schedules | Coordinates scheduling for Manage Resource-Loaded Schedules | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.4.340 – Manage Resource-Loaded Schedules | Oversees Manage Resource-Loaded Schedules | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.340 – Manage Resource-Loaded Schedules | Field coordination for Manage Resource-Loaded Schedules | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.345 – Conduct Schedule Review Meetings | Coordinates scheduling for Conduct Schedule Review Meetings | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.4.345 – Conduct Schedule Review Meetings | Oversees Conduct Schedule Review Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.345 – Conduct Schedule Review Meetings | Field coordination for Conduct Schedule Review Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.350 – Manage Schedule Change Requests | Coordinates scheduling for Manage Schedule Change Requests | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.4.350 – Manage Schedule Change Requests | Oversees Manage Schedule Change Requests | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.350 – Manage Schedule Change Requests | Field coordination for Manage Schedule Change Requests | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.355 – Manage Project Scope | Manages contract changes for Manage Project Scope | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.355 – Manage Project Scope | Field coordination for Manage Project Scope | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.360 – Manage Change Orders | Manages contract changes for Manage Change Orders | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.360 – Manage Change Orders | Field coordination for Manage Change Orders | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.365 – Manage Potential Change Orders (PCOs) | Manages contract changes for Manage Potential Change Orders (PCOs) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.365 – Manage Potential Change Orders (PCOs) | Field coordination for Manage Potential Change Orders (PCOs) | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.370 – Manage Owner Directives | Participates in client communications for Manage Owner Directives | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Branch Manager in Sec. 9.6 Branch Management
9.4.370 – Manage Owner Directives | Oversees Manage Owner Directives | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.370 – Manage Owner Directives | Field coordination for Manage Owner Directives | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.375 – Manage Scope Clarifications | Manages contract changes for Manage Scope Clarifications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.375 – Manage Scope Clarifications | Field coordination for Manage Scope Clarifications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Scope management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.380 – Manage Backcharges | Manages contract changes for Manage Backcharges | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.380 – Manage Backcharges | Field coordination for Manage Backcharges | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.385 – Manage Force Account Work | Manages contract changes for Manage Force Account Work | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Project Manager in Sec. 9.5 PM Directives
9.4.385 – Manage Force Account Work | Field coordination for Manage Force Account Work | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.390 – Manage Claims | Provides executive approval for Manage Claims | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Branch Manager in Sec. 9.6 Branch Management
9.4.390 – Manage Claims | Oversees Manage Claims | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.390 – Manage Claims | Field coordination for Manage Claims | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.400 – Monitor Project Costs | Provides financial support for Monitor Project Costs | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.400 – Monitor Project Costs | Oversees Monitor Project Costs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.400 – Monitor Project Costs | Field coordination for Monitor Project Costs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.405 – Manage Cost Forecasts | Provides financial support for Manage Cost Forecasts | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.405 – Manage Cost Forecasts | Oversees Manage Cost Forecasts | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.405 – Manage Cost Forecasts | Field coordination for Manage Cost Forecasts | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.410 – Manage Cost Codes | Manages financial documentation for Manage Cost Codes | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit R assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.410 – Manage Cost Codes | Oversees Manage Cost Codes | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.410 – Manage Cost Codes | Field coordination for Manage Cost Codes | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.415 – Manage Committed Costs | Provides financial support for Manage Committed Costs | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.415 – Manage Committed Costs | Oversees Manage Committed Costs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.415 – Manage Committed Costs | Field coordination for Manage Committed Costs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.420 – Manage Actual Costs | Provides financial support for Manage Actual Costs | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.420 – Manage Actual Costs | Oversees Manage Actual Costs | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.420 – Manage Actual Costs | Field coordination for Manage Actual Costs | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.425 – Manage Job Cost Reports | Manages financial documentation for Manage Job Cost Reports | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit R assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.425 – Manage Job Cost Reports | Oversees Manage Job Cost Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.425 – Manage Job Cost Reports | Field coordination for Manage Job Cost Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.430 – Manage Profit Projections | Provides financial support for Manage Profit Projections | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.430 – Manage Profit Projections | Oversees Manage Profit Projections | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.430 – Manage Profit Projections | Field coordination for Manage Profit Projections | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.435 – Manage Cost-to-Complete | Provides financial support for Manage Cost-to-Complete | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.435 – Manage Cost-to-Complete | Oversees Manage Cost-to-Complete | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.435 – Manage Cost-to-Complete | Field coordination for Manage Cost-to-Complete | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Cost management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.440 – Prepare Billing Schedule | Manages financial documentation for Prepare Billing Schedule | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit R assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.440 – Prepare Billing Schedule | Coordinates scheduling for Prepare Billing Schedule | Superintendent | Sec. 9.4 Superintendent Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Superintendent in Sec. 9.4 Superintendent Directives
9.4.440 – Prepare Billing Schedule | Oversees Prepare Billing Schedule | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.440 – Prepare Billing Schedule | Field coordination for Prepare Billing Schedule | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Schedule management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.445 – Prepare Monthly Pay Applications | Manages financial documentation for Prepare Monthly Pay Applications | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.445 – Prepare Monthly Pay Applications | Oversees Prepare Monthly Pay Applications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.445 – Prepare Monthly Pay Applications | Field coordination for Prepare Monthly Pay Applications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.450 – Track Accounts Receivable | Manages financial documentation for Track Accounts Receivable | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.450 – Track Accounts Receivable | Oversees Track Accounts Receivable | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.450 – Track Accounts Receivable | Field coordination for Track Accounts Receivable | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.455 – Manage Lien Waivers | Oversees Manage Lien Waivers | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.455 – Manage Lien Waivers | Field coordination for Manage Lien Waivers | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.460 – Manage Retainage | Manages financial documentation for Manage Retainage | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.460 – Manage Retainage | Oversees Manage Retainage | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.460 – Manage Retainage | Field coordination for Manage Retainage | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.465 – Manage Final Invoicing | Oversees Manage Final Invoicing | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.465 – Manage Final Invoicing | Field coordination for Manage Final Invoicing | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.475 – Conduct Safety Orientation | Leads safety activities for Conduct Safety Orientation | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit R assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.4.475 – Conduct Safety Orientation | Oversees Conduct Safety Orientation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.475 – Conduct Safety Orientation | Field coordination for Conduct Safety Orientation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.480 – Conduct Safety Inspections | Leads safety activities for Conduct Safety Inspections | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit R assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.4.480 – Conduct Safety Inspections | Oversees Conduct Safety Inspections | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.480 – Conduct Safety Inspections | Field coordination for Conduct Safety Inspections | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.485 – Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit R assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.4.485 – Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.485 – Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.490 – Report Safety Incidents | Leads safety activities for Report Safety Incidents | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit R assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.4.490 – Report Safety Incidents | Oversees Report Safety Incidents | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.490 – Report Safety Incidents | Field coordination for Report Safety Incidents | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.495 – Investigate Accidents | Leads safety activities for Investigate Accidents | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.4.495 – Investigate Accidents | Oversees Investigate Accidents | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.495 – Investigate Accidents | Field coordination for Investigate Accidents | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.500 – Conduct Emergency Preparedness | Leads safety activities for Conduct Emergency Preparedness | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.4.500 – Conduct Emergency Preparedness | Oversees Conduct Emergency Preparedness | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.500 – Conduct Emergency Preparedness | Field coordination for Conduct Emergency Preparedness | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.505 – Conduct Safety Compliance Audits | Reviews for safety compliance for Conduct Safety Compliance Audits | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit C assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.4.505 – Conduct Safety Compliance Audits | Oversees Conduct Safety Compliance Audits | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.505 – Conduct Safety Compliance Audits | Field coordination for Conduct Safety Compliance Audits | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.510 – Provide Safety Training | Reviews for safety compliance for Provide Safety Training | Safety Coordinator | Sec. 9.7 Safety Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit C assignment for Safety Coordinator in Sec. 9.7 Safety Directives
9.4.510 – Provide Safety Training | Oversees Provide Safety Training | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.510 – Provide Safety Training | Field coordination for Provide Safety Training | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Safety management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.515 – Develop Quality Management Plan | Performs quality activities for Develop Quality Management Plan | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit R assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.4.515 – Develop Quality Management Plan | Oversees Develop Quality Management Plan | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.515 – Develop Quality Management Plan | Field coordination for Develop Quality Management Plan | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.520 – Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit R assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.4.520 – Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.520 – Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.525 – Conduct Quality Inspections | Performs quality activities for Conduct Quality Inspections | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit R assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.4.525 – Conduct Quality Inspections | Oversees Conduct Quality Inspections | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.525 – Conduct Quality Inspections | Field coordination for Conduct Quality Inspections | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.530 – Manage Quality Testing | Provides quality oversight for Manage Quality Testing | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.4.530 – Manage Quality Testing | Oversees Manage Quality Testing | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.530 – Manage Quality Testing | Field coordination for Manage Quality Testing | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.535 – Manage Nonconformance Reports (NCRs) | Performs quality activities for Manage Nonconformance Reports (NCRs) | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.4.535 – Manage Nonconformance Reports (NCRs) | Oversees Manage Nonconformance Reports (NCRs) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.535 – Manage Nonconformance Reports (NCRs) | Field coordination for Manage Nonconformance Reports (NCRs) | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.540 – Manage Quality Records | Provides quality oversight for Manage Quality Records | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.4.540 – Manage Quality Records | Oversees Manage Quality Records | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.540 – Manage Quality Records | Field coordination for Manage Quality Records | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.545 – Manage Punch List Quality | Provides quality oversight for Manage Punch List Quality | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.4.545 – Manage Punch List Quality | Oversees Manage Punch List Quality | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.545 – Manage Punch List Quality | Field coordination for Manage Punch List Quality | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.560 – Manage Manpower Allocation | Manages field operations for Manage Manpower Allocation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.560 – Manage Manpower Allocation | Oversees Manage Manpower Allocation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.565 – Manage Equipment Allocation | Oversees Manage Equipment Allocation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.565 – Manage Equipment Allocation | Field coordination for Manage Equipment Allocation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.570 – Manage Material Allocation | Oversees Manage Material Allocation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.570 – Manage Material Allocation | Field coordination for Manage Material Allocation | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.576 – Manage Subcontractor Resources | Performs subcontracted work for Manage Subcontractor Resources | Subcontractors | Contract Requirements | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit R assignment for Subcontractors in Contract Requirements
9.4.576 – Manage Subcontractor Resources | Oversees Manage Subcontractor Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.576 – Manage Subcontractor Resources | Field coordination for Manage Subcontractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.580 – Manage Vendor Resources | Manages procurement for Manage Vendor Resources | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.580 – Manage Vendor Resources | Oversees Manage Vendor Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.580 – Manage Vendor Resources | Field coordination for Manage Vendor Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.585 – Plan Prefabrication Resources | Coordinates prefabrication for Plan Prefabrication Resources | Prefabrication Lead | Sec. 9.12 Prefabrication Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit R assignment for Prefabrication Lead in Sec. 9.12 Prefabrication Directives
9.4.585 – Plan Prefabrication Resources | Oversees Plan Prefabrication Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.585 – Plan Prefabrication Resources | Field coordination for Plan Prefabrication Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.590 – Manage Specialty Contractor Resources | Oversees Manage Specialty Contractor Resources | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.590 – Manage Specialty Contractor Resources | Field coordination for Manage Specialty Contractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.595 – Prepare Resource Reports | Oversees Prepare Resource Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.595 – Prepare Resource Reports | Field coordination for Prepare Resource Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.605 – Issue Purchase Orders | Manages procurement for Issue Purchase Orders | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.605 – Issue Purchase Orders | Oversees Issue Purchase Orders | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.605 – Issue Purchase Orders | Field coordination for Issue Purchase Orders | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.610 – Manage Vendor Prequalification | Manages procurement for Manage Vendor Prequalification | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.610 – Manage Vendor Prequalification | Oversees Manage Vendor Prequalification | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.610 – Manage Vendor Prequalification | Field coordination for Manage Vendor Prequalification | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.615 – Manage Vendor Evaluations | Manages procurement for Manage Vendor Evaluations | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.615 – Manage Vendor Evaluations | Oversees Manage Vendor Evaluations | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.615 – Manage Vendor Evaluations | Field coordination for Manage Vendor Evaluations | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.620 – Manage Expediting | Manages procurement for Manage Expediting | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.620 – Manage Expediting | Oversees Manage Expediting | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.620 – Manage Expediting | Field coordination for Manage Expediting | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.625 – Manage Delivery Tracking | Manages procurement for Manage Delivery Tracking | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.625 – Manage Delivery Tracking | Oversees Manage Delivery Tracking | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.625 – Manage Delivery Tracking | Field coordination for Manage Delivery Tracking | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.630 – Manage Material Receiving | Manages procurement for Manage Material Receiving | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.630 – Manage Material Receiving | Oversees Manage Material Receiving | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.630 – Manage Material Receiving | Field coordination for Manage Material Receiving | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.631 – Release of Large Feeder Wire | Oversees Release of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.631 – Release of Large Feeder Wire | Field coordination for Release of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.635 – Manage Material Inspection | Oversees Manage Material Inspection | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.635 – Manage Material Inspection | Field coordination for Manage Material Inspection | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.640 – Manage Storage and Logistics | Oversees Manage Storage and Logistics | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.640 – Manage Storage and Logistics | Field coordination for Manage Storage and Logistics | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.645 – Manage Material Handling | Oversees Manage Material Handling | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.645 – Manage Material Handling | Field coordination for Manage Material Handling | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.650 – Manage Inventory | Manages procurement for Manage Inventory | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.650 – Manage Inventory | Oversees Manage Inventory | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.650 – Manage Inventory | Field coordination for Manage Inventory | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.655 – Prepare Procurement Reports | Manages procurement for Prepare Procurement Reports | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.655 – Prepare Procurement Reports | Oversees Prepare Procurement Reports | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.655 – Prepare Procurement Reports | Field coordination for Prepare Procurement Reports | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.660 – Manage Procurement Closeout | Manages procurement for Manage Procurement Closeout | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.660 – Manage Procurement Closeout | Oversees closeout for Manage Procurement Closeout | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.660 – Manage Procurement Closeout | Field coordination for Manage Procurement Closeout | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.665 – Reconcile Procurement Accounts | Manages procurement for Reconcile Procurement Accounts | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.665 – Reconcile Procurement Accounts | Manages financial documentation for Reconcile Procurement Accounts | Accounting | Sec. 9.11 Accounting Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Accounting in Sec. 9.11 Accounting Directives
9.4.665 – Reconcile Procurement Accounts | Oversees Reconcile Procurement Accounts | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.665 – Reconcile Procurement Accounts | Field coordination for Reconcile Procurement Accounts | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.670 – Manage Vendor Closeout | Manages procurement for Manage Vendor Closeout | Purchasing | Sec. 9.10 Purchasing Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit R assignment for Purchasing in Sec. 9.10 Purchasing Directives
9.4.670 – Manage Vendor Closeout | Oversees closeout for Manage Vendor Closeout | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.670 – Manage Vendor Closeout | Field coordination for Manage Vendor Closeout | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Procurement execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.675 – Conduct Daily Huddles | Leads crew activities for Conduct Daily Huddles | Foreman | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit R assignment for Foreman in Sec. 9.3 Field Leadership
9.4.675 – Conduct Daily Huddles | Oversees Conduct Daily Huddles | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.675 – Conduct Daily Huddles | Field coordination for Conduct Daily Huddles | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.680 – Conduct Weekly Foreman Meetings | Leads crew activities for Conduct Weekly Foreman Meetings | Foreman | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit R assignment for Foreman in Sec. 9.3 Field Leadership
9.4.680 – Conduct Weekly Foreman Meetings | Oversees Conduct Weekly Foreman Meetings | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.680 – Conduct Weekly Foreman Meetings | Field coordination for Conduct Weekly Foreman Meetings | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.690 – Track Manpower Utilization | Manages field operations for Track Manpower Utilization | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.690 – Track Manpower Utilization | Oversees Track Manpower Utilization | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Resource management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.695 – Track Production Quantities | Manages field operations for Track Production Quantities | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.695 – Track Production Quantities | Oversees Track Production Quantities | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.700 – Track Equipment Utilization | Oversees Track Equipment Utilization | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.700 – Track Equipment Utilization | Field coordination for Track Equipment Utilization | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.705 – Manage Work Packaging | Oversees Manage Work Packaging | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.705 – Manage Work Packaging | Field coordination for Manage Work Packaging | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.710 – Manage Workface Planning | Oversees Manage Workface Planning | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.710 – Manage Workface Planning | Field coordination for Manage Workface Planning | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.715 – Manage Field Coordination | Manages field operations for Manage Field Coordination | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.715 – Manage Field Coordination | Oversees Manage Field Coordination | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Coordination | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.720 – Conduct Productivity Analysis | Oversees Conduct Productivity Analysis | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.720 – Conduct Productivity Analysis | Field coordination for Conduct Productivity Analysis | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Execution | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.725 – Resolve Field Problems | Manages field operations for Resolve Field Problems | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.725 – Resolve Field Problems | Oversees Resolve Field Problems | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.735 – Perform Field Quality Verifications | Provides quality oversight for Perform Field Quality Verifications | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.4.735 – Perform Field Quality Verifications | Oversees Perform Field Quality Verifications | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.735 – Perform Field Quality Verifications | Field coordination for Perform Field Quality Verifications | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Quality management | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.745 – Manage Field Rework | Manages field operations for Manage Field Rework | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | Add explicit R assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.4.745 – Manage Field Rework | Oversees Manage Field Rework | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.755 – Implement Field Productivity Improvements | Oversees Implement Field Productivity Improvements | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.4.755 – Implement Field Productivity Improvements | Field coordination for Implement Field Productivity Improvements | Field Supervisor | Sec. 9.3 Field Leadership | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Field operations | Add explicit C assignment for Field Supervisor in Sec. 9.3 Field Leadership
9.6.005 – Prepare for Turnover (Field Perspective) | Oversees closeout for Prepare for Turnover (Field Perspective) | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.6.015 – Manage Project Turnover Documentation | Oversees closeout for Manage Project Turnover Documentation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.6.020 – Manage Punch List Closeout | Provides quality oversight for Manage Punch List Closeout | Quality Inspector | Sec. 9.13 Quality Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit C assignment for Quality Inspector in Sec. 9.13 Quality Directives
9.6.020 – Manage Punch List Closeout | Oversees closeout for Manage Punch List Closeout | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.6.035 – Submit Warranties | Oversees Submit Warranties | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.6.040 – Submit O&M Manuals | Oversees closeout for Submit O&M Manuals | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.6.050 – Provide Owner Training | Participates in client communications for Provide Owner Training | Branch Manager | Sec. 9.6 Branch Management | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit C assignment for Branch Manager in Sec. 9.6 Branch Management
9.6.050 – Provide Owner Training | Oversees Provide Owner Training | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives
9.6.065 – Archive Project Documentation | Manages documentation for Archive Project Documentation | Site Administrator | Sec. 9.8 Site Administration | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit R assignment for Site Administrator in Sec. 9.8 Site Administration
9.6.065 – Archive Project Documentation | Oversees Archive Project Documentation | Project Manager | Sec. 9.5 PM Directives | ⚠ Gap – role inferred | Verify role assignment and add explicit RACI to SOP. | Project closeout | Add explicit A assignment for Project Manager in Sec. 9.5 PM Directives

## Conflict Matrix
SOP Title | Conflict Description | Conflict Type | Resolution Recommendation
9.2.010 – Team Selection | Responsibility overlap between PM and GS | Authority Chain | Clarify PM as A (accountable), GS as R (responsible) for field activities
9.3.050 – Setup Temporary Water | Multiple R assignments: Field Supervisor, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.3.060 – Setup Sanitary Facilities | Multiple R assignments: Field Supervisor, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.3.070 – Setup Temporary Lighting | Multiple R assignments: Field Supervisor, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.3.080 – Setup Signage | Multiple R assignments: Field Supervisor, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.3.090 – Setup Security | Multiple R assignments: Field Supervisor, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.3.100 – Setup Laydown Area | Multiple R assignments: Field Supervisor, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.3.110 – Setup Equipment Staging | Multiple R assignments: Field Supervisor, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.3.120 – Setup Parking | Multiple R assignments: Field Supervisor, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.4.020 – Conduct Subcontractor Coordination Meetings | Multiple R assignments: Subcontractors, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.4.050 – Conduct Prefabrication Coordination Meetings | Multiple R assignments: Prefabrication Lead, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.4.290 – Manage Subcontractor Communications | Multiple R assignments: Subcontractors, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.4.295 – Manage Vendor Supplier Communications | Multiple R assignments: Purchasing, Project Manager | Accountability Clarity | Designate single R, convert others to C or I
9.4.665 – Reconcile Procurement Accounts | Multiple R assignments: Purchasing, Accounting | Accountability Clarity | Designate single R, convert others to C or I

## Closeout Checklist
Role | Closeout Task | Directive Section | Coverage Status
Project Manager | Submit O&M manuals and warranty letters | Sec. 9.5 PM Directives | ✔ Covered
Project Manager | Ensure all RFIs, Submittals, and Change Orders are closed | Sec. 9.5 PM Directives | ✔ Covered
Project Manager | Complete final billing and retainage release | Sec. 9.5 PM Directives | ✔ Covered
Project Manager | Conduct post-project review meeting | Sec. 9.5 PM Directives | ✔ Covered
Project Manager | Archive project documentation | Sec. 9.5 PM Directives | ✔ Covered
Project Manager | Capture lessons learned | Sec. 9.5 PM Directives | ✔ Covered
Field Supervisor | Submit daily reports and as-built drawings | Sec. 9.3 Field Leadership | ✔ Covered
Field Supervisor | Complete punch list closeout | Sec. 9.3 Field Leadership | ✔ Covered
Field Supervisor | Demobilize site and equipment | Sec. 9.3 Field Leadership | ✔ Covered
General Superintendent | Confirm apprentice/journeyman ratios and training docs | Sec. 9.4 GS Directives | ✔ Covered
General Superintendent | Review final manpower utilization | Sec. 9.4 GS Directives | ✔ Covered
Safety Coordinator | Submit final safety reports | Sec. 9.7 Safety Directives | ✔ Covered
Safety Coordinator | Close out incident investigations | Sec. 9.7 Safety Directives | ✔ Covered
Quality Inspector | Complete final quality inspections | Sec. 9.13 Quality Directives | ✔ Covered
Quality Inspector | Close NCRs and quality records | Sec. 9.13 Quality Directives | ✔ Covered
Purchasing | Reconcile procurement accounts | Sec. 9.10 Purchasing Directives | ✔ Covered
Purchasing | Complete vendor closeout | Sec. 9.10 Purchasing Directives | ✔ Covered
Accounting | Final invoicing and AR collection | Sec. 9.11 Accounting Directives | ✔ Covered
Accounting | Release retainage and lien waivers | Sec. 9.11 Accounting Directives | ✔ Covered
Site Administrator | Archive all project files | Sec. 9.8 Site Administration | ✔ Covered
Site Administrator | Transfer documentation to owner | Sec. 9.8 Site Administration | ✔ Covered
Branch Manager | Approve final project closeout | Sec. 9.6 Branch Management | ✔ Covered
Branch Manager | Review project profitability | Sec. 9.6 Branch Management | ✔ Covered

## Role Alignment Matrix
SOP Title | Category | Accounting | Branch Manager | Estimator | Field Supervisor | Foreman | General Superintendent | Prefabrication Lead | Project Coordinator | Project Manager | Purchasing | Quality Inspector | Safety Coordinator | Site Administrator | Subcontractors | Superintendent | ¦ Assistant PM/Project Coordinator | ¦ Branch Manager | ¦ Business Development | ¦ Client/Owner | ¦ Commissioning Agent | ¦ Electrical Subcontractor | ¦ Executive Committee | ¦ Field Leadership | ¦ Field Supervisor | ¦ Foreman | ¦ Foreman/Journeyman | ¦ General Superintendent | ¦ Operations Manager | ¦ Project Engineer/APM | ¦ Project Manager | ¦ Purchasing | ¦ Quality/QA-QC | ¦ Safety Coordinator | ¦ Site Administrator | ¦ Subcontractors
9.1.050 – Prepare Construction Takeoff | General | [8 empty] | R
9.2.005 – Review Contract for High Risk Clauses | Scope and contract review | [8 empty] | A
9.2.010 – Team Selection | Team selection and turnover |  | A |  |  |  | C | I | I | R | I |  | C
9.2.015 – Project Turnover Meeting | Team selection and turnover | [8 empty] | A
9.2.020 – Procurement of Large Feeder Wire | Procurement planning | [8 empty] | A | R
9.2.030 – Review Contract for Unfavorable or High-Risk Clauses | Scope and contract review | [8 empty] | A
9.2.040 – Project Manager Reviews Plans Specifications & Schedule | Scheduling | [8 empty] | R | [5 empty] | C
9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | Scheduling | [8 empty] | R | [5 empty] | C
9.2.055 – Compare Estimated vs Planned Performance | Preconstruction planning |  |  | C | [5 empty] | A
9.2.057 – Identify VE and Prefabrication Opportunities | Preconstruction planning | [6 empty] | R |  | A
9.2.060 – Create Issue List and Begin RFI Process | Preconstruction planning | [15 empty] | R | [7 empty] | C |  |  | C |  |  | A
9.2.070 – Conduct Site Visit | Preconstruction planning | [22 empty] | R |  |  |  | C |  |  | A |  |  | R
9.2.080 – Prepare Material Handling Plan | Procurement planning | [8 empty] | A
9.2.090 – Develop Labor Budget | Budgeting | C | [7 empty] | A
9.2.100 – Prepare Layout & Sequencing Plan | Preconstruction planning | [8 empty] | A
9.2.110 – Develop Project Schedule | Scheduling | [8 empty] | A | [5 empty] | C
9.2.120 – Establish Tracking & Control Systems | Preconstruction planning | [8 empty] | A
9.2.130 – Construction Execution Kickoff Meeting | Preconstruction planning | [8 empty] | R
9.2.140 – Develop Project Budget | Budgeting | C | [7 empty] | A
9.2.160 – Develop Procurement Plan | Procurement planning | [8 empty] | A | R
9.3.010 – Setup Office Trailer | Site mobilization | [23 empty] | R |  |  | C |  |  | A |  |  | C | R
9.3.020 – Setup Storage Trailer | Site mobilization | [23 empty] | A | R | [5 empty] | C |  | C
9.3.030 – Setup Site Fencing and Access Control | Site mobilization | [23 empty] | A | R |  |  |  |  | C |  |  | R
9.3.040 – Setup Temporary Power | Site mobilization | [20 empty] | R |  |  | A |  | R |  |  |  | C |  |  | C
9.3.050 – Setup Temporary Water | Site mobilization |  |  |  | R |  |  |  |  | R
9.3.060 – Setup Sanitary Facilities | Site mobilization |  |  |  | R |  |  |  |  | R
9.3.070 – Setup Temporary Lighting | Site mobilization |  |  |  | R |  |  |  |  | R
9.3.080 – Setup Signage | Site mobilization |  |  |  | R |  |  |  |  | R
9.3.090 – Setup Security | Site mobilization |  |  |  | R |  |  |  |  | R
9.3.100 – Setup Laydown Area | Site mobilization |  |  |  | R |  |  |  |  | R
9.3.110 – Setup Equipment Staging | Site mobilization |  |  |  | R |  |  |  |  | R
9.3.120 – Setup Parking | Site mobilization |  |  |  | R |  |  |  |  | R
9.3.470 – Develop Site-Specific Safety Plan | Safety setup |  |  |  | C |  |  |  |  | R |  |  | C
9.4.010 – Conduct Coordination Meetings | Coordination |  |  |  | C |  |  |  |  | R
9.4.020 – Conduct Subcontractor Coordination Meetings | Coordination |  |  |  | C |  |  |  |  | R |  |  |  |  | R
9.4.030 – Conduct Client/Owner Meetings | Coordination |  | C |  | C |  |  |  |  | A
9.4.040 – Conduct Safety Meetings | Safety management |  |  |  | C |  |  |  |  | A |  |  | R
9.4.045 – Identify Value Engineering & Prefabrication Opportunities | Execution |  |  |  | C |  |  | R |  | A
9.4.050 – Conduct Prefabrication Coordination Meetings | Coordination |  |  |  | C |  |  | R |  | R
9.4.055 – Procurement of Large Feeder Wire | Procurement execution |  |  |  | C |  |  |  |  | A | R
9.4.060 – Conduct Quality Meetings | Quality management |  |  |  | C |  |  |  |  | A |  | R
9.4.190 – Document Filing Standards | Document management |  |  |  | C |  |  |  |  | A |  |  |  | R
9.4.195 – Manage Project Documentation System | Document management |  |  |  | C |  |  |  |  | A |  |  |  | R
9.4.200 – Manage Submittals | Document management |  |  |  | C |  |  |  |  | R
9.4.205 – Manage RFIs (Requests for Information) | Document management |  |  |  | C |  |  |  |  | R
9.4.210 – Manage Meeting Minutes | Coordination |  |  |  | C |  |  |  |  | A |  |  |  | R
9.4.215 – Manage Daily Reports | Execution |  |  |  | R |  |  |  |  | A
9.4.220 – Manage Drawing Logs | Execution |  |  |  | C |  |  |  |  | R
9.4.225 – Manage Specifications | Execution |  |  |  | C |  |  |  |  | R
9.4.230 – Manage Correspondence | Execution |  |  |  | C |  |  |  |  | A |  |  |  | R
9.4.235 – Manage Permits | Execution |  |  |  | C |  |  |  |  | A
9.4.240 – Manage Inspection Reports | Execution |  |  |  | C |  |  |  |  | A
9.4.270 – Manage Project Communications | Communications |  |  |  | C |  |  |  |  | R
9.4.275 – Manage Internal Communications | Communications |  |  |  | C |  |  |  |  | R
9.4.280 – Manage External Communications | Communications |  |  |  | C |  |  |  |  | R
9.4.285 – Manage Client/Owner Communications | Communications |  | C |  | C |  |  |  |  | R
9.4.290 – Manage Subcontractor Communications | Communications |  |  |  | C |  |  |  |  | R |  |  |  |  | R
9.4.295 – Manage Vendor Supplier Communications | Communications |  |  |  | C |  |  |  |  | R | R
9.4.300 – Manage Architect/Engineer Communications | Communications |  |  |  | C |  |  |  |  | R
9.4.305 – Manage Regulatory/Authority Communications | Communications |  |  |  | C |  |  |  |  | R
9.4.310 – Manage General Contractor Communications | Communications |  |  |  | C |  |  |  |  | R
9.4.315 – Develop Project Schedule | Schedule management |  |  |  | C |  |  |  |  | A | [5 empty] | C
9.4.320 – Update Project Schedule | Schedule management |  |  |  | C |  |  |  |  | A | [5 empty] | C
9.4.325 – Monitor Schedule Performance | Schedule management |  |  |  | C |  |  |  |  | A | [5 empty] | C
9.4.330 – Develop Schedule Recovery Plans | Schedule management |  |  |  | C |  |  |  |  | A | [5 empty] | C
9.4.335 – Prepare Lookahead Schedules | Schedule management |  |  |  | C |  |  |  |  | A | [5 empty] | C
9.4.340 – Manage Resource-Loaded Schedules | Schedule management |  |  |  | C |  |  |  |  | A | [5 empty] | C
9.4.345 – Conduct Schedule Review Meetings | Schedule management |  |  |  | C |  |  |  |  | A | [5 empty] | C
9.4.350 – Manage Schedule Change Requests | Schedule management |  |  |  | C |  |  |  |  | A | [5 empty] | C
9.4.355 – Manage Project Scope | Scope management |  |  |  | C |  |  |  |  | R
9.4.360 – Manage Change Orders | Scope management |  |  |  | C |  |  |  |  | R
9.4.365 – Manage Potential Change Orders (PCOs) | Scope management |  |  |  | C |  |  |  |  | R
9.4.370 – Manage Owner Directives | Execution |  | C |  | C |  |  |  |  | A
9.4.375 – Manage Scope Clarifications | Scope management |  |  |  | C |  |  |  |  | R
9.4.380 – Manage Backcharges | Execution |  |  |  | C |  |  |  |  | R
9.4.385 – Manage Force Account Work | Execution |  |  |  | C |  |  |  |  | R
9.4.390 – Manage Claims | Execution |  | A |  | C |  |  |  |  | A
9.4.400 – Monitor Project Costs | Cost management | C |  |  | C |  |  |  |  | A
9.4.405 – Manage Cost Forecasts | Cost management | C |  |  | C |  |  |  |  | A
9.4.410 – Manage Cost Codes | Cost management | R |  |  | C |  |  |  |  | A
9.4.415 – Manage Committed Costs | Cost management | C |  |  | C |  |  |  |  | A
9.4.420 – Manage Actual Costs | Cost management | C |  |  | C |  |  |  |  | A
9.4.425 – Manage Job Cost Reports | Cost management | R |  |  | C |  |  |  |  | A
9.4.430 – Manage Profit Projections | Execution | C |  |  | C |  |  |  |  | A
9.4.435 – Manage Cost-to-Complete | Cost management | C |  |  | C |  |  |  |  | A
9.4.440 – Prepare Billing Schedule | Schedule management | R |  |  | C |  |  |  |  | A | [5 empty] | C
9.4.445 – Prepare Monthly Pay Applications | Execution | R |  |  | C |  |  |  |  | A
9.4.450 – Track Accounts Receivable | Execution | R |  |  | C |  |  |  |  | A
9.4.455 – Manage Lien Waivers | Execution |  |  |  | C |  |  |  |  | A
9.4.460 – Manage Retainage | Execution | R |  |  | C |  |  |  |  | A
9.4.465 – Manage Final Invoicing | Execution |  |  |  | C |  |  |  |  | A
9.4.475 – Conduct Safety Orientation | Safety management |  |  |  | C |  |  |  |  | A |  |  | R
9.4.480 – Conduct Safety Inspections | Safety management |  |  |  | C |  |  |  |  | A |  |  | R
9.4.485 – Conduct Safety Meetings | Safety management |  |  |  | C |  |  |  |  | A |  |  | R
9.4.490 – Report Safety Incidents | Safety management |  |  |  | C |  |  |  |  | A |  |  | R
9.4.495 – Investigate Accidents | Execution |  |  |  | C |  |  |  |  | A |  |  | R
9.4.500 – Conduct Emergency Preparedness | Execution |  |  |  | C |  |  |  |  | A |  |  | R
9.4.505 – Conduct Safety Compliance Audits | Safety management |  |  |  | C |  |  |  |  | A |  |  | C
9.4.510 – Provide Safety Training | Safety management |  |  |  | C |  |  |  |  | A |  |  | C
9.4.515 – Develop Quality Management Plan | Quality management |  |  |  | C |  |  |  |  | A |  | R
9.4.520 – Conduct Quality Meetings | Quality management |  |  |  | C |  |  |  |  | A |  | R
9.4.525 – Conduct Quality Inspections | Quality management |  |  |  | C |  |  |  |  | A |  | R
9.4.530 – Manage Quality Testing | Quality management |  |  |  | C |  |  |  |  | A |  | C
9.4.535 – Manage Nonconformance Reports (NCRs) | Execution |  |  |  | C |  |  |  |  | A |  | R
9.4.540 – Manage Quality Records | Quality management |  |  |  | C |  |  |  |  | A |  | C
9.4.545 – Manage Punch List Quality | Quality management |  |  |  | C |  |  |  |  | A |  | C
9.4.560 – Manage Manpower Allocation | Resource management |  |  |  | R |  |  |  |  | A
9.4.565 – Manage Equipment Allocation | Execution |  |  |  | C |  |  |  |  | A
9.4.570 – Manage Material Allocation | Execution |  |  |  | C |  |  |  |  | A
9.4.576 – Manage Subcontractor Resources | Resource management |  |  |  | C |  |  |  |  | A |  |  |  |  | R
9.4.580 – Manage Vendor Resources | Procurement execution |  |  |  | C |  |  |  |  | A | R
9.4.585 – Plan Prefabrication Resources | Resource management |  |  |  | C |  |  | R |  | A
9.4.590 – Manage Specialty Contractor Resources | Resource management |  |  |  | C |  |  |  |  | A
9.4.595 – Prepare Resource Reports | Resource management |  |  |  | C |  |  |  |  | A
9.4.605 – Issue Purchase Orders | Procurement execution |  |  |  | C |  |  |  |  | A | R
9.4.610 – Manage Vendor Prequalification | Procurement execution |  |  |  | C |  |  |  |  | A | R
9.4.615 – Manage Vendor Evaluations | Procurement execution |  |  |  | C |  |  |  |  | A | R
9.4.620 – Manage Expediting | Execution |  |  |  | C |  |  |  |  | A | R
9.4.625 – Manage Delivery Tracking | Execution |  |  |  | C |  |  |  |  | A | R
9.4.630 – Manage Material Receiving | Execution |  |  |  | C |  |  |  |  | A | R
9.4.631 – Release of Large Feeder Wire | Execution |  |  |  | C |  |  |  |  | A
9.4.635 – Manage Material Inspection | Execution |  |  |  | C |  |  |  |  | A
9.4.640 – Manage Storage and Logistics | Execution |  |  |  | C |  |  |  |  | A
9.4.645 – Manage Material Handling | Execution |  |  |  | C |  |  |  |  | A
9.4.650 – Manage Inventory | Execution |  |  |  | C |  |  |  |  | A | R
9.4.655 – Prepare Procurement Reports | Procurement execution |  |  |  | C |  |  |  |  | A | R
9.4.660 – Manage Procurement Closeout | Procurement execution |  |  |  | C |  |  |  |  | A | R
9.4.665 – Reconcile Procurement Accounts | Procurement execution | R |  |  | C |  |  |  |  | A | R
9.4.670 – Manage Vendor Closeout | Procurement execution |  |  |  | C |  |  |  |  | A | R
9.4.675 – Conduct Daily Huddles | Execution |  |  |  | C | R |  |  |  | A
9.4.680 – Conduct Weekly Foreman Meetings | Coordination |  |  |  | C | R |  |  |  | A
9.4.690 – Track Manpower Utilization | Resource management |  |  |  | R |  |  |  |  | A
9.4.695 – Track Production Quantities | Field operations |  |  |  | R |  |  |  |  | A
9.4.700 – Track Equipment Utilization | Execution |  |  |  | C |  |  |  |  | A
9.4.705 – Manage Work Packaging | Execution |  |  |  | C |  |  |  |  | A
9.4.710 – Manage Workface Planning | Execution |  |  |  | C |  |  |  |  | A
9.4.715 – Manage Field Coordination | Coordination |  |  |  | R |  |  |  |  | A
9.4.720 – Conduct Productivity Analysis | Execution |  |  |  | C |  |  |  |  | A
9.4.725 – Resolve Field Problems | Field operations |  |  |  | R |  |  |  |  | A
9.4.735 – Perform Field Quality Verifications | Quality management |  |  |  | C |  |  |  |  | A |  | C
9.4.745 – Manage Field Rework | Field operations |  |  |  | R |  |  |  |  | A
9.4.755 – Implement Field Productivity Improvements | Field operations |  |  |  | C |  |  |  |  | A
9.5.020 – Handling and/or Disposing of Excess Materials | Commissioning | [19 empty] | R |  |  |  | R | [5 empty] | A |  | C |  |  | R
9.5.550 – Manage Commissioning Activities | Commissioning | [19 empty] | R |  |  |  | R | [5 empty] | A |  | R |  |  | R
9.6.005 – Prepare for Turnover (Field Perspective) | Project closeout | [8 empty] | A
9.6.010 – Conduct Closeout Meetings | Project closeout | [18 empty] | I |  |  |  |  | R | [5 empty] | A |  |  |  |  | R
9.6.015 – Manage Project Turnover Documentation | Project closeout | [8 empty] | A
9.6.020 – Manage Punch List Closeout | Project closeout | [8 empty] | A |  | C
9.6.030 – Manage As-Built Drawings | Project closeout | [23 empty] | R | R |  |  |  | R | A
9.6.035 – Submit Warranties | Project closeout | [8 empty] | A
9.6.040 – Submit O&M Manuals | Project closeout | [8 empty] | A
9.6.050 – Provide Owner Training | Project closeout |  | C | [6 empty] | A
9.6.065 – Archive Project Documentation | Project closeout | [8 empty] | A |  |  |  | R
9.6.070 – Conduct Post-Project Review | Project closeout | [16 empty] | A | [6 empty] | R |  |  |  | C |  | R
9.6.080 – Capture Client Feedback | Project closeout | [16 empty] | A | C |  |  |  | I | [7 empty] | R
9.6.085 – Document Lessons Learned | Project closeout | [16 empty] | C | [6 empty] | R |  |  |  | A |  | R

## SOP Number Crosswalk
Legacy SOP # | New SOP # | Title | SOP Title | Notes
9.41.745 | 9.4.745 | Manage Field Rework | Manage Field Rework | Legacy-to-current crosswalk entry
9.41.190A | 9.4.190 | Document Filing Standards | Document Filing Standards | Legacy-to-current crosswalk entry
9.41.035 | 9.2.070 | Conduct Site Visit | Conduct Site Visit | Legacy-to-current crosswalk entry
9.41.040 | 9.2.055 | Compare Estimated vs. Planned Performance | Compare Est. vs. Planned | Legacy-to-current crosswalk entry
9.41.050 | 9.2.057 | Identify VE and Prefab Opportunities | Identify VE and Prefabrication Opportunities | Legacy-to-current crosswalk entry
9.41.060 | 9.2.060 | Create Issue List and Begin RFI Process | Create Issue List and Begin RFI Process | Legacy-to-current crosswalk entry

## Change_Log
Timestamp | Sheet | Change Type | Details
2026-01-19T16:14:24 | GSL_SOP_Metadata | Create | Generated 156 SOP metadata entries
2026-01-19T16:14:24 | GSL_SOP_Metadata | Status Fix | Set all Status fields to 'Approved'
2026-01-19T16:14:24 | GSL_SOP_Metadata | Add Descriptions | Added descriptions from SOP_Descriptions_Full.csv
2026-01-19T16:14:24 | Coverage Matrix | Create | Generated 406 coverage entries
2026-01-19T16:14:24 | RACI Matrix | Create | Generated 406 RACI entries
2026-01-19T16:14:24 | Redline Recs | Create | Generated 343 gap entries for review
2026-01-19T16:14:24 | Conflict Matrix | Create | Generated 14 conflict entries
2026-01-19T16:14:24 | Closeout Checklist | Create | Generated 23 closeout tasks
2026-01-19T16:14:24 | Role Alignment Matrix | Create | Generated alignment for 35 roles
2026-01-19T16:14:24 | SOP Number Crosswalk | Create | Added 6 crosswalk entries

## Mapping_Log
Sheet | SOP Title | Source Action | Mapped Action | Role | Source Version | Match Score
RACI Matrix | 9.1.050 – Prepare Construction Takeoff | No explicit RACI in document | Oversees Prepare Construction Takeoff | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.005 – Review Contract for High Risk Clauses | No explicit RACI in document | Oversees Review Contract for High Risk Clauses | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.015 – Project Turnover Meeting | No explicit RACI in document | Oversees closeout for Project Turnover Meeting | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.020 – Procurement of Large Feeder Wire | No explicit RACI in document | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Inferred | 0.8
RACI Matrix | 9.2.020 – Procurement of Large Feeder Wire | No explicit RACI in document | Oversees Procurement of Large Feeder Wire | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.030 – Review Contract for Unfavorable or High-Risk Clauses | No explicit RACI in document | Oversees Review Contract for Unfavorable or High-Risk Clauses | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.040 – Project Manager Reviews Plans Specifications & Schedule | No explicit RACI in document | Coordinates scheduling for Project Manager Reviews Plans Specifications & Schedule | Superintendent | Inferred | 0.8
RACI Matrix | 9.2.040 – Project Manager Reviews Plans Specifications & Schedule | No explicit RACI in document | Manages technical documentation for Project Manager Reviews Plans Specifications & Schedule | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | No explicit RACI in document | Coordinates scheduling for Field Supervisor Reviews Plans Specifications & Schedule | Superintendent | Inferred | 0.8
RACI Matrix | 9.2.050 – Field Supervisor Reviews Plans Specifications & Schedule | No explicit RACI in document | Manages technical documentation for Field Supervisor Reviews Plans Specifications & Schedule | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.055 – Compare Estimated vs Planned Performance | No explicit RACI in document | Provides estimating support for Compare Estimated vs Planned Performance | Estimator | Inferred | 0.8
RACI Matrix | 9.2.055 – Compare Estimated vs Planned Performance | No explicit RACI in document | Oversees Compare Estimated vs Planned Performance | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.057 – Identify VE and Prefabrication Opportunities | No explicit RACI in document | Coordinates prefabrication for Identify VE and Prefabrication Opportunities | Prefabrication Lead | Inferred | 0.8
RACI Matrix | 9.2.057 – Identify VE and Prefabrication Opportunities | No explicit RACI in document | Oversees Identify VE and Prefabrication Opportunities | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.080 – Prepare Material Handling Plan | No explicit RACI in document | Oversees Prepare Material Handling Plan | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.090 – Develop Labor Budget | No explicit RACI in document | Provides financial support for Develop Labor Budget | Accounting | Inferred | 0.8
RACI Matrix | 9.2.090 – Develop Labor Budget | No explicit RACI in document | Oversees Develop Labor Budget | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.100 – Prepare Layout & Sequencing Plan | No explicit RACI in document | Oversees Prepare Layout & Sequencing Plan | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.110 – Develop Project Schedule | No explicit RACI in document | Coordinates scheduling for Develop Project Schedule | Superintendent | Inferred | 0.8
RACI Matrix | 9.2.110 – Develop Project Schedule | No explicit RACI in document | Oversees Develop Project Schedule | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.120 – Establish Tracking & Control Systems | No explicit RACI in document | Oversees Establish Tracking & Control Systems | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.130 – Construction Execution Kickoff Meeting | No explicit RACI in document | Leads coordination for Construction Execution Kickoff Meeting | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.140 – Develop Project Budget | No explicit RACI in document | Provides financial support for Develop Project Budget | Accounting | Inferred | 0.8
RACI Matrix | 9.2.140 – Develop Project Budget | No explicit RACI in document | Oversees Develop Project Budget | Project Manager | Inferred | 0.8
RACI Matrix | 9.2.160 – Develop Procurement Plan | No explicit RACI in document | Manages procurement for Develop Procurement Plan | Purchasing | Inferred | 0.8
RACI Matrix | 9.2.160 – Develop Procurement Plan | No explicit RACI in document | Oversees Develop Procurement Plan | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.050 – Setup Temporary Water | No explicit RACI in document | Coordinates site setup for Setup Temporary Water | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.3.050 – Setup Temporary Water | No explicit RACI in document | Oversees Setup Temporary Water | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.060 – Setup Sanitary Facilities | No explicit RACI in document | Coordinates site setup for Setup Sanitary Facilities | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.3.060 – Setup Sanitary Facilities | No explicit RACI in document | Oversees Setup Sanitary Facilities | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.070 – Setup Temporary Lighting | No explicit RACI in document | Coordinates site setup for Setup Temporary Lighting | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.3.070 – Setup Temporary Lighting | No explicit RACI in document | Oversees Setup Temporary Lighting | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.080 – Setup Signage | No explicit RACI in document | Coordinates site setup for Setup Signage | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.3.080 – Setup Signage | No explicit RACI in document | Oversees Setup Signage | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.090 – Setup Security | No explicit RACI in document | Coordinates site setup for Setup Security | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.3.090 – Setup Security | No explicit RACI in document | Oversees Setup Security | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.100 – Setup Laydown Area | No explicit RACI in document | Coordinates site setup for Setup Laydown Area | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.3.100 – Setup Laydown Area | No explicit RACI in document | Oversees Setup Laydown Area | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.110 – Setup Equipment Staging | No explicit RACI in document | Coordinates site setup for Setup Equipment Staging | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.3.110 – Setup Equipment Staging | No explicit RACI in document | Oversees Setup Equipment Staging | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.120 – Setup Parking | No explicit RACI in document | Coordinates site setup for Setup Parking | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.3.120 – Setup Parking | No explicit RACI in document | Oversees Setup Parking | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.470 – Develop Site-Specific Safety Plan | No explicit RACI in document | Reviews for safety compliance for Develop Site-Specific Safety Plan | Safety Coordinator | Inferred | 0.8
RACI Matrix | 9.3.470 – Develop Site-Specific Safety Plan | No explicit RACI in document | Oversees Develop Site-Specific Safety Plan | Project Manager | Inferred | 0.8
RACI Matrix | 9.3.470 – Develop Site-Specific Safety Plan | No explicit RACI in document | Field coordination for Develop Site-Specific Safety Plan | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.4.010 – Conduct Coordination Meetings | No explicit RACI in document | Leads coordination for Conduct Coordination Meetings | Project Manager | Inferred | 0.8
RACI Matrix | 9.4.010 – Conduct Coordination Meetings | No explicit RACI in document | Field coordination for Conduct Coordination Meetings | Field Supervisor | Inferred | 0.8
RACI Matrix | 9.4.020 – Conduct Subcontractor Coordination Meetings | No explicit RACI in document | Performs subcontracted work for Conduct Subcontractor Coordination Meetings | Subcontractors | Inferred | 0.8
RACI Matrix | 9.4.020 – Conduct Subcontractor Coordination Meetings | No explicit RACI in document | Leads coordination for Conduct Subcontractor Coordination Meetings | Project Manager | Inferred | 0.8
RACI Matrix | 9.4.020 – Conduct Subcontractor Coordination Meetings | No explicit RACI in document | Field coordination for Conduct Subcontractor Coordination Meetings | Field Supervisor | Inferred | 0.8