## GSL_SOP_Metadata
SOP ID | Name | SOP File Name | Title | Description | Phase | Category | Roles (RACI) | Discipline | Status | Document Type
9.1.050 | 9.1.050 - Prepare Construction Takeoff | 9.1.050 – Prepare Construction Takeoff.docx | Prepare Construction Takeoff | To prepare a detailed construction takeoff that validates estimated quantities and provides the basis for procurement, labor budgeting, and execution planning. Scope This SOP applies to Project Managers and Estimators for all awarded projects be... | 1 - Estimating | Estimating | [Inferred] Project Manager (R) | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.055 – Procurement of Large Feeder Wire Reference: GSL Pre-Construction Planning – Construction Takeoff | Approved | SOP
9.2.005 | 9.2.005 - Review Contract for High Risk Clauses | 9.2.005 – Review Contract for High Risk Clauses.docx | Review Contract for High Risk Clauses | To establish a standardized process for reviewing contract terms to identify unfavorable or high-risk clauses before baseline planning begins, ensuring proper risk mitigation and approval protocols are in place. SCOPE Applies to all projects / sit... | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Branch Management | Approved | SOP
9.2.010 | 9.2.010 - Team Selection | 9.2.010 – Team Selection.docx | Team Selection | To establish a standardized process for selecting and assembling the project team immediately after project award, ensuring the right mix of skills, experience, and availability to meet project requirements. SCOPE Applies to all projects / situati... | 2 - Preconstruction | Preconstruction | Branch Manager (A); Project Manager (R); General Superintendent (C); Safety Coordinator (C); Purchasing (I); Prefabrication Lead (I); Project Coordinator (I) | Project Management / Operations | Approved | SOP
9.2.015 | 9.2.015 - Project Turnover Meeting | 9.2.015 – Project Turnover Meeting.docx | Project Turnover Meeting | To ensure a consistent and documented turnover process for newly awarded projects using a standardized Smartsheet agenda to guide communication, task planning, and team alignment. Scope This SOP applies to all projects awarded through GSL's esti... | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.2 Related SOPs: | Approved | SOP
9.2.020 | 9.2.020 - Procurement of Large Feeder Wire | 9.2.020 – Procurement of Large Feeder Wire.docx | Procurement of Large Feeder Wire | To define the standardized process for the planning, procurement, and delivery of large feeder wire to ensure that project cost, schedule, and quality targets are achieved in accordance with GSL Electric’s Management Directives. 2. | 2 - Preconstruction | Preconstruction | [Inferred] Purchasing (R); Project Manager (A) | Operations | Approved | SOP
9.2.030 | 9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | 9.2.030 – Review Contract for Unfavorable or High Risk Clauses.docx | Review Contract for Unfavorable or High-Risk Clauses | To ensure all project contracts are reviewed systematically for unfavorable or high-risk clauses that could affect project execution, budget, or liability, and to define mitigation measures prior to mobilization. Scope This SOP applies to all Pr... | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Pre-Construction Created by: Schachinger Solutions GmbH Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Contract Review | Approved | SOP
9.2.040 | 9.2.040 - Project Manager Reviews Plans Specifications & Schedule | 9.2.040 – Project Manager Reviews Plans, Specifications & Schedule.docx | Project Manager Reviews Plans Specifications & Schedule | To ensure that the Project Manager conducts a detailed review of project drawings, specifications, and schedules to confirm alignment with contract requirements and identify risks before mobilization. Scope This SOP applies to all Project Manage... | 2 - Preconstruction | Preconstruction | [Inferred] Superintendent (C); Project Manager (R) | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable or High-Risk Clauses; 9.41.025 – Field Supervisor Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Scope & Schedule Review | Approved | SOP
9.2.050 | 9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | 9.2.050 – Field Supervisor Reviews Plans, Specifications & Schedule.docx | Field Supervisor Reviews Plans Specifications & Schedule | To ensure Field Supervisors conduct a detailed review of project drawings, specifications, and schedules with a focus on constructability, sequencing, and field logistics, supporting accurate execution planning. Scope This SOP applies to Field S... | 2 - Preconstruction | Preconstruction | [Inferred] Superintendent (C); Project Manager (R) | Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process Reference: GSL Pre-Construction Planning – Scope & Schedule Review | Approved | SOP
9.2.055 | 9.2.055 - Compare Estimated vs Planned Performance | 9.2.055 – Compare Estimated vs Planned Performance.docx | Compare Estimated vs Planned Performance | To confirm that bid assumptions for labor, materials, and productivity align with the planned project execution strategy, ensuring accurate budgets and realistic performance goals. Scope This SOP applies to Project Managers and Estimators during... | 2 - Preconstruction | Preconstruction | [Inferred] Estimator (C); Project Manager (A) | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.045 – Identify Value Engineering & Prefabrication Opportunities Reference: GSL Pre-Construction Planning – Bid vs. Execution Review | Approved | SOP
9.2.057 | 9.2.057 - Identify VE and Prefabrication Opportunities | 9.2.057 – Identify VE and Prefabrication Opportunities.docx | Identify VE and Prefabrication Opportunities | To define the process for identifying, developing, and documenting the project’s prefabrication strategy, allowing for improved planning, efficiency, and field execution through the use of off-site construction. Scope Applies to all projects wit... | 2 - Preconstruction | Preconstruction | [Inferred] Prefabrication Lead (R); Project Manager (A) | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.060 | 9.2.060 - Create Issue List and Begin RFI Process | 9.2.060 – Create Issue List and Begin RFI Process.docx | Create Issue List and Begin RFI Process | To establish a standardized process for documenting project issues identified during pre-construction review and initiating the Request for Information (RFI) process to resolve them befo... | 2 - Preconstruction | Preconstruction | ¦ Project Manager (A); ¦ Assistant PM/Project Coordinator (R); ¦ Field Supervisor (C); ¦ General Superintendent (C) | Project Management | Approved | SOP
9.2.070 | 9.2.070 - Conduct Site Visit | 9.2.070 – Conduct Site Visit.docx | Conduct Site Visit | To establish a standardized process for conducting pre-construction site visits to assess existing conditions, identify logistical requirements, and validate planning assumptions before ... | 2 - Preconstruction | Preconstruction | ¦ Project Manager (A); ¦ Field Leadership (R); ¦ Safety Coordinator (R); ¦ General Superintendent (C) | Project Management / Field Operations | Approved | SOP
9.2.080 | 9.2.080 - Prepare Material Handling Plan | 9.2.080 – Prepare Material Handling Plan.docx | Prepare Material Handling Plan | To define the process for creating a job-specific Material Handling Plan that ensures efficient, safe, and cost-effective delivery, storage, movement, and installation of materials on-site. Scope Applies to all projects requiring material moveme... | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.090 | 9.2.090 - Develop Labor Budget | 9.2.090 – Develop Labor Budget.docx | Develop Labor Budget | To establish a standardized process for creating a project-specific labor budget that reflects estimated manhours by phase and supports resource planning, cost tracking, and productivity measurement. Scope Applies to all awarded projects and mus... | 2 - Preconstruction | Preconstruction | [Inferred] Accounting (C); Project Manager (A) | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.100 | 9.2.100 - Prepare Layout & Sequencing Plan | 9.2.100 – Prepare Layout & Sequencing Plan.docx | Prepare Layout & Sequencing Plan | To establish a coordinated layout and sequencing plan that supports efficient installation, minimizes trade conflicts, and ensures project milestones are achieved. Scope This SOP applies to Project Managers, Field Supervisors, and General Superi... | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.065 – Develop Labor Budget; 9.41.075 – Develop Project Schedule Reference: GSL Pre-Construction Planning – Layout & Sequencing | Approved | SOP
9.2.110 | 9.2.110 - Develop Project Schedule | 9.2.110 – Develop Project Schedule.docx | Develop Project Schedule | To outline the process for developing a complete project schedule that aligns field activities, procurement, prefab, and inspections to meet project milestones and client expectations. Scope Applies to all awarded projects prior to mobilization. | 2 - Preconstruction | Preconstruction | [Inferred] Superintendent (C); Project Manager (A) | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.120 | 9.2.120 - Establish Tracking & Control Systems | 9.2.120 – Establish Tracking & Control Systems.docx | Establish Tracking & Control Systems | To implement standardized systems for monitoring labor, materials, procurement, safety, and project performance, enabling accurate reporting and proactive management. Scope This SOP applies to Project Managers, Field Supervisors, Purchasing, and... | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (A) | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Pre-Construction Planning – Tracking & Control | Approved | SOP
9.2.130 | 9.2.130 - Construction Execution Kickoff Meeting | 9.2.130 – Construction Execution Kickoff Meeting.docx | Construction Execution Kickoff Meeting | To formally launch field construction by aligning the project team, reviewing key work plans, confirming roles, and addressing critical first-week activities before installation begins. Scope Applies to all projects immediately prior to the star... | 2 - Preconstruction | Preconstruction | [Inferred] Project Manager (R) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | Approved | SOP
9.2.140 | 9.2.140 - Develop Project Budget | 9.2.140 – Develop Project Budget.docx | Develop Project Budget | To establish a comprehensive project budget that reflects the contract value, cost codes, and anticipated expenses, serving as the baseline for cost control. Scope This SOP applies to Project Managers, Estimators, and Accounting. | 2 - Preconstruction | Preconstruction | [Inferred] Accounting (C); Project Manager (A) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.360 – Manage Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.2.160 | 9.2.160 - Develop Procurement Plan | 9.2.160 – Develop Procurement Plan.docx | Develop Procurement Plan | To prepare a procurement plan that identifies all major materials, equipment, and subcontracted services required for the project, including lead times and responsibilities. Scope This SOP applies to Project Managers, Estimators, and Purchasing. | 2 - Preconstruction | Preconstruction | [Inferred] Purchasing (R); Project Manager (A) | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.395 – Develop Project Budget; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.3.010 | 9.3.010 - Setup Office Trailer | 9.3.010 – Setup Office Trailer.docx | Setup Office Trailer | To establish a standardized process for setting up the project office trailer, ensuring proper placement, utilities, and functionality for project administration and team coordination. =... | 3 - Mobilization | Mobilization | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Site Administrator (R); ¦ Safety Coordinator (C); ¦ General Superintendent (C) | Project Management / Field Operations | Approved | SOP
9.3.020 | 9.3.020 - Setup Storage Trailer | 9.3.020 – Setup Storage Trailer.docx | Setup Storage Trailer | To establish a standardized process for setting up project storage trailers/containers, ensuring secure and organized storage for materials, tools, and equipment. =======================... | 3 - Mobilization | Mobilization | ¦ Field Supervisor (A); ¦ Foreman (R); ¦ Purchasing (C); ¦ Safety Coordinator (C) | Field Operations | Approved | SOP
9.3.030 | 9.3.030 - Setup Site Fencing and Access Control | 9.3.030 – Setup Site Fencing and Access Control.docx | Setup Site Fencing and Access Control | To establish a standardized process for installing site fencing and access control measures, ensuring site security and controlled entry/exit for personnel and deliveries. ==============... | 3 - Mobilization | Mobilization | ¦ Field Supervisor (A); ¦ Foreman (R); ¦ Safety Coordinator (R); ¦ Project Manager (C) | Field Operations / Safety | Approved | SOP
9.3.040 | 9.3.040 - Setup Temporary Power | 9.3.040 – Setup Temporary Power.docx | Setup Temporary Power | To establish a standardized process for installing temporary electrical power distribution, ensuring safe and adequate power for construction operations, trailers, and equipment. =======... | 3 - Mobilization | Mobilization | ¦ Field Supervisor (A); ¦ Foreman/Journeyman (R); ¦ Safety Coordinator (C); ¦ Project Manager (C); ¦ Electrical Subcontractor (R) | Field Operations | Approved | SOP
9.3.050 | 9.3.050 - Setup Temporary Water | 9.3.050 – Setup Temporary Water.docx | Setup Temporary Water | To provide safe, reliable temporary water supply for construction use, including dust control, concrete work, cleaning, and sanitary needs. Scope This SOP applies to Project Managers and Field Supervisors during mobilization and throughout proje... | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.060 | 9.3.060 - Setup Sanitary Facilities | 9.3.060 – Setup Sanitary Facilities.docx | Setup Sanitary Facilities | To provide adequate sanitary facilities (toilets, wash stations) for workers in compliance with OSHA requirements and project specifications. Scope This SOP applies to Project Managers and Safety Coordinators during site mobilization and through... | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer; 9.41.110 – Setup Temporary Water Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.070 | 9.3.070 - Setup Temporary Lighting | 9.3.070 – Setup Temporary Lighting.docx | Setup Temporary Lighting | To provide adequate temporary lighting for safety, security, and productivity during construction. Scope This SOP applies to Project Managers, Field Supervisors, and Safety Coordinators during mobilization and project execution. | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.105 – Setup Temporary Power; 9.41.110 – Setup Temporary Water; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.080 | 9.3.080 - Setup Signage | 9.3.080 – Setup Signage.docx | Setup Signage | To install signage that provides safety information, site identification, and directional guidance for workers, visitors, and the public. Scope This SOP applies to Project Managers, Field Supervisors, and Safety Coordinators during mobilization. | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.090 | 9.3.090 - Setup Security | 9.3.090 – Setup Security.docx | Setup Security | To establish security measures that protect personnel, equipment, and materials from theft, vandalism, and unauthorized access. Scope This SOP applies to Project Managers, Field Supervisors, and Safety Coordinators during mobilization and throug... | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.125 – Setup Signage Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.100 | 9.3.100 - Setup Laydown Area | 9.3.100 – Setup Laydown Area.docx | Setup Laydown Area | To establish a designated laydown area for material storage and staging to support efficient project operations and site safety. Scope This SOP applies to Project Managers and Field Supervisors during mobilization. | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.095 – Setup Storage Trailer; 9.41.100 – Setup Site Fencing and Access Control Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.110 | 9.3.110 - Setup Equipment Staging | 9.3.110 – Setup Equipment Staging.docx | Setup Equipment Staging | To establish designated areas for equipment staging, ensuring safe and efficient deployment of construction equipment. Scope This SOP applies to Project Managers, Field Supervisors, and Equipment Operators during mobilization. | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.120 | 9.3.120 - Setup Parking | 9.3.120 – Setup Parking.docx | Setup Parking | To designate and manage parking areas for workers, visitors, and deliveries, ensuring safety and minimizing disruption to site operations. Scope This SOP applies to Project Managers, Field Supervisors, and Safety Coordinators during mobilization. | 3 - Mobilization | Mobilization | [Inferred] Field Supervisor (R); Project Manager (R) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Mobilization | Approved | SOP
9.3.470 | 9.3.470 - Develop Site-Specific Safety Plan | 9.3.470 – Develop Site Specific Safety Plan.docx | Develop Site-Specific Safety Plan | To prepare and implement a site-specific safety plan (SSSP) that identifies hazards, compliance requirements, and procedures to protect workers and the public. Scope This SOP applies to Project Managers, Safety Coordinators, and Field Supervisors. | 3 - Mobilization | Mobilization | [Inferred] Safety Coordinator (C); Project Manager (R); Field Supervisor (C) | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.010 | 9.4.010 - Conduct Coordination Meetings | 9.4.010 – Conduct Coordination Meetings.docx | Conduct Coordination Meetings | To establish a standard process for conducting project coordination meetings to ensure alignment between all project stakeholders, resolve issues, and review progress. Scope This SOP applies to Project Managers, Field Supervisors, Subcontractors... | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Owner/GC Coordination Meetings; 9.41.170 – Conduct Progress Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.020 | 9.4.020 - Conduct Subcontractor Coordination Meetings | 9.4.020 – Conduct Subcontractor Coordination Meetings.docx | Conduct Subcontractor Coordination Meetings | To lead regular subcontractor coordination meetings to ensure subcontractor activities align with project schedule, logistics, and safety requirements. Scope This SOP applies to Project Managers, Field Supervisors, and all subcontractors assigne... | 4 - Execution | Execution | [Inferred] Subcontractors (R); Project Manager (R); Field Supervisor (C) | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.030 | 9.4.030 - Conduct Client/Owner Meetings | 9.4.030 – Conduct Client Owner Meetings.docx | Conduct Client/Owner Meetings | To conduct meetings with the client/owner to provide project updates, resolve issues, and ensure contractual and performance expectations are met. Scope This SOP applies to Project Managers, Branch Managers, and project teams when interfacing wi... | 4 - Execution | Execution | [Inferred] Branch Manager (C); Project Manager (A); Field Supervisor (C) | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable Clauses; 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.040 | 9.4.040 - Conduct Safety Meetings | 9.4.040 – Conduct Safety Meetings.docx | Conduct Safety Meetings | To conduct regular safety meetings to promote awareness, communicate hazards, and reinforce compliance with OSHA and GSL safety standards. Scope This SOP applies to Project Managers, Safety Coordinators, Field Supervisors, and all on-site person... | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.115 – Setup Sanitary Facilities; 9.41.120 – Setup Temporary Lighting Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.045 | 9.4.045 - Identify Value Engineering & Prefabrication Opportunities | 9.4.045 – Identify Value Engineering & Prefabrication Opportunities.docx | Identify Value Engineering & Prefabrication Opportunities | To identify and evaluate opportunities for value engineering (VE) and prefabrication to reduce cost, improve efficiency, and simplify work without compromising project scope or quality. Scope This SOP applies to Project Managers, Field Superviso... | 4 - Execution | Execution | [Inferred] Prefabrication Lead (R); Project Manager (A); Field Supervisor (C) | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.050 – Prepare Construction Takeoff Reference: GSL Pre-Construction Planning – Value Engineering & Prefabrication | Approved | SOP
9.4.050 | 9.4.050 - Conduct Prefabrication Coordination Meetings | 9.4.050 – Conduct Prefabrication Coordination Meetings.docx | Conduct Prefabrication Coordination Meetings | To coordinate with the prefabrication team to align prefab deliverables with the construction schedule, manpower plan, and site logistics. Scope This SOP applies to Project Managers, Prefab Leads, and Field Supervisors during pre-construction an... | 4 - Execution | Execution | [Inferred] Prefabrication Lead (R); Project Manager (R); Field Supervisor (C) | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.050 – Prepare Construction Takeoff; 9.41.065 – Develop Labor Budget Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.055 | 9.4.055 - Procurement of Large Feeder Wire | 9.4.055 – 1 Procurement of Large Feeder Wire.docx | Procurement of Large Feeder Wire | To define the standardized process for the planning, procurement, and delivery of large feeder wire to ensure that project cost, schedule, and quality targets are achieved in accordance with GSL Electric’s Management Directives. 2. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Operations | Approved | SOP
9.4.060 | 9.4.060 - Conduct Quality Meetings | 9.4.060 – Conduct Quality Meetings.docx | Conduct Quality Meetings | To conduct regular quality meetings to ensure project work meets specifications, client requirements, and GSL standards. Scope This SOP applies to Project Managers, Field Supervisors, Safety Coordinators, and Quality Inspectors during pre-constr... | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Project Management / Quality Control Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.080 – Establish Tracking & Control Systems Reference: GSL Project Manager Procedures – Coordination | Approved | SOP
9.4.190 | 9.4.190 - Document Filing Standards | 9.4.190 – A Document Filing Standards.docx | Document Filing Standards | To define standard filing responsibilities and locations for all project documentation to ensure consistency, accountability, and accessibility. Scope This SOP applies to all Project Managers, Field Foremen, Site Administrators, and Subcontracto... | 4 - Execution | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: All documentation-related SOPs (9.41.195 – 9.41.265 and beyond) Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.195 | 9.4.195 - Manage Project Documentation System | 9.4.195 – Manage Project Documentation System.docx | Manage Project Documentation System | To establish and maintain a structured documentation system that ensures all project records are organized, accessible, and compliant with contractual and legal requirements. Scope This SOP applies to Project Managers, Site Administrators, and F... | 4 - Execution | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.005 – Team Selection; 9.41.010 – Project Turnover Meeting; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.200 | 9.4.200 - Manage Submittals | 9.4.200 – Manage Submittals.docx | Manage Submittals | To establish a standard process for preparing, submitting, tracking, and closing out all project submittals to ensure compliance with specifications and schedule. Scope This SOP applies to Project Managers, Purchasing, and Subcontractors. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.050 – Prepare Construction Takeoff; 9.41.055 – Procurement of Large Feeder Wire; 9.41.075 – Develop Project Schedule; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.205 | 9.4.205 - Manage RFIs (Requests for Information) | 9.4.205 – Manage RF Is (Requests for Information).docx | Manage RFIs (Requests for Information) | To standardize the RFI process to ensure issues are documented, submitted, tracked, and resolved in a timely manner. Scope This SOP applies to Project Managers, Field Supervisors, and Subcontractors. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Pre-Construction Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.210 | 9.4.210 - Manage Meeting Minutes | 9.4.210 – Manage Meeting Minutes.docx | Manage Meeting Minutes | To standardize the recording, distribution, and archiving of meeting minutes to ensure accountability and continuity. Scope This SOP applies to Project Managers, Site Administrators, and meeting participants. | 4 - Execution | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Client/Owner Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.215 | 9.4.215 - Manage Daily Reports | 9.4.215 – Manage Daily Reports.docx | Manage Daily Reports | To document daily site conditions, manpower, equipment, progress, and incidents. Scope This SOP applies to Field Supervisors, Project Managers, and Safety Coordinators. | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.080 – Establish Tracking & Control Systems; 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.220 | 9.4.220 - Manage Drawing Logs | 9.4.220 – Manage Drawing Logs.docx | Manage Drawing Logs | To maintain an accurate and up-to-date drawing log, ensuring the field team works from the latest approved drawings. Scope This SOP applies to Project Managers, Site Administrators, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.225 | 9.4.225 - Manage Specifications | 9.4.225 – Manage Specifications.docx | Manage Specifications | To ensure specifications are properly logged, tracked, distributed, and accessible to all team members. Scope This SOP applies to Project Managers, Site Administrators, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.200 – Manage Submittals; 9.41.220 – Manage Drawing Logs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.230 | 9.4.230 - Manage Correspondence | 9.4.230 – Manage Correspondence.docx | Manage Correspondence | To log, track, and store all project-related correspondence for accountability and claims protection. Scope This SOP applies to Project Managers, Site Administrators, and Field Foremen. | 4 - Execution | Execution | [Inferred] Site Administrator (R); Project Manager (A); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.205 – Manage RFIs; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.235 | 9.4.235 - Manage Permits | 9.4.235 – Manage Permits.docx | Manage Permits | To obtain, track, and maintain all project permits and inspection records required by law and contract. Scope This SOP applies to Project Managers, Safety Coordinators, and Site Administrators. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Safety / Compliance Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.240 | 9.4.240 - Manage Inspection Reports | 9.4.240 – Manage Inspection Reports.docx | Manage Inspection Reports | To ensure inspection reports (safety, quality, and compliance) are logged, distributed, and archived to support accountability and corrective actions. Scope This SOP applies to Project Managers, Safety Coordinators, Quality Inspectors, and Site ... | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Quality / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.235 – Manage Permits; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | Approved | SOP
9.4.270 | 9.4.270 - Manage Project Communications | 9.4.270 – Manage Project Communications.docx | Manage Project Communications | To establish a consistent process for managing all project-related communications to ensure clarity, accountability, and traceability. Scope This SOP applies to Project Managers, Field Foremen, and Site Administrators. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.275 | 9.4.275 - Manage Internal Communications | 9.4.275 – Manage Internal Communications.docx | Manage Internal Communications | To ensure timely and accurate communication within the GSL project team to support coordination and decision-making. Scope This SOP applies to Project Managers, Field Foremen, Superintendents, and Site Administrators. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.165 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.280 | 9.4.280 - Manage External Communications | 9.4.280 – Manage External Communications.docx | Manage External Communications | To establish guidelines for all communications with clients, owners, architects, engineers, subcontractors, and vendors. Scope This SOP applies to Project Managers, Site Administrators, and Field Foremen. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.285 | 9.4.285 - Manage Client/Owner Communications | 9.4.285 – Manage Client Owner Communications.docx | Manage Client/Owner Communications | To establish guidelines for consistent and professional communications with the client/owner, ensuring contractual obligations, updates, and issues are clearly documented. Scope This SOP applies to Project Managers, Branch Managers, and Site Adm... | 4 - Execution | Execution | [Inferred] Branch Manager (C); Project Manager (R); Field Supervisor (C) | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.290 | 9.4.290 - Manage Subcontractor Communications | 9.4.290 – Manage Subcontractor Communications.docx | Manage Subcontractor Communications | To establish a standard process for documenting and tracking communications with subcontractors to ensure clarity, accountability, and compliance. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 - Execution | Execution | [Inferred] Subcontractors (R); Project Manager (R); Field Supervisor (C) | Project Management / Subcontractor Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.295 | 9.4.295 - Manage Vendor Supplier Communications | 9.4.295 – Manage Vendor Supplier Communications.docx | Manage Vendor Supplier Communications | To document and manage all communications with vendors and suppliers to ensure purchase orders, delivery schedules, and technical data are accurate and traceable. Scope This SOP applies to Project Managers, Purchasing, and Site Administrators. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (R); Field Supervisor (C) | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.200 – Manage Submittals; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.300 | 9.4.300 - Manage Architect/Engineer Communications | 9.4.300 – Manage Architect Engineer Communications.docx | Manage Architect/Engineer Communications | To document and manage all communications with architects and engineers to ensure design clarifications, RFIs, and revisions are properly tracked. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.305 | 9.4.305 - Manage Regulatory/Authority Communications | 9.4.305 – Manage Regulatory Authority Communications.docx | Manage Regulatory/Authority Communications | To document and manage all communications with architects and engineers to ensure design clarifications, RFIs, and revisions are properly tracked. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.310 | 9.4.310 - Manage General Contractor Communications | 9.4.310 – Manage General Contractor Communications.docx | Manage General Contractor Communications | To manage communications with the General Contractor (GC) to ensure coordination, contractual compliance, and documentation of all directives. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.150 – Conduct Project Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | Approved | SOP
9.4.315 | 9.4.315 - Develop Project Schedule | 9.4.315 – Develop Project Schedule.docx | Develop Project Schedule | To establish a baseline project schedule that reflects contractual milestones, critical path activities, and resource requirements. Scope This SOP applies to Project Managers, Superintendents, and Scheduling Coordinators. | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.010 – Project Turnover Meeting; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.320 | 9.4.320 - Update Project Schedule | 9.4.320 – Update Project Schedule.docx | Update Project Schedule | To update the project schedule regularly, reflecting actual progress, changes, and delays, ensuring alignment with field execution. Scope This SOP applies to Project Managers, Superintendents, and Site Administrators. | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.150 – Conduct Project Coordination Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.325 | 9.4.325 - Monitor Schedule Performance | 9.4.325 – Monitor Schedule Performance.docx | Monitor Schedule Performance | To monitor schedule performance by comparing baseline, updated schedules, and actual field progress to identify variances and risks. Scope This SOP applies to Project Managers, Superintendents, and Branch Managers. | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.330 | 9.4.330 - Develop Schedule Recovery Plans | 9.4.330 – Develop Schedule Recovery Plans.docx | Develop Schedule Recovery Plans | To create corrective action plans when project schedules deviate from baseline or milestones are at risk. Scope This SOP applies to Project Managers, Superintendents, and Branch Managers. | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.325 – Monitor Schedule Performance; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.335 | 9.4.335 - Prepare Lookahead Schedules | 9.4.335 – Prepare Lookahead Schedules.docx | Prepare Lookahead Schedules | To prepare short-term lookahead schedules that detail upcoming work and resource requirements to guide daily and weekly field activities. Scope This SOP applies to Project Managers, Superintendents, and Field Foremen. | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.340 | 9.4.340 - Manage Resource-Loaded Schedules | 9.4.340 – Manage Resource Loaded Schedules.docx | Manage Resource-Loaded Schedules | To integrate labor, equipment, and material resources into the project schedule to provide realistic forecasts and improve resource management. Scope This SOP applies to Project Managers, Superintendents, and Branch Managers. | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.345 | 9.4.345 - Conduct Schedule Review Meetings | 9.4.345 – Conduct Schedule Review Meetings.docx | Conduct Schedule Review Meetings | To review the project schedule with stakeholders at regular intervals, ensuring alignment between planned activities and field performance. Scope This SOP applies to Project Managers, Superintendents, Field Foremen, and Branch Managers. | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.350 | 9.4.350 - Manage Schedule Change Requests | 9.4.350 – Manage Schedule Change Requests.docx | Manage Schedule Change Requests | To evaluate, document, and process schedule change requests to ensure all modifications are justified, approved, and properly incorporated into the project schedule. Scope This SOP applies to Project Managers, Branch Managers, and Site Administr... | 4 - Execution | Execution | [Inferred] Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Scheduling / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | Approved | SOP
9.4.355 | 9.4.355 - Manage Project Scope | 9.4.355 – Manage Project Scope.docx | Manage Project Scope | To define, communicate, and control the contractual scope of work, ensuring all team members and subcontractors understand project requirements. Scope This SOP applies to Project Managers, Estimators, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.315 – Develop Project Schedule; 9.41.350 – Manage Schedule Change Requests; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.360 | 9.4.360 - Manage Change Orders | 9.4.360 – Manage Change Orders.docx | Manage Change Orders | To establish a consistent company-wide procedure for identifying, pricing, approving, documenting, and billing all contract changes (RFQs, Field Change Directives, and disputed changes) in alignment with GSL Electric’s Management Directives for Pr... | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Operations | Approved | SOP
9.4.365 | 9.4.365 - Manage Potential Change Orders (PCOs) | 9.4.365 – Manage Potential Change Orders (PCOs).docx | Manage Potential Change Orders (PCOs) | To identify, log, and track potential change orders (PCOs) before they become formal change orders, allowing proactive risk management. Scope This SOP applies to Project Managers, Estimators, and Site Administrators. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.370 | 9.4.370 - Manage Owner Directives | 9.4.370 – Manage Owner Directives.docx | Manage Owner Directives | To document and manage all owner directives that modify or clarify the scope of work, ensuring contractual and financial impacts are tracked. Scope This SOP applies to Project Managers, Site Administrators, and Estimators. | 4 - Execution | Execution | [Inferred] Branch Manager (C); Project Manager (A); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.375 | 9.4.375 - Manage Scope Clarifications | 9.4.375 – Manage Scope Clarifications.docx | Manage Scope Clarifications | To capture, track, and communicate scope clarifications arising during design interpretation, RFIs, or owner/GC discussions. Scope This SOP applies to Project Managers, Estimators, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.205 – Manage RFIs; 9.41.370 – Manage Owner Directives; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.380 | 9.4.380 - Manage Backcharges | 9.4.380 – Manage Backcharges.docx | Manage Backcharges | To document, track, and process backcharges applied to subcontractors or vendors for work not performed, damaged, or corrected by GSL. Scope This SOP applies to Project Managers, Accounting, and Site Administrators. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.290 – Manage Subcontractor Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.385 | 9.4.385 - Manage Force Account Work | 9.4.385 – Manage Force Account Work.docx | Manage Force Account Work | To document, track, and bill for force account work performed outside the contract scope but directed by the owner or GC. Scope This SOP applies to Project Managers, Field Supervisors, and Accounting. | 4 - Execution | Execution | [Inferred] Project Manager (R); Field Supervisor (C) | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.380 – Manage Backcharges; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.390 | 9.4.390 - Manage Claims | 9.4.390 – Manage Claims.docx | Manage Claims | To document, prepare, and submit claims for additional time, cost, or damages arising from circumstances outside GSL’s control. Scope This SOP applies to Project Managers, Branch Managers, Estimators, and Legal Counsel. | 4 - Execution | Execution | [Inferred] Branch Manager (A); Project Manager (A); Field Supervisor (C) | Project Management / Contract Administration / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.370 – Manage Owner Directives; 9.41.385 – Manage Force Account Work; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | Approved | SOP
9.4.400 | 9.4.400 - Monitor Project Costs | 9.4.400 – Monitor Project Costs.docx | Monitor Project Costs | To monitor actual costs against the project budget, ensuring variances are detected early and corrective actions are taken. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.405 – Manage Cost Forecasts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.405 | 9.4.405 - Manage Cost Forecasts | 9.4.405 – Manage Cost Forecasts.docx | Manage Cost Forecasts | To forecast final project costs based on current performance and anticipated trends, ensuring management has accurate projections. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.410 | 9.4.410 - Manage Cost Codes | 9.4.410 – Manage Cost Codes.docx | Manage Cost Codes | To standardize and maintain cost codes for consistent budgeting, tracking, and reporting across projects. Scope This SOP applies to Project Managers, Estimators, and Accounting. | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.415 | 9.4.415 - Manage Committed Costs | 9.4.415 – Manage Committed Costs.docx | Manage Committed Costs | To track and manage committed costs (purchase orders, subcontracts, and other financial commitments) against the project budget. Scope This SOP applies to Project Managers, Purchasing, and Accounting. | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.420 | 9.4.420 - Manage Actual Costs | 9.4.420 – Manage Actual Costs.docx | Manage Actual Costs | To record, verify, and report actual costs incurred on the project for accurate financial tracking and reporting. Scope This SOP applies to Project Managers, Accounting, and Site Administrators. | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.425 | 9.4.425 - Manage Job Cost Reports | 9.4.425 – Manage Job Cost Reports.docx | Manage Job Cost Reports | To prepare and distribute job cost reports that compare actual and committed costs to the budget, ensuring management visibility of project financial status. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.430 | 9.4.430 - Manage Profit Projections | 9.4.430 – Manage Profit Projections.docx | Manage Profit Projections | To project project-level and portfolio-level profitability by comparing revenue, costs, and forecasts. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.435 | 9.4.435 - Manage Cost-to-Complete | 9.4.435 – Manage Cost to Complete.docx | Manage Cost-to-Complete | To calculate and monitor cost-to-complete (CTC) values, ensuring accurate forecasting of final project costs and profitability. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 - Execution | Execution | [Inferred] Accounting (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.420 – Manage Actual Costs; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | Approved | SOP
9.4.440 | 9.4.440 - Prepare Billing Schedule | 9.4.440 – Prepare Billing Schedule.docx | Prepare Billing Schedule | To develop a billing schedule that aligns with the project contract, milestones, and cash flow requirements. Scope This SOP applies to Project Managers and Accounting. | 4 - Execution | Execution | [Inferred] Accounting (R); Superintendent (C); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.445 | 9.4.445 - Prepare Monthly Pay Applications | 9.4.445 – Prepare Monthly Pay Applications.docx | Prepare Monthly Pay Applications | To prepare monthly pay applications in accordance with the contract, ensuring accurate billing of work performed and materials stored. Scope This SOP applies to Project Managers, Field Supervisors, and Accounting. | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.440 – Prepare Billing Schedule; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.450 | 9.4.450 - Track Accounts Receivable | 9.4.450 – Track Accounts Receivable.docx | Track Accounts Receivable | To track accounts receivable (AR) from submitted invoices and pay applications, ensuring timely collection of payments. Scope This SOP applies to Accounting, Project Managers, and Branch Managers. | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Accounting / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.455 | 9.4.455 - Manage Lien Waivers | 9.4.455 – Manage Lien Waivers.docx | Manage Lien Waivers | To collect, verify, and submit lien waivers in compliance with contract requirements and to protect against payment disputes. Scope This SOP applies to Project Managers, Accounting, and Subcontractors. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.460 | 9.4.460 - Manage Retainage | 9.4.460 – Manage Retainage.docx | Manage Retainage | To track retainage withheld on pay applications and ensure proper release at substantial completion and final project closeout. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 - Execution | Execution | [Inferred] Accounting (R); Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.465 – Manage Final Invoicing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.465 | 9.4.465 - Manage Final Invoicing | 9.4.465 – Manage Final Invoicing.docx | Manage Final Invoicing | To prepare and submit the final invoice for project payment, ensuring all conditions precedent to final payment are satisfied. Scope This SOP applies to Project Managers, Accounting, and Branch Managers. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.455 – Manage Lien Waivers; 9.41.460 – Manage Retainage; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | Approved | SOP
9.4.475 | 9.4.475 - Conduct Safety Orientation | 9.4.475 – Conduct Safety Orientation.docx | Conduct Safety Orientation | To provide safety orientation for all employees, subcontractors, and visitors before they begin work on-site. Scope This SOP applies to Safety Coordinators, Project Managers, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.480 | 9.4.480 - Conduct Safety Inspections | 9.4.480 – Conduct Safety Inspections.docx | Conduct Safety Inspections | To conduct regular safety inspections of the jobsite, identify hazards, and verify compliance with OSHA and company standards. Scope This SOP applies to Safety Coordinators, Field Supervisors, and Project Managers. | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.485 | 9.4.485 - Conduct Safety Meetings | 9.4.485 – Conduct Safety Meetings.docx | Conduct Safety Meetings | To conduct regular safety meetings (toolbox talks and formal sessions) to communicate safety policies, hazards, and corrective actions. Scope This SOP applies to Safety Coordinators, Project Managers, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.490 | 9.4.490 - Report Safety Incidents | 9.4.490 – Report Safety Incidents.docx | Report Safety Incidents | To report all safety incidents, including near misses, injuries, and property damage, in a timely and consistent manner. Scope This SOP applies to all employees, subcontractors, Project Managers, and Safety Coordinators. | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.485 – Conduct Safety Meetings; 9.41.495 – Investigate Accidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.495 | 9.4.495 - Investigate Accidents | 9.4.495 – Investigate Accidents.docx | Investigate Accidents | To investigate accidents and near misses to identify root causes, prevent recurrence, and comply with regulatory requirements. Scope This SOP applies to Project Managers, Safety Coordinators, Field Supervisors, and Branch Managers. | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Project Management / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.490 – Report Safety Incidents; 9.41.485 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.500 | 9.4.500 - Conduct Emergency Preparedness | 9.4.500 – Conduct Emergency Preparedness.docx | Conduct Emergency Preparedness | To establish and maintain emergency preparedness procedures to ensure a safe and effective response to jobsite emergencies. Scope This SOP applies to Safety Coordinators, Project Managers, Field Supervisors, and all jobsite personnel. | 4 - Execution | Execution | [Inferred] Safety Coordinator (R); Project Manager (A); Field Supervisor (C) | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.490 – Report Safety Incidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.505 | 9.4.505 - Conduct Safety Compliance Audits | 9.4.505 – Conduct Safety Compliance Audits.docx | Conduct Safety Compliance Audits | To conduct safety compliance audits that verify adherence to OSHA standards, contract requirements, and company policies. Scope This SOP applies to Safety Coordinators, Project Managers, and Branch Managers. | 4 - Execution | Execution | [Inferred] Safety Coordinator (C); Project Manager (A); Field Supervisor (C) | Safety / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.480 – Conduct Safety Inspections; 9.41.495 – Investigate Accidents; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.510 | 9.4.510 - Provide Safety Training | 9.4.510 – Provide Safety Training.docx | Provide Safety Training | To provide ongoing safety training for employees and subcontractors, ensuring compliance with regulatory standards and company policies. Scope This SOP applies to Safety Coordinators, Project Managers, and HR. | 4 - Execution | Execution | [Inferred] Safety Coordinator (C); Project Manager (A); Field Supervisor (C) | Safety / Human Resources Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.475 – Conduct Safety Orientation; 9.41.485 – Conduct Safety Meetings; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | Approved | SOP
9.4.515 | 9.4.515 - Develop Quality Management Plan | 9.4.515 – Develop Quality Management Plan.docx | Develop Quality Management Plan | To develop a project-specific Quality Management Plan (QMP) that defines standards, responsibilities, inspections, and acceptance criteria. Scope This SOP applies to Project Managers, Quality Inspectors, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.520 | 9.4.520 - Conduct Quality Meetings | 9.4.520 – Conduct Quality Meetings.docx | Conduct Quality Meetings | To conduct regular quality meetings to review standards, discuss issues, and ensure compliance with project requirements. Scope This SOP applies to Project Managers, Quality Inspectors, Field Supervisors, and Subcontractors. | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.175 – Conduct Quality Meetings; 9.41.515 – Develop Quality Management Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.525 | 9.4.525 - Conduct Quality Inspections | 9.4.525 – Conduct Quality Inspections.docx | Conduct Quality Inspections | To perform inspections that verify work complies with contract documents, specifications, and quality standards. Scope This SOP applies to Quality Inspectors, Project Managers, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Safety / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.515 – Develop Quality Management Plan; 9.41.520 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.530 | 9.4.530 - Manage Quality Testing | 9.4.530 – Manage Quality Testing.docx | Manage Quality Testing | To perform and document quality testing in accordance with project specifications, codes, and standards. Scope This SOP applies to Quality Inspectors, Testing Agencies, and Project Managers. | 4 - Execution | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.525 – Conduct Quality Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.535 | 9.4.535 - Manage Nonconformance Reports (NCRs) | 9.4.535 – Manage Nonconformance Reports (NC Rs).docx | Manage Nonconformance Reports (NCRs) | To identify, document, and resolve nonconforming work in a consistent and traceable manner. Scope This SOP applies to Project Managers, Quality Inspectors, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Quality Inspector (R); Project Manager (A); Field Supervisor (C) | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.530 – Manage Quality Testing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.540 | 9.4.540 - Manage Quality Records | 9.4.540 – Manage Quality Records.docx | Manage Quality Records | To establish a system for maintaining and archiving quality records that demonstrate compliance with project and contractual requirements. Scope This SOP applies to Project Managers, Site Administrators, and Quality Inspectors. | 4 - Execution | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.530 – Manage Quality Testing; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.545 | 9.4.545 - Manage Punch List Quality | 9.4.545 – Manage Punch List Quality.docx | Manage Punch List Quality | To ensure punch list items are documented, corrected, and verified for quality compliance prior to project closeout. Scope This SOP applies to Project Managers, Field Supervisors, Subcontractors, and Quality Inspectors. | 4 - Execution | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.245 – Manage Punch Lists; 9.41.525 – Conduct Quality Inspections; 9.41.540 – Manage Quality Records; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.4.560 | 9.4.560 - Manage Manpower Allocation | 9.4.560 – Manage Manpower Allocation.docx | Manage Manpower Allocation | To allocate manpower efficiently across projects, ensuring sufficient labor resources are available to meet schedule and productivity requirements. Scope This SOP applies to Project Managers, Superintendents, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.565 | 9.4.565 - Manage Equipment Allocation | 9.4.565 – Manage Equipment Allocation.docx | Manage Equipment Allocation | To allocate, track, and maintain equipment resources across projects to ensure availability and cost efficiency. Scope This SOP applies to Project Managers, Superintendents, and Equipment Managers. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.570 | 9.4.570 - Manage Material Allocation | 9.4.570 – Manage Material Allocation.docx | Manage Material Allocation | To manage allocation and delivery of materials to ensure availability at the right time and location while minimizing waste and storage costs. Scope This SOP applies to Project Managers, Purchasing, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.565 – Manage Equipment Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.576 | 9.4.576 - Manage Subcontractor Resources | 9.4.576 – Manage Subcontractor Resources.docx | Manage Subcontractor Resources | To manage subcontractor manpower, equipment, and material resources to ensure their availability aligns with project requirements and schedules. Scope This SOP applies to Project Managers, Field Supervisors, and Subcontractors. | 4 - Execution | Execution | [Inferred] Subcontractors (R); Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.415 – Manage Committed Costs; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.580 | 9.4.580 - Manage Vendor Resources | 9.4.580 – Manage Vendor Resources.docx | Manage Vendor Resources | To coordinate vendor-provided resources (materials, deliveries, technical support) to ensure timely project execution. Scope This SOP applies to Project Managers, Purchasing, and Vendors. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.295 – Manage Vendor / Supplier Communications; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.585 | 9.4.585 - Plan Prefabrication Resources | 9.4.585 – Plan Prefabrication Resources.docx | Plan Prefabrication Resources | To plan prefabrication resources (labor, space, tools, and materials) to optimize efficiency, reduce jobsite congestion, and improve quality. Scope This SOP applies to Project Managers, Prefabrication Managers, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Prefabrication Lead (R); Project Manager (A); Field Supervisor (C) | Project Management / Field Operations / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.590 | 9.4.590 - Manage Specialty Contractor Resources | 9.4.590 – Manage Specialty Contractor Resources.docx | Manage Specialty Contractor Resources | To manage specialty contractor resources (e.g. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.575 – Manage Subcontractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.595 | 9.4.595 - Prepare Resource Reports | 9.4.595 – Prepare Resource Reports.docx | Prepare Resource Reports | To prepare weekly and monthly resource reports that summarize manpower, equipment, material, and subcontractor usage across the project. Scope This SOP applies to Project Managers, Superintendents, and Branch Managers. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.590 – Manage Specialty Contractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | Approved | SOP
9.4.605 | 9.4.605 - Issue Purchase Orders | 9.4.605 – Issue Purchase Orders.docx | Issue Purchase Orders | To issue purchase orders (POs) for materials and equipment, ensuring accuracy, cost compliance, and delivery coordination. Scope This SOP applies to Purchasing, Project Managers, and Accounting. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.415 – Manage Committed Costs; 9.41.600 – Develop Procurement Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.610 | 9.4.610 - Manage Vendor Prequalification | 9.4.610 – Manage Vendor Prequalification.docx | Manage Vendor Prequalification | To prequalify vendors and suppliers based on financial stability, safety record, quality performance, and capacity. Scope This SOP applies to Purchasing, Project Managers, and Branch Managers. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.290 – Manage Subcontractor Communications; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.615 | 9.4.615 - Manage Vendor Evaluations | 9.4.615 – Manage Vendor Evaluations.docx | Manage Vendor Evaluations | To evaluate vendor performance on each project, focusing on quality, timeliness, cost compliance, and communication. Scope This SOP applies to Project Managers, Purchasing, and Branch Managers. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.620 | 9.4.620 - Manage Expediting | 9.4.620 – Manage Expediting.docx | Manage Expediting | To expedite vendor and supplier commitments to ensure timely delivery of critical materials and equipment. Scope This SOP applies to Purchasing, Project Managers, and Vendors. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.625 | 9.4.625 - Manage Delivery Tracking | 9.4.625 – Manage Delivery Tracking.docx | Manage Delivery Tracking | To track vendor and supplier deliveries, ensuring that materials and equipment arrive on schedule and in good condition. Scope This SOP applies to Purchasing, Project Managers, and Field Supervisors. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.620 – Manage Expediting; 9.41.570 – Manage Material Allocation; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.630 | 9.4.630 - Manage Material Receiving | 9.4.630 – Manage Material Receiving.docx | Manage Material Receiving | To ensure materials and equipment received on-site are verified for accuracy, quality, and compliance with purchase orders. Scope This SOP applies to Field Supervisors, Project Managers, and Purchasing. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Field Operations / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.625 – Manage Delivery Tracking; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.631 | 9.4.631 - Release of Large Feeder Wire | 9.4.631 – Release of Large Feeder Wire.docx | Release of Large Feeder Wire | Standardizes the process for verifying, releasing, and tracking large feeder wire after procurement to ensure accuracy, proper sequencing, and timely delivery. Scope Applies to all large feeder wire (1 AWG and larger) released from vendor storag... | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Leadership / Purchasing | Approved | SOP
9.4.635 | 9.4.635 - Manage Material Inspection | 9.4.635 – Manage Material Inspection.docx | Manage Material Inspection | To inspect materials and equipment for compliance with specifications, submittals, and quality requirements before installation. Scope This SOP applies to Field Supervisors, Quality Inspectors, and Project Managers. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Field Operations / Quality / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.530 – Manage Quality Testing; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.640 | 9.4.640 - Manage Storage and Logistics | 9.4.640 – Manage Storage and Logistics.docx | Manage Storage and Logistics | To manage storage and logistics of materials and equipment to ensure availability, protection, and efficient handling on-site. Scope This SOP applies to Project Managers, Field Supervisors, and Warehouse/Logistics Personnel. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.570 – Manage Material Allocation; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.645 | 9.4.645 - Manage Material Handling | 9.4.645 – Manage Material Handling.docx | Manage Material Handling | To safely and efficiently handle materials on-site, minimizing waste, damage, and productivity loss. Scope This SOP applies to Field Supervisors, Warehouse/Logistics Personnel, and Project Managers. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Field Operations / Logistics / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.650 | 9.4.650 - Manage Inventory | 9.4.650 – Manage Inventory.docx | Manage Inventory | To maintain accurate inventory records of materials, tools, and equipment to ensure availability and accountability. Scope This SOP applies to Field Supervisors, Site Administrators, and Project Managers. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Field Operations / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.645 – Manage Material Handling; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.655 | 9.4.655 - Prepare Procurement Reports | 9.4.655 – Prepare Procurement Reports.docx | Prepare Procurement Reports | To prepare weekly and monthly procurement reports that summarize commitments, deliveries, and outstanding issues. Scope This SOP applies to Purchasing, Project Managers, and Branch Managers. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.650 – Manage Inventory; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.660 | 9.4.660 - Manage Procurement Closeout | 9.4.660 – Manage Procurement Closeout.docx | Manage Procurement Closeout | To close out all procurement activities by confirming that purchase orders, deliveries, and invoices are complete and reconciled. Scope This SOP applies to Project Managers, Purchasing, and Accounting. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.465 – Manage Final Invoicing; 9.41.650 – Manage Inventory; 9.41.655 – Prepare Procurement Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.665 | 9.4.665 - Reconcile Procurement Accounts | 9.4.665 – Reconcile Procurement Accounts.docx | Reconcile Procurement Accounts | To reconcile procurement accounts by confirming all commitments, invoices, and payments match and that no outstanding liabilities remain. Scope This SOP applies to Accounting, Project Managers, and Purchasing. | 4 - Execution | Execution | [Inferred] Purchasing (R); Accounting (R); Project Manager (A); Field Supervisor (C) | Accounting / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.420 – Manage Actual Costs; 9.41.660 – Manage Procurement Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.670 | 9.4.670 - Manage Vendor Closeout | 9.4.670 – Manage Vendor Closeout.docx | Manage Vendor Closeout | To formally close out vendor accounts by verifying completion of work, receipt of materials, and settlement of all financial obligations. Scope This SOP applies to Purchasing, Project Managers, and Accounting. | 4 - Execution | Execution | [Inferred] Purchasing (R); Project Manager (A); Field Supervisor (C) | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.615 – Manage Vendor Evaluations; 9.41.660 – Manage Procurement Closeout; 9.41.665 – Reconcile Procurement Accounts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | Approved | SOP
9.4.675 | 9.4.675 - Conduct Daily Huddles | 9.4.675 – Conduct Daily Huddles.docx | Conduct Daily Huddles | To conduct daily field huddles with crews to communicate work plans, hazards, and coordination needs. Scope This SOP applies to Field Supervisors, Foremen, and Project Managers. | 4 - Execution | Execution | [Inferred] Foreman (R); Project Manager (A); Field Supervisor (C) | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.680 | 9.4.680 - Conduct Weekly Foreman Meetings | 9.4.680 – Conduct Weekly Foreman Meetings.docx | Conduct Weekly Foreman Meetings | To conduct weekly foreman meetings to review schedule, manpower, coordination issues, and site logistics. Scope This SOP applies to Project Managers, Field Supervisors, and Foremen. | 4 - Execution | Execution | [Inferred] Foreman (R); Project Manager (A); Field Supervisor (C) | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.690 | 9.4.690 - Track Manpower Utilization | 9.4.690 – Track Manpower Utilization.docx | Track Manpower Utilization | To track manpower utilization daily to ensure labor is allocated effectively and productivity targets are met. Scope This SOP applies to Project Managers, Field Supervisors, and Site Administrators. | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Field Operations / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.695 | 9.4.695 - Track Production Quantities | 9.4.695 – Track Production Quantities.docx | Track Production Quantities | To track production quantities of installed work daily to measure productivity and progress against plan. Scope This SOP applies to Field Supervisors, Foremen, and Project Managers. | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.400 – Monitor Project Costs; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.700 | 9.4.700 - Track Equipment Utilization | 9.4.700 – Track Equipment Utilization.docx | Track Equipment Utilization | To track equipment usage daily to ensure proper allocation, cost control, and productivity. Scope This SOP applies to Field Supervisors, Equipment Managers, and Project Managers. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.565 – Manage Equipment Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.705 | 9.4.705 - Manage Work Packaging | 9.4.705 – Manage Work Packaging.docx | Manage Work Packaging | To break down project scope into manageable work packages for efficient planning, assignment, and tracking. Scope This SOP applies to Project Managers, Field Supervisors, and Foremen. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.335 – Prepare Lookahead Schedules; 9.41.695 – Track Production Quantities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.710 | 9.4.710 - Manage Workface Planning | 9.4.710 – Manage Workface Planning.docx | Manage Workface Planning | To implement workface planning (WFP) by providing crews with all information, materials, and tools needed before starting field tasks. Scope This SOP applies to Project Managers, Field Supervisors, and Foremen. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.705 – Manage Work Packaging; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.715 | 9.4.715 - Manage Field Coordination | 9.4.715 – Manage Field Coordination.docx | Manage Field Coordination | To coordinate daily field activities across crews and subcontractors, ensuring work is sequenced properly and conflicts are resolved. Scope This SOP applies to Project Managers, Field Supervisors, and Subcontractors. | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.680 – Conduct Weekly Foreman Meetings; 9.41.705 – Manage Work Packaging; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.720 | 9.4.720 - Conduct Productivity Analysis | 9.4.720 – Conduct Productivity Analysis.docx | Conduct Productivity Analysis | To analyze field productivity by comparing actual labor hours and production against planned values, enabling corrective action. Scope This SOP applies to Project Managers, Field Supervisors, and Accounting. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.695 – Track Production Quantities; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.725 | 9.4.725 - Resolve Field Problems | 9.4.725 – Resolve Field Problems.docx | Resolve Field Problems | To resolve field problems promptly to avoid delays, rework, or safety risks. Scope This SOP applies to Field Supervisors, Project Managers, and Quality Inspectors. | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.715 – Manage Field Coordination; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.735 | 9.4.735 - Perform Field Quality Verifications | 9.4.735 – Perform Field Quality Verifications.docx | Perform Field Quality Verifications | To perform ongoing quality verifications in the field to ensure work is performed according to drawings, specifications, and approved submittals. Scope This SOP applies to Field Supervisors, Quality Inspectors, and Project Managers. | 4 - Execution | Execution | [Inferred] Quality Inspector (C); Project Manager (A); Field Supervisor (C) | Field Operations / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.535 – Manage Nonconformance Reports; 9.41.720 – Conduct Productivity Analysis; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.745 | 9.4.745 - Manage Field Rework | 9.4.745 – Manage Field Rework.docx | Manage Field Rework | To manage field rework systematically so deficiencies are corrected efficiently, minimizing cost and schedule impacts. Scope This SOP applies to Project Managers, Field Supervisors, Foremen, and Quality Inspectors. | 4 - Execution | Execution | [Inferred] Field Supervisor (R); Project Manager (A) | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.535 – Manage Nonconformance Reports; 9.41.725 – Resolve Field Problems; 9.41.735 – Perform Field Quality Verifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.4.755 | 9.4.755 - Implement Field Productivity Improvements | 9.4.755 – Implement Field Productivity Improvements.docx | Implement Field Productivity Improvements | To identify, implement, and monitor productivity improvement measures in field operations. Scope This SOP applies to Project Managers, Field Supervisors, and Foremen. | 4 - Execution | Execution | [Inferred] Project Manager (A); Field Supervisor (C) | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.720 – Conduct Productivity Analysis; 9.41.695 – Track Production Quantities; 9.41.585 – Plan Prefabrication Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.5.020 | 9.5.020 - Handling and/or Disposing of Excess Materials | 9.5.020 – Handling and or Disposing of Excess Materials.docx | Handling and/or Disposing of Excess Materials | To establish a standardized process for conducting commissioning meetings, ensuring proper coordination between all parties during the testing, verification, and turnover phases of the p... | 5 - Commissioning | Commissioning | ¦ Project Manager (A); ¦ Commissioning Agent (R); ¦ Field Supervisor (R); ¦ Quality/QA-QC (C); ¦ Subcontractors (R) | Project Management / Quality | Approved | SOP
9.5.550 | 9.5.550 - Manage Commissioning Activities | 9.5.550 – Manage Commissioning Activities.docx | Manage Commissioning Activities | To establish a standardized process for managing all commissioning activities, ensuring systematic testing, verification, and documentation of electrical systems prior to owner turnover.... | 5 - Commissioning | Commissioning | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Commissioning Agent (R); ¦ Quality/QA-QC (R); ¦ Subcontractors (R) | Project Management / Quality | Approved | SOP
9.6.005 | 9.6.005 - Prepare for Turnover (Field Perspective) | 9.6.005 – Prepare for Turnover (Field Perspective).docx | Prepare for Turnover (Field Perspective) | To prepare field operations for turnover by ensuring punch lists, as-builts, and corrective actions are completed and verified. Scope This SOP applies to Field Supervisors, Foremen, and Project Managers. | 6 - Closeout | Closeout | [Inferred] Project Manager (A) | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.555 – Manage Project Turnover Documentation; 9.41.730 – Manage As-Built Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | Approved | SOP
9.6.010 | 9.6.010 - Conduct Closeout Meetings | 9.6.010 – Conduct Closeout Meetings.docx | Conduct Closeout Meetings | To establish a standardized process for conducting project closeout meetings, ensuring proper coordination of all closeout activities and successful project completion. =================... | 6 - Closeout | Closeout | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Subcontractors (R); ¦ Client/Owner (I) | Project Management | Approved | SOP
9.6.015 | 9.6.015 - Manage Project Turnover Documentation | 9.6.015 – Manage Project Turnover Documentation.docx | Manage Project Turnover Documentation | To compile, review, and submit all turnover documentation to the Owner/GC, ensuring contractual requirements are satisfied. Scope This SOP applies to Project Managers, Site Administrators, and Branch Managers. | 6 - Closeout | Closeout | [Inferred] Project Manager (A) | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.545 – Manage Punch List Quality; 9.41.550 – Manage Commissioning Activities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | Approved | SOP
9.6.020 | 9.6.020 - Manage Punch List Closeout | 9.6.020 – Manage Punch List Closeout.docx | Manage Punch List Closeout | To complete and verify punch list items before project turnover. Scope This SOP applies to Project Managers, Field Supervisors, Quality Inspectors, and Subcontractors. | 6 - Closeout | Closeout | [Inferred] Quality Inspector (C); Project Manager (A) | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.760 – Prepare for Turnover (Field Perspective); 9.41.555 – Manage Project Turnover Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.030 | 9.6.030 - Manage As-Built Drawings | 9.6.030 – Manage As Built Drawings.docx | Manage As-Built Drawings | To establish a standardized process for managing as-built drawings, ensuring accurate documentation of installed conditions for owner records and future maintenance. ====================... | 6 - Closeout | Closeout | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Foreman (R); ¦ Project Engineer/APM (R) | Project Management / Field Operations | Approved | SOP
9.6.035 | 9.6.035 - Submit Warranties | 9.6.035 – Submit Warranties.docx | Submit Warranties | To collect, verify, and submit warranties to the Owner/GC as part of turnover documentation. Scope This SOP applies to Project Managers, Site Administrators, and Subcontractors. | 6 - Closeout | Closeout | [Inferred] Project Manager (A) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.770 – Manage Punch List Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.040 | 9.6.040 - Submit O&M Manuals | 9.6.040 – Submit O&M Manuals.docx | Submit O&M Manuals | To submit Operations & Maintenance (O&M) manuals for equipment and systems in compliance with contract requirements. Scope This SOP applies to Project Managers, Site Administrators, and Vendors/Subcontractors. | 6 - Closeout | Closeout | [Inferred] Project Manager (A) | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.550 – Manage Commissioning Activities; 9.41.775 – Submit Warranties; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.050 | 9.6.050 - Provide Owner Training | 9.6.050 – Provide Owner Training.docx | Provide Owner Training | To provide Owner training on systems and equipment to ensure proper operation and maintenance after turnover. Scope This SOP applies to Project Managers, Vendors, Subcontractors, and the Owner/GC. | 6 - Closeout | Closeout | [Inferred] Branch Manager (C); Project Manager (A) | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.550 – Manage Commissioning Activities; 9.41.780 – Submit O&M Manuals; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.065 | 9.6.065 - Archive Project Documentation | 9.6.065 – Archive Project Documentation.docx | Archive Project Documentation | To archive all project documentation for future reference, audits, and warranty compliance. Scope This SOP applies to Project Managers, Site Administrators, and Branch Managers. | 6 - Closeout | Closeout | [Inferred] Site Administrator (R); Project Manager (A) | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.265 – Manage Closeout Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | Approved | SOP
9.6.070 | 9.6.070 - Conduct Post-Project Review | 9.6.070 – Conduct Post Project Review.docx | Conduct Post-Project Review | To establish a standardized process for conducting post-project reviews, evaluating project performance, and identifying successes and areas for improvement. ============================... | 6 - Closeout | Closeout | ¦ Branch Manager (A); ¦ Project Manager (R); ¦ Field Supervisor (R); ¦ Operations Manager (C) | Project Management | Approved | SOP
9.6.080 | 9.6.080 - Capture Client Feedback | 9.6.080 – Capture Client Feedback.docx | Capture Client Feedback | To establish a standardized process for capturing client feedback at project completion, enabling continuous improvement and strengthening client relationships. =========================... | 6 - Closeout | Closeout | ¦ Branch Manager (A); ¦ Project Manager (R); ¦ Business Development (C); ¦ Executive Committee (I) | Project Management | Approved | SOP
9.6.085 | 9.6.085 - Document Lessons Learned | 9.6.085 – Document Lessons Learned.docx | Document Lessons Learned | To establish a standardized process for documenting lessons learned throughout and at the completion of projects, creating an organizational knowledge base for continuous improvement. ==... | 6 - Closeout | Closeout | ¦ Operations Manager (A); ¦ Project Manager (R); ¦ Field Supervisor (R); ¦ Branch Manager (C) | Project Management | Approved | SOP

## Coverage Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category
9.1.050 - Prepare Construction Takeoff | Oversees Prepare Construction Takeoff | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 1 - Estimating
9.2.005 - Review Contract for High Risk Clauses | Oversees Review Contract for High Risk Clauses | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.010 - Team Selection | Selects Project Manager and assigns or approves final team assignments; Allocates resources across projects; Resolves resource conflicts. | Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Identifies required roles and skill sets; Recommends team members; Coordinates with Branch Manager on availability. | Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Validates field leadership assignments; Confirms crew availability and capability | General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Ensures safety-qualified personnel are assigned, Reviews site-specific safety requirements. | Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Informed of procurement resource needs | Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Informed of prefab support requirements | Prefabrication Lead | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction
9.2.015 - Project Turnover Meeting | Oversees closeout for Project Turnover Meeting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.020 - Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.020 - Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | Oversees Review Contract for Unfavorable or High-Risk Clauses | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.040 - Project Manager Reviews Plans Specifications & Schedule | Coordinates scheduling for Project Manager Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.040 - Project Manager Reviews Plans Specifications & Schedule | Manages technical documentation for Project Manager Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | Coordinates scheduling for Field Supervisor Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | Manages technical documentation for Field Supervisor Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.055 - Compare Estimated vs Planned Performance | Provides estimating support for Compare Estimated vs Planned Performance | Estimator | Sec. 9.9 Estimating Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.055 - Compare Estimated vs Planned Performance | Oversees Compare Estimated vs Planned Performance | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.057 - Identify VE and Prefabrication Opportunities | Coordinates prefabrication for Identify VE and Prefabrication Opportunities | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.057 - Identify VE and Prefabrication Opportunities | Oversees Identify VE and Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.060 - Create Issue List and Begin RFI Process | Manages overall issue resolution; Prioritizes RFIs; Tracks responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create Issue List and Begin RFI Process | Creates and submits RFIs; Maintains issue log; Follows up on responses ¦ | ¦ Assistant PM/Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create Issue List and Begin RFI Process | Contributes constructability issues; Reviews RFI responses for field impact ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create Issue List and Begin RFI Process | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | Coordinates site visit; Documents findings; Integrates into project planning ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | Conducts physical site inspection; Identifies constructability and logistics issues ¦ | ¦ Field Leadership | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | Assesses site safety conditions; Identifies hazards and requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction
9.2.080 - Prepare Material Handling Plan | Oversees Prepare Material Handling Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.090 - Develop Labor Budget | Provides financial support for Develop Labor Budget | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.090 - Develop Labor Budget | Oversees Develop Labor Budget | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.100 - Prepare Layout & Sequencing Plan | Oversees Prepare Layout & Sequencing Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.110 - Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.110 - Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.120 - Establish Tracking & Control Systems | Oversees Establish Tracking & Control Systems | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.130 - Construction Execution Kickoff Meeting | Leads coordination for Construction Execution Kickoff Meeting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.140 - Develop Project Budget | Provides financial support for Develop Project Budget | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.140 - Develop Project Budget | Oversees Develop Project Budget | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.160 - Develop Procurement Plan | Manages procurement for Develop Procurement Plan | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.2.160 - Develop Procurement Plan | Oversees Develop Procurement Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction
9.3.010 - Setup Office Trailer | Approves trailer location and configuration; Coordinates delivery timing ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization
9.3.010 - Setup Office Trailer | Oversees physical setup; Coordinates with delivery vendor; Ensures utility connections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.010 - Setup Office Trailer | Sets up office equipment and supplies; Establishes filing systems ¦ | ¦ Site Administrator | Sec. 9.8 Site Administration | Covered | No change required. | 3 - Mobilization
9.3.010 - Setup Office Trailer | Reviews placement for safety compliance; Ensures egress requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization
9.3.010 - Setup Office Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 3 - Mobilization
9.3.020 - Setup Storage Trailer | Oversees setup and organization; Establishes security protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.020 - Setup Storage Trailer | Coordinates physical placement; Organizes interior layout ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.020 - Setup Storage Trailer | Coordinates material delivery timing with storage availability ¦ | ¦ Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 3 - Mobilization
9.3.020 - Setup Storage Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization
9.3.030 - Setup Site Fencing and Access Control | Oversees fencing installation; Establishes access protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.030 - Setup Site Fencing and Access Control | Coordinates installation; Manages gate operations ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.030 - Setup Site Fencing and Access Control | Defines safety requirements; Reviews emergency egress ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization
9.3.030 - Setup Site Fencing and Access Control | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | Oversees installation; Ensures code compliance ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | Installs temporary power system; Makes connections ¦ | ¦ Foreman/Journeyman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | Reviews safety requirements; Verifies GFCI protection ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | Coordinates with utility company; Approves power plan ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization
9.3.040 - Setup Temporary Power | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Electrical Subcontractor | Sec. 9.2 General Directives | Covered | No change required. | 3 - Mobilization
9.3.050 - Setup Temporary Water | Coordinates site setup for Setup Temporary Water | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.050 - Setup Temporary Water | Oversees Setup Temporary Water | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.060 - Setup Sanitary Facilities | Coordinates site setup for Setup Sanitary Facilities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.060 - Setup Sanitary Facilities | Oversees Setup Sanitary Facilities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.070 - Setup Temporary Lighting | Coordinates site setup for Setup Temporary Lighting | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.070 - Setup Temporary Lighting | Oversees Setup Temporary Lighting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.080 - Setup Signage | Coordinates site setup for Setup Signage | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.080 - Setup Signage | Oversees Setup Signage | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.090 - Setup Security | Coordinates site setup for Setup Security | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.090 - Setup Security | Oversees Setup Security | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.100 - Setup Laydown Area | Coordinates site setup for Setup Laydown Area | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.100 - Setup Laydown Area | Oversees Setup Laydown Area | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.110 - Setup Equipment Staging | Coordinates site setup for Setup Equipment Staging | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.110 - Setup Equipment Staging | Oversees Setup Equipment Staging | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.120 - Setup Parking | Coordinates site setup for Setup Parking | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.3.120 - Setup Parking | Oversees Setup Parking | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.470 - Develop Site-Specific Safety Plan | Reviews for safety compliance for Develop Site-Specific Safety Plan | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.470 - Develop Site-Specific Safety Plan | Oversees Develop Site-Specific Safety Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization
9.3.470 - Develop Site-Specific Safety Plan | Field coordination for Develop Site-Specific Safety Plan | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization
9.4.010 - Conduct Coordination Meetings | Leads coordination for Conduct Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.010 - Conduct Coordination Meetings | Field coordination for Conduct Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.020 - Conduct Subcontractor Coordination Meetings | Performs subcontracted work for Conduct Subcontractor Coordination Meetings | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.020 - Conduct Subcontractor Coordination Meetings | Leads coordination for Conduct Subcontractor Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.020 - Conduct Subcontractor Coordination Meetings | Field coordination for Conduct Subcontractor Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.030 - Conduct Client/Owner Meetings | Participates in client communications for Conduct Client/Owner Meetings | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution
9.4.030 - Conduct Client/Owner Meetings | Oversees Conduct Client/Owner Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.030 - Conduct Client/Owner Meetings | Field coordination for Conduct Client/Owner Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.040 - Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.040 - Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.040 - Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Coordinates prefabrication for Identify Value Engineering & Prefabrication Opportunities | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Oversees Identify Value Engineering & Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Field coordination for Identify Value Engineering & Prefabrication Opportunities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.050 - Conduct Prefabrication Coordination Meetings | Coordinates prefabrication for Conduct Prefabrication Coordination Meetings | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.050 - Conduct Prefabrication Coordination Meetings | Leads coordination for Conduct Prefabrication Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.050 - Conduct Prefabrication Coordination Meetings | Field coordination for Conduct Prefabrication Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.055 - Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.055 - Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.055 - Procurement of Large Feeder Wire | Field coordination for Procurement of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.060 - Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.060 - Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.060 - Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.190 - Document Filing Standards | Manages documentation for Document Filing Standards | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution
9.4.190 - Document Filing Standards | Oversees Document Filing Standards | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.190 - Document Filing Standards | Field coordination for Document Filing Standards | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.195 - Manage Project Documentation System | Manages documentation for Manage Project Documentation System | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution
9.4.195 - Manage Project Documentation System | Oversees Manage Project Documentation System | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.195 - Manage Project Documentation System | Field coordination for Manage Project Documentation System | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.200 - Manage Submittals | Manages technical documentation for Manage Submittals | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.200 - Manage Submittals | Field coordination for Manage Submittals | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.205 - Manage RFIs (Requests for Information) | Manages technical documentation for Manage RFIs (Requests for Information) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.205 - Manage RFIs (Requests for Information) | Field coordination for Manage RFIs (Requests for Information) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.210 - Manage Meeting Minutes | Manages documentation for Manage Meeting Minutes | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution
9.4.210 - Manage Meeting Minutes | Oversees Manage Meeting Minutes | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.210 - Manage Meeting Minutes | Field coordination for Manage Meeting Minutes | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.215 - Manage Daily Reports | Manages field operations for Manage Daily Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.215 - Manage Daily Reports | Oversees Manage Daily Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.220 - Manage Drawing Logs | Manages technical documentation for Manage Drawing Logs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.220 - Manage Drawing Logs | Field coordination for Manage Drawing Logs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.225 - Manage Specifications | Manages technical documentation for Manage Specifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.225 - Manage Specifications | Field coordination for Manage Specifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.230 - Manage Correspondence | Manages documentation for Manage Correspondence | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution
9.4.230 - Manage Correspondence | Oversees Manage Correspondence | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.230 - Manage Correspondence | Field coordination for Manage Correspondence | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.235 - Manage Permits | Oversees Manage Permits | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.235 - Manage Permits | Field coordination for Manage Permits | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.240 - Manage Inspection Reports | Oversees Manage Inspection Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.240 - Manage Inspection Reports | Field coordination for Manage Inspection Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.270 - Manage Project Communications | Manages communications for Manage Project Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.270 - Manage Project Communications | Field coordination for Manage Project Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.275 - Manage Internal Communications | Manages communications for Manage Internal Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.275 - Manage Internal Communications | Field coordination for Manage Internal Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.280 - Manage External Communications | Manages communications for Manage External Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.280 - Manage External Communications | Field coordination for Manage External Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.285 - Manage Client/Owner Communications | Participates in client communications for Manage Client/Owner Communications | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution
9.4.285 - Manage Client/Owner Communications | Manages communications for Manage Client/Owner Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.285 - Manage Client/Owner Communications | Field coordination for Manage Client/Owner Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.290 - Manage Subcontractor Communications | Performs subcontracted work for Manage Subcontractor Communications | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.290 - Manage Subcontractor Communications | Manages communications for Manage Subcontractor Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.290 - Manage Subcontractor Communications | Field coordination for Manage Subcontractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.295 - Manage Vendor Supplier Communications | Manages procurement for Manage Vendor Supplier Communications | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.295 - Manage Vendor Supplier Communications | Manages communications for Manage Vendor Supplier Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.295 - Manage Vendor Supplier Communications | Field coordination for Manage Vendor Supplier Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.300 - Manage Architect/Engineer Communications | Manages communications for Manage Architect/Engineer Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.300 - Manage Architect/Engineer Communications | Field coordination for Manage Architect/Engineer Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.305 - Manage Regulatory/Authority Communications | Manages communications for Manage Regulatory/Authority Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.305 - Manage Regulatory/Authority Communications | Field coordination for Manage Regulatory/Authority Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.310 - Manage General Contractor Communications | Manages communications for Manage General Contractor Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.310 - Manage General Contractor Communications | Field coordination for Manage General Contractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.315 - Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.315 - Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.315 - Develop Project Schedule | Field coordination for Develop Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.320 - Update Project Schedule | Coordinates scheduling for Update Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.320 - Update Project Schedule | Oversees Update Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.320 - Update Project Schedule | Field coordination for Update Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.325 - Monitor Schedule Performance | Coordinates scheduling for Monitor Schedule Performance | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.325 - Monitor Schedule Performance | Oversees Monitor Schedule Performance | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.325 - Monitor Schedule Performance | Field coordination for Monitor Schedule Performance | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.330 - Develop Schedule Recovery Plans | Coordinates scheduling for Develop Schedule Recovery Plans | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.330 - Develop Schedule Recovery Plans | Oversees Develop Schedule Recovery Plans | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.330 - Develop Schedule Recovery Plans | Field coordination for Develop Schedule Recovery Plans | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.335 - Prepare Lookahead Schedules | Coordinates scheduling for Prepare Lookahead Schedules | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.335 - Prepare Lookahead Schedules | Oversees Prepare Lookahead Schedules | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.335 - Prepare Lookahead Schedules | Field coordination for Prepare Lookahead Schedules | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.340 - Manage Resource-Loaded Schedules | Coordinates scheduling for Manage Resource-Loaded Schedules | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.340 - Manage Resource-Loaded Schedules | Oversees Manage Resource-Loaded Schedules | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.340 - Manage Resource-Loaded Schedules | Field coordination for Manage Resource-Loaded Schedules | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.345 - Conduct Schedule Review Meetings | Coordinates scheduling for Conduct Schedule Review Meetings | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.345 - Conduct Schedule Review Meetings | Oversees Conduct Schedule Review Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.345 - Conduct Schedule Review Meetings | Field coordination for Conduct Schedule Review Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.350 - Manage Schedule Change Requests | Coordinates scheduling for Manage Schedule Change Requests | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.350 - Manage Schedule Change Requests | Oversees Manage Schedule Change Requests | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.350 - Manage Schedule Change Requests | Field coordination for Manage Schedule Change Requests | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.355 - Manage Project Scope | Manages contract changes for Manage Project Scope | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.355 - Manage Project Scope | Field coordination for Manage Project Scope | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.360 - Manage Change Orders | Manages contract changes for Manage Change Orders | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.360 - Manage Change Orders | Field coordination for Manage Change Orders | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.365 - Manage Potential Change Orders (PCOs) | Manages contract changes for Manage Potential Change Orders (PCOs) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.365 - Manage Potential Change Orders (PCOs) | Field coordination for Manage Potential Change Orders (PCOs) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.370 - Manage Owner Directives | Participates in client communications for Manage Owner Directives | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution
9.4.370 - Manage Owner Directives | Oversees Manage Owner Directives | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.370 - Manage Owner Directives | Field coordination for Manage Owner Directives | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.375 - Manage Scope Clarifications | Manages contract changes for Manage Scope Clarifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.375 - Manage Scope Clarifications | Field coordination for Manage Scope Clarifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.380 - Manage Backcharges | Manages contract changes for Manage Backcharges | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.380 - Manage Backcharges | Field coordination for Manage Backcharges | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.385 - Manage Force Account Work | Manages contract changes for Manage Force Account Work | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.385 - Manage Force Account Work | Field coordination for Manage Force Account Work | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.390 - Manage Claims | Provides executive approval for Manage Claims | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution
9.4.390 - Manage Claims | Oversees Manage Claims | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.390 - Manage Claims | Field coordination for Manage Claims | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.400 - Monitor Project Costs | Provides financial support for Monitor Project Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.400 - Monitor Project Costs | Oversees Monitor Project Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.400 - Monitor Project Costs | Field coordination for Monitor Project Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.405 - Manage Cost Forecasts | Provides financial support for Manage Cost Forecasts | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.405 - Manage Cost Forecasts | Oversees Manage Cost Forecasts | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.405 - Manage Cost Forecasts | Field coordination for Manage Cost Forecasts | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.410 - Manage Cost Codes | Manages financial documentation for Manage Cost Codes | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.410 - Manage Cost Codes | Oversees Manage Cost Codes | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.410 - Manage Cost Codes | Field coordination for Manage Cost Codes | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.415 - Manage Committed Costs | Provides financial support for Manage Committed Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.415 - Manage Committed Costs | Oversees Manage Committed Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.415 - Manage Committed Costs | Field coordination for Manage Committed Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.420 - Manage Actual Costs | Provides financial support for Manage Actual Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.420 - Manage Actual Costs | Oversees Manage Actual Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.420 - Manage Actual Costs | Field coordination for Manage Actual Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.425 - Manage Job Cost Reports | Manages financial documentation for Manage Job Cost Reports | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.425 - Manage Job Cost Reports | Oversees Manage Job Cost Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.425 - Manage Job Cost Reports | Field coordination for Manage Job Cost Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.430 - Manage Profit Projections | Provides financial support for Manage Profit Projections | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.430 - Manage Profit Projections | Oversees Manage Profit Projections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.430 - Manage Profit Projections | Field coordination for Manage Profit Projections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.435 - Manage Cost-to-Complete | Provides financial support for Manage Cost-to-Complete | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.435 - Manage Cost-to-Complete | Oversees Manage Cost-to-Complete | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.435 - Manage Cost-to-Complete | Field coordination for Manage Cost-to-Complete | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.440 - Prepare Billing Schedule | Manages financial documentation for Prepare Billing Schedule | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.440 - Prepare Billing Schedule | Coordinates scheduling for Prepare Billing Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.440 - Prepare Billing Schedule | Oversees Prepare Billing Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.440 - Prepare Billing Schedule | Field coordination for Prepare Billing Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.445 - Prepare Monthly Pay Applications | Manages financial documentation for Prepare Monthly Pay Applications | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.445 - Prepare Monthly Pay Applications | Oversees Prepare Monthly Pay Applications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.445 - Prepare Monthly Pay Applications | Field coordination for Prepare Monthly Pay Applications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.450 - Track Accounts Receivable | Manages financial documentation for Track Accounts Receivable | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.450 - Track Accounts Receivable | Oversees Track Accounts Receivable | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.450 - Track Accounts Receivable | Field coordination for Track Accounts Receivable | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.455 - Manage Lien Waivers | Oversees Manage Lien Waivers | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.455 - Manage Lien Waivers | Field coordination for Manage Lien Waivers | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.460 - Manage Retainage | Manages financial documentation for Manage Retainage | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.460 - Manage Retainage | Oversees Manage Retainage | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.460 - Manage Retainage | Field coordination for Manage Retainage | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.465 - Manage Final Invoicing | Oversees Manage Final Invoicing | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.465 - Manage Final Invoicing | Field coordination for Manage Final Invoicing | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.475 - Conduct Safety Orientation | Leads safety activities for Conduct Safety Orientation | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.475 - Conduct Safety Orientation | Oversees Conduct Safety Orientation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.475 - Conduct Safety Orientation | Field coordination for Conduct Safety Orientation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.480 - Conduct Safety Inspections | Leads safety activities for Conduct Safety Inspections | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.480 - Conduct Safety Inspections | Oversees Conduct Safety Inspections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.480 - Conduct Safety Inspections | Field coordination for Conduct Safety Inspections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.485 - Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.485 - Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.485 - Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.490 - Report Safety Incidents | Leads safety activities for Report Safety Incidents | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.490 - Report Safety Incidents | Oversees Report Safety Incidents | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.490 - Report Safety Incidents | Field coordination for Report Safety Incidents | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.495 - Investigate Accidents | Leads safety activities for Investigate Accidents | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.495 - Investigate Accidents | Oversees Investigate Accidents | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.495 - Investigate Accidents | Field coordination for Investigate Accidents | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.500 - Conduct Emergency Preparedness | Leads safety activities for Conduct Emergency Preparedness | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.500 - Conduct Emergency Preparedness | Oversees Conduct Emergency Preparedness | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.500 - Conduct Emergency Preparedness | Field coordination for Conduct Emergency Preparedness | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.505 - Conduct Safety Compliance Audits | Reviews for safety compliance for Conduct Safety Compliance Audits | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.505 - Conduct Safety Compliance Audits | Oversees Conduct Safety Compliance Audits | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.505 - Conduct Safety Compliance Audits | Field coordination for Conduct Safety Compliance Audits | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.510 - Provide Safety Training | Reviews for safety compliance for Provide Safety Training | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.510 - Provide Safety Training | Oversees Provide Safety Training | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.510 - Provide Safety Training | Field coordination for Provide Safety Training | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.515 - Develop Quality Management Plan | Performs quality activities for Develop Quality Management Plan | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.515 - Develop Quality Management Plan | Oversees Develop Quality Management Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.515 - Develop Quality Management Plan | Field coordination for Develop Quality Management Plan | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.520 - Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.520 - Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.520 - Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.525 - Conduct Quality Inspections | Performs quality activities for Conduct Quality Inspections | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.525 - Conduct Quality Inspections | Oversees Conduct Quality Inspections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.525 - Conduct Quality Inspections | Field coordination for Conduct Quality Inspections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.530 - Manage Quality Testing | Provides quality oversight for Manage Quality Testing | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.530 - Manage Quality Testing | Oversees Manage Quality Testing | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.530 - Manage Quality Testing | Field coordination for Manage Quality Testing | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.535 - Manage Nonconformance Reports (NCRs) | Performs quality activities for Manage Nonconformance Reports (NCRs) | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.535 - Manage Nonconformance Reports (NCRs) | Oversees Manage Nonconformance Reports (NCRs) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.535 - Manage Nonconformance Reports (NCRs) | Field coordination for Manage Nonconformance Reports (NCRs) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.540 - Manage Quality Records | Provides quality oversight for Manage Quality Records | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.540 - Manage Quality Records | Oversees Manage Quality Records | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.540 - Manage Quality Records | Field coordination for Manage Quality Records | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.545 - Manage Punch List Quality | Provides quality oversight for Manage Punch List Quality | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.545 - Manage Punch List Quality | Oversees Manage Punch List Quality | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.545 - Manage Punch List Quality | Field coordination for Manage Punch List Quality | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.560 - Manage Manpower Allocation | Manages field operations for Manage Manpower Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.560 - Manage Manpower Allocation | Oversees Manage Manpower Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.565 - Manage Equipment Allocation | Oversees Manage Equipment Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.565 - Manage Equipment Allocation | Field coordination for Manage Equipment Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.570 - Manage Material Allocation | Oversees Manage Material Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.570 - Manage Material Allocation | Field coordination for Manage Material Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.576 - Manage Subcontractor Resources | Performs subcontracted work for Manage Subcontractor Resources | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.576 - Manage Subcontractor Resources | Oversees Manage Subcontractor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.576 - Manage Subcontractor Resources | Field coordination for Manage Subcontractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.580 - Manage Vendor Resources | Manages procurement for Manage Vendor Resources | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.580 - Manage Vendor Resources | Oversees Manage Vendor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.580 - Manage Vendor Resources | Field coordination for Manage Vendor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.585 - Plan Prefabrication Resources | Coordinates prefabrication for Plan Prefabrication Resources | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.585 - Plan Prefabrication Resources | Oversees Plan Prefabrication Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.585 - Plan Prefabrication Resources | Field coordination for Plan Prefabrication Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.590 - Manage Specialty Contractor Resources | Oversees Manage Specialty Contractor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.590 - Manage Specialty Contractor Resources | Field coordination for Manage Specialty Contractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.595 - Prepare Resource Reports | Oversees Prepare Resource Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.595 - Prepare Resource Reports | Field coordination for Prepare Resource Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.605 - Issue Purchase Orders | Manages procurement for Issue Purchase Orders | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.605 - Issue Purchase Orders | Oversees Issue Purchase Orders | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.605 - Issue Purchase Orders | Field coordination for Issue Purchase Orders | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.610 - Manage Vendor Prequalification | Manages procurement for Manage Vendor Prequalification | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.610 - Manage Vendor Prequalification | Oversees Manage Vendor Prequalification | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.610 - Manage Vendor Prequalification | Field coordination for Manage Vendor Prequalification | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.615 - Manage Vendor Evaluations | Manages procurement for Manage Vendor Evaluations | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.615 - Manage Vendor Evaluations | Oversees Manage Vendor Evaluations | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.615 - Manage Vendor Evaluations | Field coordination for Manage Vendor Evaluations | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.620 - Manage Expediting | Manages procurement for Manage Expediting | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.620 - Manage Expediting | Oversees Manage Expediting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.620 - Manage Expediting | Field coordination for Manage Expediting | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.625 - Manage Delivery Tracking | Manages procurement for Manage Delivery Tracking | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.625 - Manage Delivery Tracking | Oversees Manage Delivery Tracking | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.625 - Manage Delivery Tracking | Field coordination for Manage Delivery Tracking | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.630 - Manage Material Receiving | Manages procurement for Manage Material Receiving | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.630 - Manage Material Receiving | Oversees Manage Material Receiving | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.630 - Manage Material Receiving | Field coordination for Manage Material Receiving | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.631 - Release of Large Feeder Wire | Oversees Release of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.631 - Release of Large Feeder Wire | Field coordination for Release of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.635 - Manage Material Inspection | Oversees Manage Material Inspection | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.635 - Manage Material Inspection | Field coordination for Manage Material Inspection | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.640 - Manage Storage and Logistics | Oversees Manage Storage and Logistics | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.640 - Manage Storage and Logistics | Field coordination for Manage Storage and Logistics | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.645 - Manage Material Handling | Oversees Manage Material Handling | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.645 - Manage Material Handling | Field coordination for Manage Material Handling | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.650 - Manage Inventory | Manages procurement for Manage Inventory | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.650 - Manage Inventory | Oversees Manage Inventory | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.650 - Manage Inventory | Field coordination for Manage Inventory | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.655 - Prepare Procurement Reports | Manages procurement for Prepare Procurement Reports | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.655 - Prepare Procurement Reports | Oversees Prepare Procurement Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.655 - Prepare Procurement Reports | Field coordination for Prepare Procurement Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.660 - Manage Procurement Closeout | Manages procurement for Manage Procurement Closeout | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.660 - Manage Procurement Closeout | Oversees closeout for Manage Procurement Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.660 - Manage Procurement Closeout | Field coordination for Manage Procurement Closeout | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.665 - Reconcile Procurement Accounts | Manages procurement for Reconcile Procurement Accounts | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.665 - Reconcile Procurement Accounts | Manages financial documentation for Reconcile Procurement Accounts | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.665 - Reconcile Procurement Accounts | Oversees Reconcile Procurement Accounts | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.665 - Reconcile Procurement Accounts | Field coordination for Reconcile Procurement Accounts | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.670 - Manage Vendor Closeout | Manages procurement for Manage Vendor Closeout | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.670 - Manage Vendor Closeout | Oversees closeout for Manage Vendor Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.670 - Manage Vendor Closeout | Field coordination for Manage Vendor Closeout | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.675 - Conduct Daily Huddles | Leads crew activities for Conduct Daily Huddles | Foreman | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.675 - Conduct Daily Huddles | Oversees Conduct Daily Huddles | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.675 - Conduct Daily Huddles | Field coordination for Conduct Daily Huddles | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.680 - Conduct Weekly Foreman Meetings | Leads crew activities for Conduct Weekly Foreman Meetings | Foreman | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.680 - Conduct Weekly Foreman Meetings | Oversees Conduct Weekly Foreman Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.680 - Conduct Weekly Foreman Meetings | Field coordination for Conduct Weekly Foreman Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.690 - Track Manpower Utilization | Manages field operations for Track Manpower Utilization | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.690 - Track Manpower Utilization | Oversees Track Manpower Utilization | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.695 - Track Production Quantities | Manages field operations for Track Production Quantities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.695 - Track Production Quantities | Oversees Track Production Quantities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.700 - Track Equipment Utilization | Oversees Track Equipment Utilization | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.700 - Track Equipment Utilization | Field coordination for Track Equipment Utilization | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.705 - Manage Work Packaging | Oversees Manage Work Packaging | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.705 - Manage Work Packaging | Field coordination for Manage Work Packaging | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.710 - Manage Workface Planning | Oversees Manage Workface Planning | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.710 - Manage Workface Planning | Field coordination for Manage Workface Planning | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.715 - Manage Field Coordination | Manages field operations for Manage Field Coordination | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.715 - Manage Field Coordination | Oversees Manage Field Coordination | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.720 - Conduct Productivity Analysis | Oversees Conduct Productivity Analysis | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.720 - Conduct Productivity Analysis | Field coordination for Conduct Productivity Analysis | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.725 - Resolve Field Problems | Manages field operations for Resolve Field Problems | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.725 - Resolve Field Problems | Oversees Resolve Field Problems | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.735 - Perform Field Quality Verifications | Provides quality oversight for Perform Field Quality Verifications | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.735 - Perform Field Quality Verifications | Oversees Perform Field Quality Verifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.735 - Perform Field Quality Verifications | Field coordination for Perform Field Quality Verifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.745 - Manage Field Rework | Manages field operations for Manage Field Rework | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.4.745 - Manage Field Rework | Oversees Manage Field Rework | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.755 - Implement Field Productivity Improvements | Oversees Implement Field Productivity Improvements | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution
9.4.755 - Implement Field Productivity Improvements | Field coordination for Implement Field Productivity Improvements | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution
9.5.020 - Handling and/or Disposing of Excess Materials | Leads meeting coordination; Tracks commissioning progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning
9.5.020 - Handling and/or Disposing of Excess Materials | Conducts testing; Documents results; Identifies deficiencies ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.020 - Handling and/or Disposing of Excess Materials | Supports testing activities; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning
9.5.020 - Handling and/or Disposing of Excess Materials | Verifies quality requirements; Reviews test results ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | Covered | No change required. | 5 - Commissioning
9.5.020 - Handling and/or Disposing of Excess Materials | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Overall commissioning management; Schedule coordination ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Supports testing; Ensures systems ready; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Executes testing protocols; Documents results ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Verifies compliance; Reviews documentation ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.6.005 - Prepare for Turnover (Field Perspective) | Oversees closeout for Prepare for Turnover (Field Perspective) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | Leads closeout meetings; Tracks closeout progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | Reports field status; Coordinates punch completion ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | Participate; Complete their closeout requirements ¦ | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Client/Owner | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.015 - Manage Project Turnover Documentation | Oversees closeout for Manage Project Turnover Documentation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.020 - Manage Punch List Closeout | Provides quality oversight for Manage Punch List Closeout | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.020 - Manage Punch List Closeout | Oversees closeout for Manage Punch List Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | Manages as-built process; Submits final drawings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | Reviews markups for accuracy; Coordinates with field ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | Creates field markups; Documents actual conditions ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Engineer/APM | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.035 - Submit Warranties | Oversees Submit Warranties | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.040 - Submit O&M Manuals | Oversees closeout for Submit O&M Manuals | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.050 - Provide Owner Training | Participates in client communications for Provide Owner Training | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 6 - Closeout
9.6.050 - Provide Owner Training | Oversees Provide Owner Training | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.065 - Archive Project Documentation | Manages documentation for Archive Project Documentation | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 6 - Closeout
9.6.065 - Archive Project Documentation | Oversees Archive Project Documentation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | Oversees review process; Approves action items ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | Leads review meeting; Compiles findings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | Provides field perspective; Shares observations ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | Oversees feedback process; Reviews results ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | Conducts feedback meeting; Documents responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | Uses feedback for relationship management ¦ | ¦ Business Development | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Executive Committee | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | Maintains lessons learned database; Ensures implementation ¦ | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | Documents project-specific lessons; Submits for review ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | Captures field-level learnings; Contributes to documentation ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout

## RACI Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | RACI
9.1.050 - Prepare Construction Takeoff | Oversees Prepare Construction Takeoff | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 1 - Estimating | R
9.2.005 - Review Contract for High Risk Clauses | Oversees Review Contract for High Risk Clauses | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.010 - Team Selection | Selects Project Manager and assigns or approves final team assignments; Allocates resources across projects; Resolves resource conflicts. | Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 2 - Preconstruction | A
9.2.010 - Team Selection | Identifies required roles and skill sets; Recommends team members; Coordinates with Branch Manager on availability. | Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | R
9.2.010 - Team Selection | Validates field leadership assignments; Confirms crew availability and capability | General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.010 - Team Selection | Ensures safety-qualified personnel are assigned, Reviews site-specific safety requirements. | Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.010 - Team Selection | Informed of procurement resource needs | Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 2 - Preconstruction | I
9.2.010 - Team Selection | Informed of prefab support requirements | Prefabrication Lead | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction | I
9.2.010 - Team Selection | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction | I
9.2.015 - Project Turnover Meeting | Oversees closeout for Project Turnover Meeting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.020 - Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.020 - Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | Oversees Review Contract for Unfavorable or High-Risk Clauses | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.040 - Project Manager Reviews Plans Specifications & Schedule | Coordinates scheduling for Project Manager Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.040 - Project Manager Reviews Plans Specifications & Schedule | Manages technical documentation for Project Manager Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | Coordinates scheduling for Field Supervisor Reviews Plans Specifications & Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | Manages technical documentation for Field Supervisor Reviews Plans Specifications & Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.055 - Compare Estimated vs Planned Performance | Provides estimating support for Compare Estimated vs Planned Performance | Estimator | Sec. 9.9 Estimating Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.055 - Compare Estimated vs Planned Performance | Oversees Compare Estimated vs Planned Performance | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.057 - Identify VE and Prefabrication Opportunities | Coordinates prefabrication for Identify VE and Prefabrication Opportunities | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.057 - Identify VE and Prefabrication Opportunities | Oversees Identify VE and Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.060 - Create Issue List and Begin RFI Process | Manages overall issue resolution; Prioritizes RFIs; Tracks responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | A
9.2.060 - Create Issue List and Begin RFI Process | Creates and submits RFIs; Maintains issue log; Follows up on responses ¦ | ¦ Assistant PM/Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction | R
9.2.060 - Create Issue List and Begin RFI Process | Contributes constructability issues; Reviews RFI responses for field impact ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction | C
9.2.060 - Create Issue List and Begin RFI Process | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.070 - Conduct Site Visit | Coordinates site visit; Documents findings; Integrates into project planning ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | A
9.2.070 - Conduct Site Visit | Conducts physical site inspection; Identifies constructability and logistics issues ¦ | ¦ Field Leadership | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction | R
9.2.070 - Conduct Site Visit | Assesses site safety conditions; Identifies hazards and requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction | R
9.2.070 - Conduct Site Visit | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.080 - Prepare Material Handling Plan | Oversees Prepare Material Handling Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.090 - Develop Labor Budget | Provides financial support for Develop Labor Budget | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.090 - Develop Labor Budget | Oversees Develop Labor Budget | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.100 - Prepare Layout & Sequencing Plan | Oversees Prepare Layout & Sequencing Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.110 - Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.110 - Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.120 - Establish Tracking & Control Systems | Oversees Establish Tracking & Control Systems | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.130 - Construction Execution Kickoff Meeting | Leads coordination for Construction Execution Kickoff Meeting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.140 - Develop Project Budget | Provides financial support for Develop Project Budget | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 2 - Preconstruction | C
9.2.140 - Develop Project Budget | Oversees Develop Project Budget | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.2.160 - Develop Procurement Plan | Manages procurement for Develop Procurement Plan | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 2 - Preconstruction | R
9.2.160 - Develop Procurement Plan | Oversees Develop Procurement Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 2 - Preconstruction | A
9.3.010 - Setup Office Trailer | Approves trailer location and configuration; Coordinates delivery timing ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization | A
9.3.010 - Setup Office Trailer | Oversees physical setup; Coordinates with delivery vendor; Ensures utility connections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | R
9.3.010 - Setup Office Trailer | Sets up office equipment and supplies; Establishes filing systems ¦ | ¦ Site Administrator | Sec. 9.8 Site Administration | Covered | No change required. | 3 - Mobilization | R
9.3.010 - Setup Office Trailer | Reviews placement for safety compliance; Ensures egress requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization | C
9.3.010 - Setup Office Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 3 - Mobilization | C
9.3.020 - Setup Storage Trailer | Oversees setup and organization; Establishes security protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | A
9.3.020 - Setup Storage Trailer | Coordinates physical placement; Organizes interior layout ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | R
9.3.020 - Setup Storage Trailer | Coordinates material delivery timing with storage availability ¦ | ¦ Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 3 - Mobilization | C
9.3.020 - Setup Storage Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization | C
9.3.030 - Setup Site Fencing and Access Control | Oversees fencing installation; Establishes access protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | A
9.3.030 - Setup Site Fencing and Access Control | Coordinates installation; Manages gate operations ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | R
9.3.030 - Setup Site Fencing and Access Control | Defines safety requirements; Reviews emergency egress ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization | R
9.3.030 - Setup Site Fencing and Access Control | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization | C
9.3.040 - Setup Temporary Power | Oversees installation; Ensures code compliance ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | A
9.3.040 - Setup Temporary Power | Installs temporary power system; Makes connections ¦ | ¦ Foreman/Journeyman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization | R
9.3.040 - Setup Temporary Power | Reviews safety requirements; Verifies GFCI protection ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization | C
9.3.040 - Setup Temporary Power | Coordinates with utility company; Approves power plan ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization | C
9.3.040 - Setup Temporary Power | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Electrical Subcontractor | Sec. 9.2 General Directives | Covered | No change required. | 3 - Mobilization | R
9.3.050 - Setup Temporary Water | Coordinates site setup for Setup Temporary Water | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.050 - Setup Temporary Water | Oversees Setup Temporary Water | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.060 - Setup Sanitary Facilities | Coordinates site setup for Setup Sanitary Facilities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.060 - Setup Sanitary Facilities | Oversees Setup Sanitary Facilities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.070 - Setup Temporary Lighting | Coordinates site setup for Setup Temporary Lighting | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.070 - Setup Temporary Lighting | Oversees Setup Temporary Lighting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.080 - Setup Signage | Coordinates site setup for Setup Signage | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.080 - Setup Signage | Oversees Setup Signage | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.090 - Setup Security | Coordinates site setup for Setup Security | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.090 - Setup Security | Oversees Setup Security | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.100 - Setup Laydown Area | Coordinates site setup for Setup Laydown Area | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.100 - Setup Laydown Area | Oversees Setup Laydown Area | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.110 - Setup Equipment Staging | Coordinates site setup for Setup Equipment Staging | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.110 - Setup Equipment Staging | Oversees Setup Equipment Staging | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.120 - Setup Parking | Coordinates site setup for Setup Parking | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.120 - Setup Parking | Oversees Setup Parking | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.470 - Develop Site-Specific Safety Plan | Reviews for safety compliance for Develop Site-Specific Safety Plan | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 3 - Mobilization | C
9.3.470 - Develop Site-Specific Safety Plan | Oversees Develop Site-Specific Safety Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 3 - Mobilization | R
9.3.470 - Develop Site-Specific Safety Plan | Field coordination for Develop Site-Specific Safety Plan | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 3 - Mobilization | C
9.4.010 - Conduct Coordination Meetings | Leads coordination for Conduct Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.010 - Conduct Coordination Meetings | Field coordination for Conduct Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.020 - Conduct Subcontractor Coordination Meetings | Performs subcontracted work for Conduct Subcontractor Coordination Meetings | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.020 - Conduct Subcontractor Coordination Meetings | Leads coordination for Conduct Subcontractor Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.020 - Conduct Subcontractor Coordination Meetings | Field coordination for Conduct Subcontractor Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.030 - Conduct Client/Owner Meetings | Participates in client communications for Conduct Client/Owner Meetings | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution | C
9.4.030 - Conduct Client/Owner Meetings | Oversees Conduct Client/Owner Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.030 - Conduct Client/Owner Meetings | Field coordination for Conduct Client/Owner Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.040 - Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.040 - Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.040 - Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Coordinates prefabrication for Identify Value Engineering & Prefabrication Opportunities | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Oversees Identify Value Engineering & Prefabrication Opportunities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.045 - Identify Value Engineering & Prefabrication Opportunities | Field coordination for Identify Value Engineering & Prefabrication Opportunities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.050 - Conduct Prefabrication Coordination Meetings | Coordinates prefabrication for Conduct Prefabrication Coordination Meetings | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.050 - Conduct Prefabrication Coordination Meetings | Leads coordination for Conduct Prefabrication Coordination Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.050 - Conduct Prefabrication Coordination Meetings | Field coordination for Conduct Prefabrication Coordination Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.055 - Procurement of Large Feeder Wire | Manages procurement for Procurement of Large Feeder Wire | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.055 - Procurement of Large Feeder Wire | Oversees Procurement of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.055 - Procurement of Large Feeder Wire | Field coordination for Procurement of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.060 - Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.060 - Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.060 - Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.190 - Document Filing Standards | Manages documentation for Document Filing Standards | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution | R
9.4.190 - Document Filing Standards | Oversees Document Filing Standards | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.190 - Document Filing Standards | Field coordination for Document Filing Standards | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.195 - Manage Project Documentation System | Manages documentation for Manage Project Documentation System | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution | R
9.4.195 - Manage Project Documentation System | Oversees Manage Project Documentation System | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.195 - Manage Project Documentation System | Field coordination for Manage Project Documentation System | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.200 - Manage Submittals | Manages technical documentation for Manage Submittals | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.200 - Manage Submittals | Field coordination for Manage Submittals | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.205 - Manage RFIs (Requests for Information) | Manages technical documentation for Manage RFIs (Requests for Information) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.205 - Manage RFIs (Requests for Information) | Field coordination for Manage RFIs (Requests for Information) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.210 - Manage Meeting Minutes | Manages documentation for Manage Meeting Minutes | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution | R
9.4.210 - Manage Meeting Minutes | Oversees Manage Meeting Minutes | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.210 - Manage Meeting Minutes | Field coordination for Manage Meeting Minutes | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.215 - Manage Daily Reports | Manages field operations for Manage Daily Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.215 - Manage Daily Reports | Oversees Manage Daily Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.220 - Manage Drawing Logs | Manages technical documentation for Manage Drawing Logs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.220 - Manage Drawing Logs | Field coordination for Manage Drawing Logs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.225 - Manage Specifications | Manages technical documentation for Manage Specifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.225 - Manage Specifications | Field coordination for Manage Specifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.230 - Manage Correspondence | Manages documentation for Manage Correspondence | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 4 - Execution | R
9.4.230 - Manage Correspondence | Oversees Manage Correspondence | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.230 - Manage Correspondence | Field coordination for Manage Correspondence | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.235 - Manage Permits | Oversees Manage Permits | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.235 - Manage Permits | Field coordination for Manage Permits | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.240 - Manage Inspection Reports | Oversees Manage Inspection Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.240 - Manage Inspection Reports | Field coordination for Manage Inspection Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.270 - Manage Project Communications | Manages communications for Manage Project Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.270 - Manage Project Communications | Field coordination for Manage Project Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.275 - Manage Internal Communications | Manages communications for Manage Internal Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.275 - Manage Internal Communications | Field coordination for Manage Internal Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.280 - Manage External Communications | Manages communications for Manage External Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.280 - Manage External Communications | Field coordination for Manage External Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.285 - Manage Client/Owner Communications | Participates in client communications for Manage Client/Owner Communications | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution | C
9.4.285 - Manage Client/Owner Communications | Manages communications for Manage Client/Owner Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.285 - Manage Client/Owner Communications | Field coordination for Manage Client/Owner Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.290 - Manage Subcontractor Communications | Performs subcontracted work for Manage Subcontractor Communications | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.290 - Manage Subcontractor Communications | Manages communications for Manage Subcontractor Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.290 - Manage Subcontractor Communications | Field coordination for Manage Subcontractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.295 - Manage Vendor Supplier Communications | Manages procurement for Manage Vendor Supplier Communications | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.295 - Manage Vendor Supplier Communications | Manages communications for Manage Vendor Supplier Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.295 - Manage Vendor Supplier Communications | Field coordination for Manage Vendor Supplier Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.300 - Manage Architect/Engineer Communications | Manages communications for Manage Architect/Engineer Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.300 - Manage Architect/Engineer Communications | Field coordination for Manage Architect/Engineer Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.305 - Manage Regulatory/Authority Communications | Manages communications for Manage Regulatory/Authority Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.305 - Manage Regulatory/Authority Communications | Field coordination for Manage Regulatory/Authority Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.310 - Manage General Contractor Communications | Manages communications for Manage General Contractor Communications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.310 - Manage General Contractor Communications | Field coordination for Manage General Contractor Communications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.315 - Develop Project Schedule | Coordinates scheduling for Develop Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.315 - Develop Project Schedule | Oversees Develop Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.315 - Develop Project Schedule | Field coordination for Develop Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.320 - Update Project Schedule | Coordinates scheduling for Update Project Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.320 - Update Project Schedule | Oversees Update Project Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.320 - Update Project Schedule | Field coordination for Update Project Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.325 - Monitor Schedule Performance | Coordinates scheduling for Monitor Schedule Performance | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.325 - Monitor Schedule Performance | Oversees Monitor Schedule Performance | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.325 - Monitor Schedule Performance | Field coordination for Monitor Schedule Performance | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.330 - Develop Schedule Recovery Plans | Coordinates scheduling for Develop Schedule Recovery Plans | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.330 - Develop Schedule Recovery Plans | Oversees Develop Schedule Recovery Plans | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.330 - Develop Schedule Recovery Plans | Field coordination for Develop Schedule Recovery Plans | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.335 - Prepare Lookahead Schedules | Coordinates scheduling for Prepare Lookahead Schedules | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.335 - Prepare Lookahead Schedules | Oversees Prepare Lookahead Schedules | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.335 - Prepare Lookahead Schedules | Field coordination for Prepare Lookahead Schedules | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.340 - Manage Resource-Loaded Schedules | Coordinates scheduling for Manage Resource-Loaded Schedules | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.340 - Manage Resource-Loaded Schedules | Oversees Manage Resource-Loaded Schedules | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.340 - Manage Resource-Loaded Schedules | Field coordination for Manage Resource-Loaded Schedules | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.345 - Conduct Schedule Review Meetings | Coordinates scheduling for Conduct Schedule Review Meetings | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.345 - Conduct Schedule Review Meetings | Oversees Conduct Schedule Review Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.345 - Conduct Schedule Review Meetings | Field coordination for Conduct Schedule Review Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.350 - Manage Schedule Change Requests | Coordinates scheduling for Manage Schedule Change Requests | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.350 - Manage Schedule Change Requests | Oversees Manage Schedule Change Requests | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.350 - Manage Schedule Change Requests | Field coordination for Manage Schedule Change Requests | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.355 - Manage Project Scope | Manages contract changes for Manage Project Scope | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.355 - Manage Project Scope | Field coordination for Manage Project Scope | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.360 - Manage Change Orders | Manages contract changes for Manage Change Orders | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.360 - Manage Change Orders | Field coordination for Manage Change Orders | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.365 - Manage Potential Change Orders (PCOs) | Manages contract changes for Manage Potential Change Orders (PCOs) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.365 - Manage Potential Change Orders (PCOs) | Field coordination for Manage Potential Change Orders (PCOs) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.370 - Manage Owner Directives | Participates in client communications for Manage Owner Directives | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution | C
9.4.370 - Manage Owner Directives | Oversees Manage Owner Directives | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.370 - Manage Owner Directives | Field coordination for Manage Owner Directives | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.375 - Manage Scope Clarifications | Manages contract changes for Manage Scope Clarifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.375 - Manage Scope Clarifications | Field coordination for Manage Scope Clarifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.380 - Manage Backcharges | Manages contract changes for Manage Backcharges | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.380 - Manage Backcharges | Field coordination for Manage Backcharges | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.385 - Manage Force Account Work | Manages contract changes for Manage Force Account Work | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.385 - Manage Force Account Work | Field coordination for Manage Force Account Work | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.390 - Manage Claims | Provides executive approval for Manage Claims | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 4 - Execution | A
9.4.390 - Manage Claims | Oversees Manage Claims | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.390 - Manage Claims | Field coordination for Manage Claims | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.400 - Monitor Project Costs | Provides financial support for Monitor Project Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.400 - Monitor Project Costs | Oversees Monitor Project Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.400 - Monitor Project Costs | Field coordination for Monitor Project Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.405 - Manage Cost Forecasts | Provides financial support for Manage Cost Forecasts | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.405 - Manage Cost Forecasts | Oversees Manage Cost Forecasts | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.405 - Manage Cost Forecasts | Field coordination for Manage Cost Forecasts | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.410 - Manage Cost Codes | Manages financial documentation for Manage Cost Codes | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.410 - Manage Cost Codes | Oversees Manage Cost Codes | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.410 - Manage Cost Codes | Field coordination for Manage Cost Codes | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.415 - Manage Committed Costs | Provides financial support for Manage Committed Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.415 - Manage Committed Costs | Oversees Manage Committed Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.415 - Manage Committed Costs | Field coordination for Manage Committed Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.420 - Manage Actual Costs | Provides financial support for Manage Actual Costs | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.420 - Manage Actual Costs | Oversees Manage Actual Costs | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.420 - Manage Actual Costs | Field coordination for Manage Actual Costs | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.425 - Manage Job Cost Reports | Manages financial documentation for Manage Job Cost Reports | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.425 - Manage Job Cost Reports | Oversees Manage Job Cost Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.425 - Manage Job Cost Reports | Field coordination for Manage Job Cost Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.430 - Manage Profit Projections | Provides financial support for Manage Profit Projections | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.430 - Manage Profit Projections | Oversees Manage Profit Projections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.430 - Manage Profit Projections | Field coordination for Manage Profit Projections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.435 - Manage Cost-to-Complete | Provides financial support for Manage Cost-to-Complete | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.435 - Manage Cost-to-Complete | Oversees Manage Cost-to-Complete | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.435 - Manage Cost-to-Complete | Field coordination for Manage Cost-to-Complete | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.440 - Prepare Billing Schedule | Manages financial documentation for Prepare Billing Schedule | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.440 - Prepare Billing Schedule | Coordinates scheduling for Prepare Billing Schedule | Superintendent | Sec. 9.4 Superintendent Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.440 - Prepare Billing Schedule | Oversees Prepare Billing Schedule | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.440 - Prepare Billing Schedule | Field coordination for Prepare Billing Schedule | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.445 - Prepare Monthly Pay Applications | Manages financial documentation for Prepare Monthly Pay Applications | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.445 - Prepare Monthly Pay Applications | Oversees Prepare Monthly Pay Applications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.445 - Prepare Monthly Pay Applications | Field coordination for Prepare Monthly Pay Applications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.450 - Track Accounts Receivable | Manages financial documentation for Track Accounts Receivable | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.450 - Track Accounts Receivable | Oversees Track Accounts Receivable | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.450 - Track Accounts Receivable | Field coordination for Track Accounts Receivable | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.455 - Manage Lien Waivers | Oversees Manage Lien Waivers | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.455 - Manage Lien Waivers | Field coordination for Manage Lien Waivers | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.460 - Manage Retainage | Manages financial documentation for Manage Retainage | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.460 - Manage Retainage | Oversees Manage Retainage | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.460 - Manage Retainage | Field coordination for Manage Retainage | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.465 - Manage Final Invoicing | Oversees Manage Final Invoicing | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.465 - Manage Final Invoicing | Field coordination for Manage Final Invoicing | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.475 - Conduct Safety Orientation | Leads safety activities for Conduct Safety Orientation | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.475 - Conduct Safety Orientation | Oversees Conduct Safety Orientation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.475 - Conduct Safety Orientation | Field coordination for Conduct Safety Orientation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.480 - Conduct Safety Inspections | Leads safety activities for Conduct Safety Inspections | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.480 - Conduct Safety Inspections | Oversees Conduct Safety Inspections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.480 - Conduct Safety Inspections | Field coordination for Conduct Safety Inspections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.485 - Conduct Safety Meetings | Leads safety activities for Conduct Safety Meetings | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.485 - Conduct Safety Meetings | Oversees Conduct Safety Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.485 - Conduct Safety Meetings | Field coordination for Conduct Safety Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.490 - Report Safety Incidents | Leads safety activities for Report Safety Incidents | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.490 - Report Safety Incidents | Oversees Report Safety Incidents | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.490 - Report Safety Incidents | Field coordination for Report Safety Incidents | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.495 - Investigate Accidents | Leads safety activities for Investigate Accidents | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.495 - Investigate Accidents | Oversees Investigate Accidents | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.495 - Investigate Accidents | Field coordination for Investigate Accidents | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.500 - Conduct Emergency Preparedness | Leads safety activities for Conduct Emergency Preparedness | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.500 - Conduct Emergency Preparedness | Oversees Conduct Emergency Preparedness | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.500 - Conduct Emergency Preparedness | Field coordination for Conduct Emergency Preparedness | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.505 - Conduct Safety Compliance Audits | Reviews for safety compliance for Conduct Safety Compliance Audits | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.505 - Conduct Safety Compliance Audits | Oversees Conduct Safety Compliance Audits | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.505 - Conduct Safety Compliance Audits | Field coordination for Conduct Safety Compliance Audits | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.510 - Provide Safety Training | Reviews for safety compliance for Provide Safety Training | Safety Coordinator | Sec. 9.7 Safety Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.510 - Provide Safety Training | Oversees Provide Safety Training | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.510 - Provide Safety Training | Field coordination for Provide Safety Training | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.515 - Develop Quality Management Plan | Performs quality activities for Develop Quality Management Plan | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.515 - Develop Quality Management Plan | Oversees Develop Quality Management Plan | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.515 - Develop Quality Management Plan | Field coordination for Develop Quality Management Plan | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.520 - Conduct Quality Meetings | Performs quality activities for Conduct Quality Meetings | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.520 - Conduct Quality Meetings | Oversees Conduct Quality Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.520 - Conduct Quality Meetings | Field coordination for Conduct Quality Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.525 - Conduct Quality Inspections | Performs quality activities for Conduct Quality Inspections | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.525 - Conduct Quality Inspections | Oversees Conduct Quality Inspections | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.525 - Conduct Quality Inspections | Field coordination for Conduct Quality Inspections | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.530 - Manage Quality Testing | Provides quality oversight for Manage Quality Testing | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.530 - Manage Quality Testing | Oversees Manage Quality Testing | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.530 - Manage Quality Testing | Field coordination for Manage Quality Testing | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.535 - Manage Nonconformance Reports (NCRs) | Performs quality activities for Manage Nonconformance Reports (NCRs) | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.535 - Manage Nonconformance Reports (NCRs) | Oversees Manage Nonconformance Reports (NCRs) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.535 - Manage Nonconformance Reports (NCRs) | Field coordination for Manage Nonconformance Reports (NCRs) | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.540 - Manage Quality Records | Provides quality oversight for Manage Quality Records | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.540 - Manage Quality Records | Oversees Manage Quality Records | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.540 - Manage Quality Records | Field coordination for Manage Quality Records | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.545 - Manage Punch List Quality | Provides quality oversight for Manage Punch List Quality | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.545 - Manage Punch List Quality | Oversees Manage Punch List Quality | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.545 - Manage Punch List Quality | Field coordination for Manage Punch List Quality | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.560 - Manage Manpower Allocation | Manages field operations for Manage Manpower Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.560 - Manage Manpower Allocation | Oversees Manage Manpower Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.565 - Manage Equipment Allocation | Oversees Manage Equipment Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.565 - Manage Equipment Allocation | Field coordination for Manage Equipment Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.570 - Manage Material Allocation | Oversees Manage Material Allocation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.570 - Manage Material Allocation | Field coordination for Manage Material Allocation | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.576 - Manage Subcontractor Resources | Performs subcontracted work for Manage Subcontractor Resources | Subcontractors | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.576 - Manage Subcontractor Resources | Oversees Manage Subcontractor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.576 - Manage Subcontractor Resources | Field coordination for Manage Subcontractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.580 - Manage Vendor Resources | Manages procurement for Manage Vendor Resources | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.580 - Manage Vendor Resources | Oversees Manage Vendor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.580 - Manage Vendor Resources | Field coordination for Manage Vendor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.585 - Plan Prefabrication Resources | Coordinates prefabrication for Plan Prefabrication Resources | Prefabrication Lead | Sec. 9.2 General Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.585 - Plan Prefabrication Resources | Oversees Plan Prefabrication Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.585 - Plan Prefabrication Resources | Field coordination for Plan Prefabrication Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.590 - Manage Specialty Contractor Resources | Oversees Manage Specialty Contractor Resources | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.590 - Manage Specialty Contractor Resources | Field coordination for Manage Specialty Contractor Resources | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.595 - Prepare Resource Reports | Oversees Prepare Resource Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.595 - Prepare Resource Reports | Field coordination for Prepare Resource Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.605 - Issue Purchase Orders | Manages procurement for Issue Purchase Orders | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.605 - Issue Purchase Orders | Oversees Issue Purchase Orders | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.605 - Issue Purchase Orders | Field coordination for Issue Purchase Orders | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.610 - Manage Vendor Prequalification | Manages procurement for Manage Vendor Prequalification | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.610 - Manage Vendor Prequalification | Oversees Manage Vendor Prequalification | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.610 - Manage Vendor Prequalification | Field coordination for Manage Vendor Prequalification | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.615 - Manage Vendor Evaluations | Manages procurement for Manage Vendor Evaluations | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.615 - Manage Vendor Evaluations | Oversees Manage Vendor Evaluations | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.615 - Manage Vendor Evaluations | Field coordination for Manage Vendor Evaluations | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.620 - Manage Expediting | Manages procurement for Manage Expediting | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.620 - Manage Expediting | Oversees Manage Expediting | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.620 - Manage Expediting | Field coordination for Manage Expediting | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.625 - Manage Delivery Tracking | Manages procurement for Manage Delivery Tracking | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.625 - Manage Delivery Tracking | Oversees Manage Delivery Tracking | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.625 - Manage Delivery Tracking | Field coordination for Manage Delivery Tracking | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.630 - Manage Material Receiving | Manages procurement for Manage Material Receiving | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.630 - Manage Material Receiving | Oversees Manage Material Receiving | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.630 - Manage Material Receiving | Field coordination for Manage Material Receiving | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.631 - Release of Large Feeder Wire | Oversees Release of Large Feeder Wire | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.631 - Release of Large Feeder Wire | Field coordination for Release of Large Feeder Wire | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.635 - Manage Material Inspection | Oversees Manage Material Inspection | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.635 - Manage Material Inspection | Field coordination for Manage Material Inspection | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.640 - Manage Storage and Logistics | Oversees Manage Storage and Logistics | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.640 - Manage Storage and Logistics | Field coordination for Manage Storage and Logistics | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.645 - Manage Material Handling | Oversees Manage Material Handling | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.645 - Manage Material Handling | Field coordination for Manage Material Handling | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.650 - Manage Inventory | Manages procurement for Manage Inventory | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.650 - Manage Inventory | Oversees Manage Inventory | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.650 - Manage Inventory | Field coordination for Manage Inventory | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.655 - Prepare Procurement Reports | Manages procurement for Prepare Procurement Reports | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.655 - Prepare Procurement Reports | Oversees Prepare Procurement Reports | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.655 - Prepare Procurement Reports | Field coordination for Prepare Procurement Reports | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.660 - Manage Procurement Closeout | Manages procurement for Manage Procurement Closeout | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.660 - Manage Procurement Closeout | Oversees closeout for Manage Procurement Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.660 - Manage Procurement Closeout | Field coordination for Manage Procurement Closeout | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.665 - Reconcile Procurement Accounts | Manages procurement for Reconcile Procurement Accounts | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.665 - Reconcile Procurement Accounts | Manages financial documentation for Reconcile Procurement Accounts | Accounting | Sec. 9.11 Accounting Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.665 - Reconcile Procurement Accounts | Oversees Reconcile Procurement Accounts | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.665 - Reconcile Procurement Accounts | Field coordination for Reconcile Procurement Accounts | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.670 - Manage Vendor Closeout | Manages procurement for Manage Vendor Closeout | Purchasing | Sec. 9.10 Purchasing Directives | Inferred | Verify role assignment. | 4 - Execution | R
9.4.670 - Manage Vendor Closeout | Oversees closeout for Manage Vendor Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.670 - Manage Vendor Closeout | Field coordination for Manage Vendor Closeout | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.675 - Conduct Daily Huddles | Leads crew activities for Conduct Daily Huddles | Foreman | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.675 - Conduct Daily Huddles | Oversees Conduct Daily Huddles | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.675 - Conduct Daily Huddles | Field coordination for Conduct Daily Huddles | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.680 - Conduct Weekly Foreman Meetings | Leads crew activities for Conduct Weekly Foreman Meetings | Foreman | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.680 - Conduct Weekly Foreman Meetings | Oversees Conduct Weekly Foreman Meetings | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.680 - Conduct Weekly Foreman Meetings | Field coordination for Conduct Weekly Foreman Meetings | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.690 - Track Manpower Utilization | Manages field operations for Track Manpower Utilization | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.690 - Track Manpower Utilization | Oversees Track Manpower Utilization | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.695 - Track Production Quantities | Manages field operations for Track Production Quantities | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.695 - Track Production Quantities | Oversees Track Production Quantities | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.700 - Track Equipment Utilization | Oversees Track Equipment Utilization | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.700 - Track Equipment Utilization | Field coordination for Track Equipment Utilization | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.705 - Manage Work Packaging | Oversees Manage Work Packaging | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.705 - Manage Work Packaging | Field coordination for Manage Work Packaging | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.710 - Manage Workface Planning | Oversees Manage Workface Planning | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.710 - Manage Workface Planning | Field coordination for Manage Workface Planning | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.715 - Manage Field Coordination | Manages field operations for Manage Field Coordination | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.715 - Manage Field Coordination | Oversees Manage Field Coordination | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.720 - Conduct Productivity Analysis | Oversees Conduct Productivity Analysis | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.720 - Conduct Productivity Analysis | Field coordination for Conduct Productivity Analysis | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.725 - Resolve Field Problems | Manages field operations for Resolve Field Problems | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.725 - Resolve Field Problems | Oversees Resolve Field Problems | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.735 - Perform Field Quality Verifications | Provides quality oversight for Perform Field Quality Verifications | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 4 - Execution | C
9.4.735 - Perform Field Quality Verifications | Oversees Perform Field Quality Verifications | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.735 - Perform Field Quality Verifications | Field coordination for Perform Field Quality Verifications | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.4.745 - Manage Field Rework | Manages field operations for Manage Field Rework | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | R
9.4.745 - Manage Field Rework | Oversees Manage Field Rework | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.755 - Implement Field Productivity Improvements | Oversees Implement Field Productivity Improvements | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 4 - Execution | A
9.4.755 - Implement Field Productivity Improvements | Field coordination for Implement Field Productivity Improvements | Field Supervisor | Sec. 9.3 Field Leadership | Inferred | Verify role assignment. | 4 - Execution | C
9.5.020 - Handling and/or Disposing of Excess Materials | Leads meeting coordination; Tracks commissioning progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning | A
9.5.020 - Handling and/or Disposing of Excess Materials | Conducts testing; Documents results; Identifies deficiencies ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.020 - Handling and/or Disposing of Excess Materials | Supports testing activities; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning | R
9.5.020 - Handling and/or Disposing of Excess Materials | Verifies quality requirements; Reviews test results ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | Covered | No change required. | 5 - Commissioning | C
9.5.020 - Handling and/or Disposing of Excess Materials | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | Overall commissioning management; Schedule coordination ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning | A
9.5.550 - Manage Commissioning Activities | Supports testing; Ensures systems ready; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | Executes testing protocols; Documents results ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | Verifies compliance; Reviews documentation ¦ | ¦ Quality/QA-QC | Sec. 9.13 Quality Directives | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.6.005 - Prepare for Turnover (Field Perspective) | Oversees closeout for Prepare for Turnover (Field Perspective) | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.010 - Conduct Closeout Meetings | Leads closeout meetings; Tracks closeout progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | A
9.6.010 - Conduct Closeout Meetings | Reports field status; Coordinates punch completion ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.010 - Conduct Closeout Meetings | Participate; Complete their closeout requirements ¦ | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | R
9.6.010 - Conduct Closeout Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Client/Owner | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | I
9.6.015 - Manage Project Turnover Documentation | Oversees closeout for Manage Project Turnover Documentation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.020 - Manage Punch List Closeout | Provides quality oversight for Manage Punch List Closeout | Quality Inspector | Sec. 9.13 Quality Directives | Inferred | Verify role assignment. | 6 - Closeout | C
9.6.020 - Manage Punch List Closeout | Oversees closeout for Manage Punch List Closeout | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.030 - Manage As-Built Drawings | Manages as-built process; Submits final drawings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | A
9.6.030 - Manage As-Built Drawings | Reviews markups for accuracy; Coordinates with field ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.030 - Manage As-Built Drawings | Creates field markups; Documents actual conditions ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.030 - Manage As-Built Drawings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Engineer/APM | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | R
9.6.035 - Submit Warranties | Oversees Submit Warranties | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.040 - Submit O&M Manuals | Oversees closeout for Submit O&M Manuals | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.050 - Provide Owner Training | Participates in client communications for Provide Owner Training | Branch Manager | Sec. 9.6 Branch Management | Inferred | Verify role assignment. | 6 - Closeout | C
9.6.050 - Provide Owner Training | Oversees Provide Owner Training | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.065 - Archive Project Documentation | Manages documentation for Archive Project Documentation | Site Administrator | Sec. 9.8 Site Administration | Inferred | Verify role assignment. | 6 - Closeout | R
9.6.065 - Archive Project Documentation | Oversees Archive Project Documentation | Project Manager | Sec. 9.5 PM Directives | Inferred | Verify role assignment. | 6 - Closeout | A
9.6.070 - Conduct Post-Project Review | Oversees review process; Approves action items ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout | A
9.6.070 - Conduct Post-Project Review | Leads review meeting; Compiles findings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.070 - Conduct Post-Project Review | Provides field perspective; Shares observations ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.070 - Conduct Post-Project Review | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | C
9.6.080 - Capture Client Feedback | Oversees feedback process; Reviews results ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout | A
9.6.080 - Capture Client Feedback | Conducts feedback meeting; Documents responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.080 - Capture Client Feedback | Uses feedback for relationship management ¦ | ¦ Business Development | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | C
9.6.080 - Capture Client Feedback | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Executive Committee | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | I
9.6.085 - Document Lessons Learned | Maintains lessons learned database; Ensures implementation ¦ | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | A
9.6.085 - Document Lessons Learned | Documents project-specific lessons; Submits for review ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.085 - Document Lessons Learned | Captures field-level learnings; Contributes to documentation ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.085 - Document Lessons Learned | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout | C

## Role Alignment Matrix
SOP ID | SOP Title | Phase | Accounting | Branch Manager | Estimator | Field Supervisor | Foreman | General Superintendent | Prefabrication Lead | Project Coordinator | Project Manager | Purchasing | Quality Inspector | Safety Coordinator | Site Administrator | Subcontractors | Superintendent | ¦ Assistant PM/Project Coordinator | ¦ Branch Manager | ¦ Business Development | ¦ Client/Owner | ¦ Commissioning Agent | ¦ Electrical Subcontractor | ¦ Executive Committee | ¦ Field Leadership | ¦ Field Supervisor | ¦ Foreman | ¦ Foreman/Journeyman | ¦ General Superintendent | ¦ Operations Manager | ¦ Project Engineer/APM | ¦ Project Manager | ¦ Purchasing | ¦ Quality/QA-QC | ¦ Safety Coordinator | ¦ Site Administrator | ¦ Subcontractors
9.1.050 | 9.1.050 - Prepare Construction Takeoff | 1 - Estimating | [8 empty] | R*
9.2.005 | 9.2.005 - Review Contract for High Risk Clauses | 2 - Preconstruction | [8 empty] | A*
9.2.010 | 9.2.010 - Team Selection | 2 - Preconstruction |  | A |  |  |  | C | I | I | R | I |  | C
9.2.015 | 9.2.015 - Project Turnover Meeting | 2 - Preconstruction | [8 empty] | A*
9.2.020 | 9.2.020 - Procurement of Large Feeder Wire | 2 - Preconstruction | [8 empty] | A* | R*
9.2.030 | 9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | 2 - Preconstruction | [8 empty] | A*
9.2.040 | 9.2.040 - Project Manager Reviews Plans Specifications & Schedule | 2 - Preconstruction | [8 empty] | R* | [5 empty] | C*
9.2.050 | 9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule | 2 - Preconstruction | [8 empty] | R* | [5 empty] | C*
9.2.055 | 9.2.055 - Compare Estimated vs Planned Performance | 2 - Preconstruction |  |  | C* | [5 empty] | A*
9.2.057 | 9.2.057 - Identify VE and Prefabrication Opportunities | 2 - Preconstruction | [6 empty] | R* |  | A*
9.2.060 | 9.2.060 - Create Issue List and Begin RFI Process | 2 - Preconstruction | [15 empty] | R | [7 empty] | C |  |  | C |  |  | A
9.2.070 | 9.2.070 - Conduct Site Visit | 2 - Preconstruction | [22 empty] | R |  |  |  | C |  |  | A |  |  | R
9.2.080 | 9.2.080 - Prepare Material Handling Plan | 2 - Preconstruction | [8 empty] | A*
9.2.090 | 9.2.090 - Develop Labor Budget | 2 - Preconstruction | C* | [7 empty] | A*
9.2.100 | 9.2.100 - Prepare Layout & Sequencing Plan | 2 - Preconstruction | [8 empty] | A*
9.2.110 | 9.2.110 - Develop Project Schedule | 2 - Preconstruction | [8 empty] | A* | [5 empty] | C*
9.2.120 | 9.2.120 - Establish Tracking & Control Systems | 2 - Preconstruction | [8 empty] | A*
9.2.130 | 9.2.130 - Construction Execution Kickoff Meeting | 2 - Preconstruction | [8 empty] | R*
9.2.140 | 9.2.140 - Develop Project Budget | 2 - Preconstruction | C* | [7 empty] | A*
9.2.160 | 9.2.160 - Develop Procurement Plan | 2 - Preconstruction | [8 empty] | A* | R*
9.3.010 | 9.3.010 - Setup Office Trailer | 3 - Mobilization | [23 empty] | R |  |  | C |  |  | A |  |  | C | R
9.3.020 | 9.3.020 - Setup Storage Trailer | 3 - Mobilization | [23 empty] | A | R | [5 empty] | C |  | C
9.3.030 | 9.3.030 - Setup Site Fencing and Access Control | 3 - Mobilization | [23 empty] | A | R |  |  |  |  | C |  |  | R
9.3.040 | 9.3.040 - Setup Temporary Power | 3 - Mobilization | [20 empty] | R |  |  | A |  | R |  |  |  | C |  |  | C
9.3.050 | 9.3.050 - Setup Temporary Water | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.060 | 9.3.060 - Setup Sanitary Facilities | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.070 | 9.3.070 - Setup Temporary Lighting | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.080 | 9.3.080 - Setup Signage | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.090 | 9.3.090 - Setup Security | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.100 | 9.3.100 - Setup Laydown Area | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.110 | 9.3.110 - Setup Equipment Staging | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.120 | 9.3.120 - Setup Parking | 3 - Mobilization |  |  |  | R* |  |  |  |  | R*
9.3.470 | 9.3.470 - Develop Site-Specific Safety Plan | 3 - Mobilization |  |  |  | C* |  |  |  |  | R* |  |  | C*
9.4.010 | 9.4.010 - Conduct Coordination Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.020 | 9.4.020 - Conduct Subcontractor Coordination Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | R* |  |  |  |  | R*
9.4.030 | 9.4.030 - Conduct Client/Owner Meetings | 4 - Execution |  | C* |  | C* |  |  |  |  | A*
9.4.040 | 9.4.040 - Conduct Safety Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.045 | 9.4.045 - Identify Value Engineering & Prefabrication Opportunities | 4 - Execution |  |  |  | C* |  |  | R* |  | A*
9.4.050 | 9.4.050 - Conduct Prefabrication Coordination Meetings | 4 - Execution |  |  |  | C* |  |  | R* |  | R*
9.4.055 | 9.4.055 - Procurement of Large Feeder Wire | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.060 | 9.4.060 - Conduct Quality Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.190 | 9.4.190 - Document Filing Standards | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  | R*
9.4.195 | 9.4.195 - Manage Project Documentation System | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  | R*
9.4.200 | 9.4.200 - Manage Submittals | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.205 | 9.4.205 - Manage RFIs (Requests for Information) | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.210 | 9.4.210 - Manage Meeting Minutes | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  | R*
9.4.215 | 9.4.215 - Manage Daily Reports | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.220 | 9.4.220 - Manage Drawing Logs | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.225 | 9.4.225 - Manage Specifications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.230 | 9.4.230 - Manage Correspondence | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  | R*
9.4.235 | 9.4.235 - Manage Permits | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.240 | 9.4.240 - Manage Inspection Reports | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.270 | 9.4.270 - Manage Project Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.275 | 9.4.275 - Manage Internal Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.280 | 9.4.280 - Manage External Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.285 | 9.4.285 - Manage Client/Owner Communications | 4 - Execution |  | C* |  | C* |  |  |  |  | R*
9.4.290 | 9.4.290 - Manage Subcontractor Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R* |  |  |  |  | R*
9.4.295 | 9.4.295 - Manage Vendor Supplier Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R* | R*
9.4.300 | 9.4.300 - Manage Architect/Engineer Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.305 | 9.4.305 - Manage Regulatory/Authority Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.310 | 9.4.310 - Manage General Contractor Communications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.315 | 9.4.315 - Develop Project Schedule | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.320 | 9.4.320 - Update Project Schedule | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.325 | 9.4.325 - Monitor Schedule Performance | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.330 | 9.4.330 - Develop Schedule Recovery Plans | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.335 | 9.4.335 - Prepare Lookahead Schedules | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.340 | 9.4.340 - Manage Resource-Loaded Schedules | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.345 | 9.4.345 - Conduct Schedule Review Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.350 | 9.4.350 - Manage Schedule Change Requests | 4 - Execution |  |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.355 | 9.4.355 - Manage Project Scope | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.360 | 9.4.360 - Manage Change Orders | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.365 | 9.4.365 - Manage Potential Change Orders (PCOs) | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.370 | 9.4.370 - Manage Owner Directives | 4 - Execution |  | C* |  | C* |  |  |  |  | A*
9.4.375 | 9.4.375 - Manage Scope Clarifications | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.380 | 9.4.380 - Manage Backcharges | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.385 | 9.4.385 - Manage Force Account Work | 4 - Execution |  |  |  | C* |  |  |  |  | R*
9.4.390 | 9.4.390 - Manage Claims | 4 - Execution |  | A* |  | C* |  |  |  |  | A*
9.4.400 | 9.4.400 - Monitor Project Costs | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.405 | 9.4.405 - Manage Cost Forecasts | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.410 | 9.4.410 - Manage Cost Codes | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.415 | 9.4.415 - Manage Committed Costs | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.420 | 9.4.420 - Manage Actual Costs | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.425 | 9.4.425 - Manage Job Cost Reports | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.430 | 9.4.430 - Manage Profit Projections | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.435 | 9.4.435 - Manage Cost-to-Complete | 4 - Execution | C* |  |  | C* |  |  |  |  | A*
9.4.440 | 9.4.440 - Prepare Billing Schedule | 4 - Execution | R* |  |  | C* |  |  |  |  | A* | [5 empty] | C*
9.4.445 | 9.4.445 - Prepare Monthly Pay Applications | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.450 | 9.4.450 - Track Accounts Receivable | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.455 | 9.4.455 - Manage Lien Waivers | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.460 | 9.4.460 - Manage Retainage | 4 - Execution | R* |  |  | C* |  |  |  |  | A*
9.4.465 | 9.4.465 - Manage Final Invoicing | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.475 | 9.4.475 - Conduct Safety Orientation | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.480 | 9.4.480 - Conduct Safety Inspections | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.485 | 9.4.485 - Conduct Safety Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.490 | 9.4.490 - Report Safety Incidents | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.495 | 9.4.495 - Investigate Accidents | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.500 | 9.4.500 - Conduct Emergency Preparedness | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | R*
9.4.505 | 9.4.505 - Conduct Safety Compliance Audits | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | C*
9.4.510 | 9.4.510 - Provide Safety Training | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  | C*
9.4.515 | 9.4.515 - Develop Quality Management Plan | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.520 | 9.4.520 - Conduct Quality Meetings | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.525 | 9.4.525 - Conduct Quality Inspections | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.530 | 9.4.530 - Manage Quality Testing | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | C*
9.4.535 | 9.4.535 - Manage Nonconformance Reports (NCRs) | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | R*
9.4.540 | 9.4.540 - Manage Quality Records | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | C*
9.4.545 | 9.4.545 - Manage Punch List Quality | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | C*
9.4.560 | 9.4.560 - Manage Manpower Allocation | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.565 | 9.4.565 - Manage Equipment Allocation | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.570 | 9.4.570 - Manage Material Allocation | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.576 | 9.4.576 - Manage Subcontractor Resources | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  |  |  |  | R*
9.4.580 | 9.4.580 - Manage Vendor Resources | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.585 | 9.4.585 - Plan Prefabrication Resources | 4 - Execution |  |  |  | C* |  |  | R* |  | A*
9.4.590 | 9.4.590 - Manage Specialty Contractor Resources | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.595 | 9.4.595 - Prepare Resource Reports | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.605 | 9.4.605 - Issue Purchase Orders | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.610 | 9.4.610 - Manage Vendor Prequalification | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.615 | 9.4.615 - Manage Vendor Evaluations | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.620 | 9.4.620 - Manage Expediting | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.625 | 9.4.625 - Manage Delivery Tracking | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.630 | 9.4.630 - Manage Material Receiving | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.631 | 9.4.631 - Release of Large Feeder Wire | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.635 | 9.4.635 - Manage Material Inspection | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.640 | 9.4.640 - Manage Storage and Logistics | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.645 | 9.4.645 - Manage Material Handling | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.650 | 9.4.650 - Manage Inventory | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.655 | 9.4.655 - Prepare Procurement Reports | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.660 | 9.4.660 - Manage Procurement Closeout | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.665 | 9.4.665 - Reconcile Procurement Accounts | 4 - Execution | R* |  |  | C* |  |  |  |  | A* | R*
9.4.670 | 9.4.670 - Manage Vendor Closeout | 4 - Execution |  |  |  | C* |  |  |  |  | A* | R*
9.4.675 | 9.4.675 - Conduct Daily Huddles | 4 - Execution |  |  |  | C* | R* |  |  |  | A*
9.4.680 | 9.4.680 - Conduct Weekly Foreman Meetings | 4 - Execution |  |  |  | C* | R* |  |  |  | A*
9.4.690 | 9.4.690 - Track Manpower Utilization | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.695 | 9.4.695 - Track Production Quantities | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.700 | 9.4.700 - Track Equipment Utilization | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.705 | 9.4.705 - Manage Work Packaging | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.710 | 9.4.710 - Manage Workface Planning | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.715 | 9.4.715 - Manage Field Coordination | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.720 | 9.4.720 - Conduct Productivity Analysis | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.4.725 | 9.4.725 - Resolve Field Problems | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.735 | 9.4.735 - Perform Field Quality Verifications | 4 - Execution |  |  |  | C* |  |  |  |  | A* |  | C*
9.4.745 | 9.4.745 - Manage Field Rework | 4 - Execution |  |  |  | R* |  |  |  |  | A*
9.4.755 | 9.4.755 - Implement Field Productivity Improvements | 4 - Execution |  |  |  | C* |  |  |  |  | A*
9.5.020 | 9.5.020 - Handling and/or Disposing of Excess Materials | 5 - Commissioning | [19 empty] | R |  |  |  | R | [5 empty] | A |  | C |  |  | R
9.5.550 | 9.5.550 - Manage Commissioning Activities | 5 - Commissioning | [19 empty] | R |  |  |  | R | [5 empty] | A |  | R |  |  | R
9.6.005 | 9.6.005 - Prepare for Turnover (Field Perspective) | 6 - Closeout | [8 empty] | A*
9.6.010 | 9.6.010 - Conduct Closeout Meetings | 6 - Closeout | [18 empty] | I |  |  |  |  | R | [5 empty] | A |  |  |  |  | R
9.6.015 | 9.6.015 - Manage Project Turnover Documentation | 6 - Closeout | [8 empty] | A*
9.6.020 | 9.6.020 - Manage Punch List Closeout | 6 - Closeout | [8 empty] | A* |  | C*
9.6.030 | 9.6.030 - Manage As-Built Drawings | 6 - Closeout | [23 empty] | R | R |  |  |  | R | A
9.6.035 | 9.6.035 - Submit Warranties | 6 - Closeout | [8 empty] | A*
9.6.040 | 9.6.040 - Submit O&M Manuals | 6 - Closeout | [8 empty] | A*
9.6.050 | 9.6.050 - Provide Owner Training | 6 - Closeout |  | C* | [6 empty] | A*
9.6.065 | 9.6.065 - Archive Project Documentation | 6 - Closeout | [8 empty] | A* |  |  |  | R*
9.6.070 | 9.6.070 - Conduct Post-Project Review | 6 - Closeout | [16 empty] | A | [6 empty] | R |  |  |  | C |  | R
9.6.080 | 9.6.080 - Capture Client Feedback | 6 - Closeout | [16 empty] | A | C |  |  |  | I | [7 empty] | R
9.6.085 | 9.6.085 - Document Lessons Learned | 6 - Closeout | [16 empty] | C | [6 empty] | R |  |  |  | A |  | R