## GSL_SOP_Metadata
SOP ID | Name | SOP File Name | Title | Description | Phase | Category (CCC Tag) | Category Group | Roles (RACI) | Primary JD | Discipline | Revision | Effective Date | Owner | Approver | Formerly | Status | Tags / Keywords | Related SOPs | Department / Division | Last Reviewed Date | Next Review Due | Document Type
9.4.050 | 9.4.050 - Prepare Construction Takeoff | 9.1.050 – Prepare Construction Takeoff.docx | Prepare Construction Takeoff |  | 4 - Execution | 050 - Reviews & Analysis | 100-199 Project Execution |  |  | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.055 – Procurement of Large Feeder Wire Reference: GSL Pre-Construction Planning – Construction Takeoff | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | prepare; construction; takeoff |  | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.055 – Procurement of Large Feeder Wire Reference: GSL Pre-Construction Planning – Construction Takeoff | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.005 | 9.2.005 - Review Contract for Unfavorable or High-Risk Clauses | 9.2.005 – Review Contract for High Risk Clauses.docx | Review Contract for Unfavorable or High-Risk Clauses | To establish a standardized process for reviewing contract terms to identify unfavorable or high-risk clauses before baseline planning begins, ensuring proper risk mitigation and approval protocols are in place. | 2 - Preconstruction | 010 - Planning & Setup | 200-299 Preconstruction Planning |  |  | Branch Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | review; contract; for; unfavorable; or; high-risk; clauses |  | Branch Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.010 | 9.2.010 - Team Selection | 9.2.010 – Team Selection.docx | Team Selection | To establish a standardized process for selecting and assembling the project team immediately after project award, ensuring the right mix of skills, experience, and availability to meet project requirements. | 2 - Preconstruction | 010 - Planning & Setup | 200-299 Preconstruction Planning | Branch Manager (A); Project Manager (R); General Superintendent (C); Safety Coordinator (C); Purchasing (I); Prefabrication Lead (I); Project Coordinator (I) |  | Project Management / Operations | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | team; selection |  | Project Management / Operations | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.010.41 | 9.010.41 - Project Turnover Meeting | 9.2.015 – Project Turnover Meeting.docx | Project Turnover Meeting |  | Unknown | 010 - Planning & Setup | 000-099 General |  |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.2 Related SOPs: | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | project; turnover; meeting |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.2 Related SOPs: | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.020 | 9.2.020 - Procurement of Large Feeder Wire | 9.2.020 – Procurement of Large Feeder Wire.docx | Procurement of Large Feeder Wire |  | 2 - Preconstruction | 010 - Planning & Setup | 200-299 Preconstruction Planning |  |  | Operations | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | procurement; of; large; feeder; wire |  | Operations | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.030 | 9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | 9.2.030 – Review Contract for Unfavorable or High Risk Clauses.docx | Review Contract for Unfavorable or High-Risk Clauses |  | 2 - Preconstruction | 010 - Planning & Setup | 200-299 Preconstruction Planning |  |  | Project Management / Pre-Construction Created by: Schachinger Solutions GmbH Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Contract Review | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | review; contract; for; unfavorable; or; high-risk; clauses |  | Project Management / Pre-Construction Created by: Schachinger Solutions GmbH Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Contract Review | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.040 | 9.2.040 - Project Manager Reviews Plans, Specifications & Schedule | 9.2.040 – Project Manager Reviews Plans, Specifications & Schedule.docx | Project Manager Reviews Plans, Specifications & Schedule |  | 2 - Preconstruction | 010 - Planning & Setup | 200-299 Preconstruction Planning |  |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable or High-Risk Clauses; 9.41.025 – Field Supervisor Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Scope & Schedule Review | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | project; manager; reviews; plans,; specifications; &; schedule |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable or High-Risk Clauses; 9.41.025 – Field Supervisor Reviews Plans, Specifications & Schedule Reference: GSL Pre-Construction Planning – Scope & Schedule Review | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.050 | 9.2.050 - Field Supervisor Reviews Plans, Specifications & Schedule | 9.2.050 – Field Supervisor Reviews Plans, Specifications & Schedule.docx | Field Supervisor Reviews Plans, Specifications & Schedule |  | 2 - Preconstruction | 050 - Reviews & Analysis | 200-299 Preconstruction Planning |  |  | Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process Reference: GSL Pre-Construction Planning – Scope & Schedule Review | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | field; supervisor; reviews; plans,; specifications; &; schedule |  | Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process Reference: GSL Pre-Construction Planning – Scope & Schedule Review | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.040 | 9.4.040 - Compare Estimated vs. Planned Performance | 9.2.055 – Compare Estimated vs Planned Performance.docx | Compare Estimated vs. Planned Performance |  | 4 - Execution | 010 - Planning & Setup | 100-199 Project Execution |  |  | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.045 – Identify Value Engineering & Prefabrication Opportunities Reference: GSL Pre-Construction Planning – Bid vs. Execution Review | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | compare; estimated; vs.; planned; performance |  | Project Management / Estimating Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.045 – Identify Value Engineering & Prefabrication Opportunities Reference: GSL Pre-Construction Planning – Bid vs. Execution Review | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.090.41 | 9.090.41 - Prefab Plan Created | 9.2.057 – Identify VE and Prefabrication Opportunities.docx | Prefab Plan Created |  | Unknown | 010 - Planning & Setup | 000-099 General |  |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | prefab; plan; created |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.060 | 9.2.060 - Create List of Issues and Begin RFI Process | 9.2.060 – Create Issue List and Begin RFI Process.docx | Create List of Issues and Begin RFI Process | To establish a standardized process for documenting project issues identified during pre-construction review and initiating the Request for Information (RFI) process to resolve them before construction begins. | 2 - Preconstruction | 050 - Reviews & Analysis | 200-299 Preconstruction Planning | ¦ Project Manager (A); ¦ Assistant PM/Project Coordinator (R); ¦ Field Supervisor (C); ¦ General Superintendent (C) |  | Project Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | create; list; of; issues; and; begin; rfi; process |  | Project Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.070 | 9.2.070 - Conduct Site Visit | 9.2.070 – Conduct Site Visit.docx | Conduct Site Visit | To establish a standardized process for conducting pre-construction site visits to assess existing conditions, identify logistical requirements, and validate planning assumptions before mobilization. | 2 - Preconstruction | 050 - Reviews & Analysis | 200-299 Preconstruction Planning | ¦ Project Manager (A); ¦ Field Leadership (R); ¦ Safety Coordinator (R); ¦ General Superintendent (C) |  | Project Management / Field Operations | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | conduct; site; visit |  | Project Management / Field Operations | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.060.41 | 9.060.41 - Prepare Material Handling Plan | 9.2.080 – Prepare Material Handling Plan.docx | Prepare Material Handling Plan |  | Unknown | 010 - Planning & Setup | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | prepare; material; handling; plan |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.065.41 | 9.065.41 - Develop Labor Budget | 9.2.090 – Develop Labor Budget.docx | Develop Labor Budget |  | Unknown | 010 - Planning & Setup | 000-099 General |  |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | develop; labor; budget |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.100 | 9.2.100 - Prepare Layout & Sequencing Plan | 9.2.100 – Prepare Layout & Sequencing Plan.docx | Prepare Layout & Sequencing Plan |  | 2 - Preconstruction | 100 - Mobilization | 200-299 Preconstruction Planning |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.065 – Develop Labor Budget; 9.41.075 – Develop Project Schedule Reference: GSL Pre-Construction Planning – Layout & Sequencing | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | prepare; layout; &; sequencing; plan |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.065 – Develop Labor Budget; 9.41.075 – Develop Project Schedule Reference: GSL Pre-Construction Planning – Layout & Sequencing | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.075.41 | 9.075.41 - Develop Project Schedule | 9.2.110 – Develop Project Schedule.docx | Develop Project Schedule |  | Unknown | 010 - Planning & Setup | 000-099 General |  |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | develop; project; schedule |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.2.120 | 9.2.120 - Establish Tracking & Control Systems | 9.2.120 – Establish Tracking & Control Systems.docx | Establish Tracking & Control Systems |  | 2 - Preconstruction | 100 - Mobilization | 200-299 Preconstruction Planning |  |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Pre-Construction Planning – Tracking & Control | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | establish; tracking; &; control; systems |  | Project Management / Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Pre-Construction Planning – Tracking & Control | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.085.41 | 9.085.41 - Construction Execution Kickoff Meeting | 9.2.130 – Construction Execution Kickoff Meeting.docx | Construction Execution Kickoff Meeting |  | Unknown | 010 - Planning & Setup | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | construction; execution; kickoff; meeting |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.2.140 – Develop Project Budget.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.360 – Manage Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.360 – Manage Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.2.160 – Develop Procurement Plan.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.395 – Develop Project Budget; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.005 – Team Selection; 9.41.395 – Develop Project Budget; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.3.010 | 9.3.010 - Setup Office Trailer | 9.3.010 – Setup Office Trailer.docx | Setup Office Trailer | To establish a standardized process for setting up the project office trailer, ensuring proper placement, utilities, and functionality for project administration and team coordination. | 3 - Mobilization & Job Site Setup | 010 - Planning & Setup | 100-199 Project Execution | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Site Administrator (R); ¦ Safety Coordinator (C); ¦ General Superintendent (C) |  | Project Management / Field Operations | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; office; trailer |  | Project Management / Field Operations | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.3.020 | 9.3.020 - Setup Storage Trailer | 9.3.020 – Setup Storage Trailer.docx | Setup Storage Trailer | To establish a standardized process for setting up project storage trailers/containers, ensuring secure and organized storage for materials, tools, and equipment. | 3 - Mobilization & Job Site Setup | 010 - Planning & Setup | 100-199 Project Execution | ¦ Field Supervisor (A); ¦ Foreman (R); ¦ Purchasing (C); ¦ Safety Coordinator (C) |  | Field Operations | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; storage; trailer |  | Field Operations | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.3.030 | 9.3.030 - Setup Site Fencing and Access Control | 9.3.030 – Setup Site Fencing and Access Control.docx | Setup Site Fencing and Access Control | To establish a standardized process for installing site fencing and access control measures, ensuring site security and controlled entry/exit for personnel and deliveries. | 3 - Mobilization & Job Site Setup | 010 - Planning & Setup | 100-199 Project Execution | ¦ Field Supervisor (A); ¦ Foreman (R); ¦ Safety Coordinator (R); ¦ Project Manager (C) |  | Field Operations / Safety | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; site; fencing; and; access; control |  | Field Operations / Safety | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.3.040 | 9.3.040 - Setup Temporary Power | 9.3.040 – Setup Temporary Power.docx | Setup Temporary Power | To establish a standardized process for installing temporary electrical power distribution, ensuring safe and adequate power for construction operations, trailers, and equipment. | 3 - Mobilization & Job Site Setup | 010 - Planning & Setup | 100-199 Project Execution | ¦ Field Supervisor (A); ¦ Foreman/Journeyman (R); ¦ Safety Coordinator (C); ¦ Project Manager (C); ¦ Electrical Subcontractor (R) |  | Field Operations | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; temporary; power |  | Field Operations | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.110 | 9.41.110 - Setup Temporary Water | 9.3.050 – Setup Temporary Water.docx | Setup Temporary Water |  | Unknown | 100 - Mobilization | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer Reference: GSL Project Manager Procedures – Mobilization | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; temporary; water |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer Reference: GSL Project Manager Procedures – Mobilization | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.115 | 9.41.115 - Setup Sanitary Facilities | 9.3.060 – Setup Sanitary Facilities.docx | Setup Sanitary Facilities |  | Unknown | 100 - Mobilization | 000-099 General |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer; 9.41.110 – Setup Temporary Water Reference: GSL Project Manager Procedures – Mobilization | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; sanitary; facilities |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer; 9.41.110 – Setup Temporary Water Reference: GSL Project Manager Procedures – Mobilization | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.120 | 9.41.120 - Setup Temporary Lighting | 9.3.070 – Setup Temporary Lighting.docx | Setup Temporary Lighting |  | Unknown | 100 - Mobilization | 000-099 General |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.105 – Setup Temporary Power; 9.41.110 – Setup Temporary Water; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; temporary; lighting |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.105 – Setup Temporary Power; 9.41.110 – Setup Temporary Water; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.125 | 9.41.125 - Setup Signage | 9.3.080 – Setup Signage.docx | Setup Signage |  | Unknown | 100 - Mobilization | 000-099 General |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; signage |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.115 – Setup Sanitary Facilities Reference: GSL Project Manager Procedures – Mobilization | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.130 | 9.41.130 - Setup Security | 9.3.090 – Setup Security.docx | Setup Security |  | Unknown | 100 - Mobilization | 000-099 General |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.125 – Setup Signage Reference: GSL Project Manager Procedures – Mobilization | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; security |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.100 – Setup Site Fencing and Access Control; 9.41.125 – Setup Signage Reference: GSL Project Manager Procedures – Mobilization | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.135 | 9.41.135 - Setup Laydown Area | 9.3.100 – Setup Laydown Area.docx | Setup Laydown Area |  | Unknown | 100 - Mobilization | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.095 – Setup Storage Trailer; 9.41.100 – Setup Site Fencing and Access Control Reference: GSL Project Manager Procedures – Mobilization | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; laydown; area |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.095 – Setup Storage Trailer; 9.41.100 – Setup Site Fencing and Access Control Reference: GSL Project Manager Procedures – Mobilization | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.140 | 9.41.140 - Setup Equipment Staging | 9.3.110 – Setup Equipment Staging.docx | Setup Equipment Staging |  | Unknown | 100 - Mobilization | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area Reference: GSL Project Manager Procedures – Mobilization | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; equipment; staging |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area Reference: GSL Project Manager Procedures – Mobilization | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.145 | 9.41.145 - Setup Parking | 9.3.120 – Setup Parking.docx | Setup Parking |  | Unknown | 100 - Mobilization | 000-099 General |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Mobilization | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | setup; parking |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Mobilization | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.3.470 – Develop Site Specific Safety Plan.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.010 – Conduct Coordination Meetings.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Owner/GC Coordination Meetings; 9.41.170 – Conduct Progress Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Coordination | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Owner/GC Coordination Meetings; 9.41.170 – Conduct Progress Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Coordination | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.020 | 9.4.020 - Conduct Subcontractor Coordination Meetings | 9.4.020 – Conduct Subcontractor Coordination Meetings.docx | Conduct Subcontractor Coordination Meetings |  | 4 - Execution | 010 - Planning & Setup | 100-199 Project Execution |  |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Coordination | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | conduct; subcontractor; coordination; meetings |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging Reference: GSL Project Manager Procedures – Coordination | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.030 | 9.4.030 - Conduct Client/Owner Meetings | 9.4.030 – Conduct Client Owner Meetings.docx | Conduct Client/Owner Meetings |  | 4 - Execution | 010 - Planning & Setup | 100-199 Project Execution |  |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable Clauses; 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Project Manager Procedures – Coordination | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | conduct; client/owner; meetings |  | Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.015 – Review Contract for Unfavorable Clauses; 9.41.075 – Develop Project Schedule; 9.41.085 – Construction Execution Kickoff Meeting Reference: GSL Project Manager Procedures – Coordination | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.040 | 9.4.040 - Conduct Safety Meetings | 9.4.040 – Conduct Safety Meetings.docx | Conduct Safety Meetings |  | 4 - Execution | 010 - Planning & Setup | 100-199 Project Execution |  |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.115 – Setup Sanitary Facilities; 9.41.120 – Setup Temporary Lighting Reference: GSL Project Manager Procedures – Coordination | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | conduct; safety; meetings |  | Project Management / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.115 – Setup Sanitary Facilities; 9.41.120 – Setup Temporary Lighting Reference: GSL Project Manager Procedures – Coordination | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.045 | 9.4.045 - Identify Value Engineering & Prefabrication Opportunities | 9.4.045 – Identify Value Engineering & Prefabrication Opportunities.docx | Identify Value Engineering & Prefabrication Opportunities |  | 4 - Execution | 010 - Planning & Setup | 100-199 Project Execution |  |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.050 – Prepare Construction Takeoff Reference: GSL Pre-Construction Planning – Value Engineering & Prefabrication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | identify; value; engineering; &; prefabrication; opportunities |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.050 – Prepare Construction Takeoff Reference: GSL Pre-Construction Planning – Value Engineering & Prefabrication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.050 | 9.4.050 - Conduct Prefabrication Coordination Meetings | 9.4.050 – Conduct Prefabrication Coordination Meetings.docx | Conduct Prefabrication Coordination Meetings |  | 4 - Execution | 050 - Reviews & Analysis | 100-199 Project Execution |  |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.050 – Prepare Construction Takeoff; 9.41.065 – Develop Labor Budget Reference: GSL Project Manager Procedures – Coordination | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | conduct; prefabrication; coordination; meetings |  | Project Management / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.050 – Prepare Construction Takeoff; 9.41.065 – Develop Labor Budget Reference: GSL Project Manager Procedures – Coordination | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.055 | 9.4.055 - 1 Procurement of Large Feeder Wire | 9.4.055 – 1 Procurement of Large Feeder Wire.docx | 1 Procurement of Large Feeder Wire |  | 4 - Execution | 050 - Reviews & Analysis | 100-199 Project Execution |  |  | Operations | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | 1; procurement; of; large; feeder; wire |  | Operations | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.060 | 9.4.060 - Conduct Quality Meetings | 9.4.060 – Conduct Quality Meetings.docx | Conduct Quality Meetings |  | 4 - Execution | 050 - Reviews & Analysis | 100-199 Project Execution |  |  | Project Management / Quality Control Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.080 – Establish Tracking & Control Systems Reference: GSL Project Manager Procedures – Coordination | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | conduct; quality; meetings |  | Project Management / Quality Control Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.080 – Establish Tracking & Control Systems Reference: GSL Project Manager Procedures – Coordination | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.190A | 9.4.190A - Document Filing Standards | 9.4.190 – A Document Filing Standards.docx | Document Filing Standards |  | 4 - Execution | 150 - Documentation | 100-199 Project Execution |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: All documentation-related SOPs (9.41.195 – 9.41.265 and beyond) Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: All documentation-related SOPs (9.41.195 – 9.41.265 and beyond) Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.195 – Manage Project Documentation System.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.005 – Team Selection; 9.41.010 – Project Turnover Meeting; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.005 – Team Selection; 9.41.010 – Project Turnover Meeting; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.200 – Manage Submittals.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.050 – Prepare Construction Takeoff; 9.41.055 – Procurement of Large Feeder Wire; 9.41.075 – Develop Project Schedule; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.050 – Prepare Construction Takeoff; 9.41.055 – Procurement of Large Feeder Wire; 9.41.075 – Develop Project Schedule; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.205 – Manage RF Is (Requests for Information).docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Pre-Construction Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Pre-Construction Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.210 – Manage Meeting Minutes.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Client/Owner Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Client/Owner Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.215 – Manage Daily Reports.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.080 – Establish Tracking & Control Systems; 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.080 – Establish Tracking & Control Systems; 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.220 – Manage Drawing Logs.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.225 – Manage Specifications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.200 – Manage Submittals; 9.41.220 – Manage Drawing Logs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.200 – Manage Submittals; 9.41.220 – Manage Drawing Logs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.230 – Manage Correspondence.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.205 – Manage RFIs; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.205 – Manage RFIs; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.235 – Manage Permits.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Safety / Compliance Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Safety / Compliance Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.115 – Setup Sanitary Facilities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.240 – Manage Inspection Reports.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.235 – Manage Permits; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality / Safety Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.1 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.175 – Conduct Quality Meetings; 9.41.235 – Manage Permits; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Documentation Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.270 – Manage Project Communications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.195 – Manage Project Documentation System; 9.41.210 – Manage Meeting Minutes; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.275 – Manage Internal Communications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.165 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Project Coordination Meetings; 9.41.165 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.280 – Manage External Communications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.285 – Manage Client Owner Communications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Client Relations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.160 – Conduct Client/Owner Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.290 – Manage Subcontractor Communications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Subcontractor Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Subcontractor Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.280 – Manage External Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.295 – Manage Vendor Supplier Communications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.200 – Manage Submittals; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.200 – Manage Submittals; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.300 – Manage Architect Engineer Communications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.305 – Manage Regulatory Authority Communications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Design Coordination Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.310 – Manage General Contractor Communications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.150 – Conduct Project Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.150 – Conduct Project Coordination Meetings; 9.41.230 – Manage Correspondence; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Communication | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.315 – Develop Project Schedule.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.010 – Project Turnover Meeting; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.010 – Project Turnover Meeting; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.320 – Update Project Schedule.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.150 – Conduct Project Coordination Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.150 – Conduct Project Coordination Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.325 – Monitor Schedule Performance.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.330 – Develop Schedule Recovery Plans.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.325 – Monitor Schedule Performance; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.325 – Monitor Schedule Performance; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.335 – Prepare Lookahead Schedules.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.340 – Manage Resource Loaded Schedules.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.345 – Conduct Schedule Review Meetings.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Scheduling Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.320 – Update Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.350 – Manage Schedule Change Requests.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Scheduling / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Scheduling / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.325 – Monitor Schedule Performance; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scheduling | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.355 – Manage Project Scope.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.315 – Develop Project Schedule; 9.41.350 – Manage Schedule Change Requests; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.315 – Develop Project Schedule; 9.41.350 – Manage Schedule Change Requests; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.360 | 9.4.360 - Manage Change Orders | 9.4.360 – Manage Change Orders.docx | Manage Change Orders |  | 4 - Execution | 300 - Scheduling | 100-199 Project Execution |  |  | Operations | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | manage; change; orders |  | Operations | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.365 – Manage Potential Change Orders (PCOs).docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.370 – Manage Owner Directives.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.375 – Manage Scope Clarifications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.205 – Manage RFIs; 9.41.370 – Manage Owner Directives; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Contract Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.355 – Manage Project Scope; 9.41.205 – Manage RFIs; 9.41.370 – Manage Owner Directives; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.380 – Manage Backcharges.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.290 – Manage Subcontractor Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.290 – Manage Subcontractor Communications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.385 – Manage Force Account Work.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.380 – Manage Backcharges; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Contract Administration / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.380 – Manage Backcharges; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.390 – Manage Claims.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Contract Administration / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.370 – Manage Owner Directives; 9.41.385 – Manage Force Account Work; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Contract Administration / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.360 – Manage Change Orders; 9.41.370 – Manage Owner Directives; 9.41.385 – Manage Force Account Work; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Scope & Change Control | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.400 – Monitor Project Costs.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.405 – Manage Cost Forecasts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.405 – Manage Cost Forecasts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.405 – Manage Cost Forecasts.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.410 – Manage Cost Codes.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.415 – Manage Committed Costs.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.395 – Develop Project Budget; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.420 – Manage Actual Costs.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.425 – Manage Job Cost Reports.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.400 – Monitor Project Costs; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.430 – Manage Profit Projections.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.435 – Manage Cost to Complete.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.420 – Manage Actual Costs; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.420 – Manage Actual Costs; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Cost Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.440 – Prepare Billing Schedule.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.430 – Manage Profit Projections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.445 – Prepare Monthly Pay Applications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.440 – Prepare Billing Schedule; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.440 – Prepare Billing Schedule; 9.41.420 – Manage Actual Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.450 – Track Accounts Receivable.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Accounting / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Accounting / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.455 – Manage Lien Waivers.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.460 – Manage Retainage.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.465 – Manage Final Invoicing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.445 – Prepare Monthly Pay Applications; 9.41.450 – Track Accounts Receivable; 9.41.465 – Manage Final Invoicing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.465 – Manage Final Invoicing.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.455 – Manage Lien Waivers; 9.41.460 – Manage Retainage; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.455 – Manage Lien Waivers; 9.41.460 – Manage Retainage; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Billing & Invoicing | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.475 – Conduct Safety Orientation.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.480 – Conduct Safety Inspections.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.485 – Conduct Safety Meetings.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.470 – Develop Site-Specific Safety Plan; 9.41.480 – Conduct Safety Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.490 – Report Safety Incidents.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.485 – Conduct Safety Meetings; 9.41.495 – Investigate Accidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.485 – Conduct Safety Meetings; 9.41.495 – Investigate Accidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.495 – Investigate Accidents.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Project Management / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.490 – Report Safety Incidents; 9.41.485 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Project Management / Legal Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.490 – Report Safety Incidents; 9.41.485 – Conduct Safety Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.500 – Conduct Emergency Preparedness.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.490 – Report Safety Incidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.470 – Develop Site-Specific Safety Plan; 9.41.475 – Conduct Safety Orientation; 9.41.490 – Report Safety Incidents; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.505 – Conduct Safety Compliance Audits.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.480 – Conduct Safety Inspections; 9.41.495 – Investigate Accidents; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Branch Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.480 – Conduct Safety Inspections; 9.41.495 – Investigate Accidents; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.510 – Provide Safety Training.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Human Resources Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.475 – Conduct Safety Orientation; 9.41.485 – Conduct Safety Meetings; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Human Resources Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.475 – Conduct Safety Orientation; 9.41.485 – Conduct Safety Meetings; 9.41.500 – Conduct Emergency Preparedness; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Safety Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.515 – Develop Quality Management Plan.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.520 – Conduct Quality Meetings.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.175 – Conduct Quality Meetings; 9.41.515 – Develop Quality Management Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.175 – Conduct Quality Meetings; 9.41.515 – Develop Quality Management Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.525 – Conduct Quality Inspections.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Safety / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.515 – Develop Quality Management Plan; 9.41.520 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Safety / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.240 – Manage Inspection Reports; 9.41.515 – Develop Quality Management Plan; 9.41.520 – Conduct Quality Meetings; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.530 – Manage Quality Testing.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.525 – Conduct Quality Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.525 – Conduct Quality Inspections; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.535 – Manage Nonconformance Reports (NC Rs).docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.530 – Manage Quality Testing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.530 – Manage Quality Testing; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.540 – Manage Quality Records.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.530 – Manage Quality Testing; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.515 – Develop Quality Management Plan; 9.41.530 – Manage Quality Testing; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.545 – Manage Punch List Quality.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.245 – Manage Punch Lists; 9.41.525 – Conduct Quality Inspections; 9.41.540 – Manage Quality Records; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.245 – Manage Punch Lists; 9.41.525 – Conduct Quality Inspections; 9.41.540 – Manage Quality Records; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.560 – Manage Manpower Allocation.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.565 – Manage Equipment Allocation.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.570 – Manage Material Allocation.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.565 – Manage Equipment Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.565 – Manage Equipment Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.576 – Manage Subcontractor Resources.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.415 – Manage Committed Costs; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.415 – Manage Committed Costs; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.580 – Manage Vendor Resources.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.295 – Manage Vendor / Supplier Communications; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.295 – Manage Vendor / Supplier Communications; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.585 – Plan Prefabrication Resources.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations / Prefabrication Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.590 – Manage Specialty Contractor Resources.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.575 – Manage Subcontractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.575 – Manage Subcontractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.595 – Prepare Resource Reports.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.590 – Manage Specialty Contractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.565 – Manage Equipment Allocation; 9.41.570 – Manage Material Allocation; 9.41.590 – Manage Specialty Contractor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Resource Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.605 – Issue Purchase Orders.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.415 – Manage Committed Costs; 9.41.600 – Develop Procurement Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.415 – Manage Committed Costs; 9.41.600 – Develop Procurement Plan; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.610 – Manage Vendor Prequalification.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Procurement / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.290 – Manage Subcontractor Communications; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Procurement / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.290 – Manage Subcontractor Communications; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.615 – Manage Vendor Evaluations.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.580 – Manage Vendor Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.620 – Manage Expediting.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.625 – Manage Delivery Tracking.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.620 – Manage Expediting; 9.41.570 – Manage Material Allocation; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Procurement / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.620 – Manage Expediting; 9.41.570 – Manage Material Allocation; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.630 – Manage Material Receiving.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.625 – Manage Delivery Tracking; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.625 – Manage Delivery Tracking; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.4.631 | 9.4.631 - Release of Large Feeder Wire | 9.4.631 – Release of Large Feeder Wire.docx | Release of Large Feeder Wire |  | 4 - Execution | 600 - Procurement | 100-199 Project Execution |  |  | Project Management / Field Leadership / Purchasing | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | release; of; large; feeder; wire | 9.2.020 – Procurement of Large Feeder Wire; 9.2.080 – Prepare Material Handling Plan; 9.2.100 – Prepare Layout & Sequencing Plan | Project Management / Field Leadership / Purchasing | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.635 – Manage Material Inspection.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Quality / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.530 – Manage Quality Testing; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Quality / Procurement Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.530 – Manage Quality Testing; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.640 – Manage Storage and Logistics.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.570 – Manage Material Allocation; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.570 – Manage Material Allocation; 9.41.630 – Manage Material Receiving; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.645 – Manage Material Handling.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Logistics / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Logistics / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.650 – Manage Inventory.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.645 – Manage Material Handling; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.645 – Manage Material Handling; 9.41.640 – Manage Storage and Logistics; 9.41.570 – Manage Material Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.655 – Prepare Procurement Reports.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Procurement / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.650 – Manage Inventory; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Procurement / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.600 – Develop Procurement Plan; 9.41.605 – Issue Purchase Orders; 9.41.625 – Manage Delivery Tracking; 9.41.650 – Manage Inventory; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.660 – Manage Procurement Closeout.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.465 – Manage Final Invoicing; 9.41.650 – Manage Inventory; 9.41.655 – Prepare Procurement Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.465 – Manage Final Invoicing; 9.41.650 – Manage Inventory; 9.41.655 – Prepare Procurement Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.665 – Reconcile Procurement Accounts.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Accounting / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.420 – Manage Actual Costs; 9.41.660 – Manage Procurement Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Accounting / Procurement / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.395 – Develop Project Budget; 9.41.420 – Manage Actual Costs; 9.41.660 – Manage Procurement Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.670 – Manage Vendor Closeout.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.615 – Manage Vendor Evaluations; 9.41.660 – Manage Procurement Closeout; 9.41.665 – Reconcile Procurement Accounts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Procurement / Project Management / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.610 – Manage Vendor Prequalification; 9.41.615 – Manage Vendor Evaluations; 9.41.660 – Manage Procurement Closeout; 9.41.665 – Reconcile Procurement Accounts; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Procurement | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.675 – Conduct Daily Huddles.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.165 – Conduct Safety Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.680 – Conduct Weekly Foreman Meetings.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.690 – Track Manpower Utilization.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.695 – Track Production Quantities.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.400 – Monitor Project Costs; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.400 – Monitor Project Costs; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.700 – Track Equipment Utilization.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.565 – Manage Equipment Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.565 – Manage Equipment Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.705 – Manage Work Packaging.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.335 – Prepare Lookahead Schedules; 9.41.695 – Track Production Quantities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.008 – Identify Prefabrication Opportunities; 9.41.335 – Prepare Lookahead Schedules; 9.41.695 – Track Production Quantities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.710 – Manage Workface Planning.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.705 – Manage Work Packaging; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.705 – Manage Work Packaging; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.715 – Manage Field Coordination.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.680 – Conduct Weekly Foreman Meetings; 9.41.705 – Manage Work Packaging; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.150 – Conduct Coordination Meetings; 9.41.680 – Conduct Weekly Foreman Meetings; 9.41.705 – Manage Work Packaging; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.720 – Conduct Productivity Analysis.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.695 – Track Production Quantities; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations / Accounting Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.695 – Track Production Quantities; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.725 – Resolve Field Problems.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.715 – Manage Field Coordination; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.205 – Manage RFIs; 9.41.715 – Manage Field Coordination; 9.41.535 – Manage Nonconformance Reports; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.735 – Perform Field Quality Verifications.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.535 – Manage Nonconformance Reports; 9.41.720 – Conduct Productivity Analysis; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Quality / Project Management Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.525 – Conduct Quality Inspections; 9.41.535 – Manage Nonconformance Reports; 9.41.720 – Conduct Productivity Analysis; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.745 – Manage Field Rework.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.535 – Manage Nonconformance Reports; 9.41.725 – Resolve Field Problems; 9.41.735 – Perform Field Quality Verifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.535 – Manage Nonconformance Reports; 9.41.725 – Resolve Field Problems; 9.41.735 – Perform Field Quality Verifications; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.4.755 – Implement Field Productivity Improvements.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.720 – Conduct Productivity Analysis; 9.41.695 – Track Production Quantities; 9.41.585 – Plan Prefabrication Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.720 – Conduct Productivity Analysis; 9.41.695 – Track Production Quantities; 9.41.585 – Plan Prefabrication Resources; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.5.010 | 9.5.010 - Conduct Commissioning Meetings | 9.5.020 – Handling and or Disposing of Excess Materials.docx | Conduct Commissioning Meetings | To establish a standardized process for conducting commissioning meetings, ensuring proper coordination between all parties during the testing, verification, and turnover phases of the project. | 5 - Commissioning | 010 - Planning & Setup | 300-399 Commissioning | ¦ Project Manager (A); ¦ Commissioning Agent (R); ¦ Field Supervisor (R); ¦ Quality/QA-QC (C); ¦ Subcontractors (R) |  | Project Management / Quality | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | conduct; commissioning; meetings |  | Project Management / Quality | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.5.550 | 9.5.550 - Manage Commissioning Activities | 9.5.550 – Manage Commissioning Activities.docx | Manage Commissioning Activities | To establish a standardized process for managing all commissioning activities, ensuring systematic testing, verification, and documentation of electrical systems prior to owner turnover. | 5 - Commissioning | 500 - Safety & Quality | 300-399 Commissioning | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Commissioning Agent (R); ¦ Quality/QA-QC (R); ¦ Subcontractors (R) |  | Project Management / Quality | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | manage; commissioning; activities |  | Project Management / Quality | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.6.005 – Prepare for Turnover (Field Perspective).docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.555 – Manage Project Turnover Documentation; 9.41.730 – Manage As-Built Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Field Operations / Project Management / Quality Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.555 – Manage Project Turnover Documentation; 9.41.730 – Manage As-Built Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Field Execution | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.6.010 | 9.6.010 - Conduct Closeout Meetings | 9.6.010 – Conduct Closeout Meetings.docx | Conduct Closeout Meetings | To establish a standardized process for conducting project closeout meetings, ensuring proper coordination of all closeout activities and successful project completion. | 6 - Closeout | 010 - Planning & Setup | 400-499 Closeout | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Subcontractors (R); ¦ Client/Owner (I) |  | Project Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | conduct; closeout; meetings |  | Project Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.6.015 – Manage Project Turnover Documentation.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.545 – Manage Punch List Quality; 9.41.550 – Manage Commissioning Activities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.265 – Manage Closeout Documentation; 9.41.545 – Manage Punch List Quality; 9.41.550 – Manage Commissioning Activities; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Quality Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.6.020 – Manage Punch List Closeout.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.760 – Prepare for Turnover (Field Perspective); 9.41.555 – Manage Project Turnover Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.545 – Manage Punch List Quality; 9.41.760 – Prepare for Turnover (Field Perspective); 9.41.555 – Manage Project Turnover Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.6.030 | 9.6.030 - Manage As-Built Drawings | 9.6.030 – Manage As Built Drawings.docx | Manage As-Built Drawings | To establish a standardized process for managing as-built drawings, ensuring accurate documentation of installed conditions for owner records and future maintenance. | 6 - Closeout | 010 - Planning & Setup | 400-499 Closeout | ¦ Project Manager (A); ¦ Field Supervisor (R); ¦ Foreman (R); ¦ Project Engineer/APM (R) |  | Project Management / Field Operations | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | manage; as-built; drawings |  | Project Management / Field Operations | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.6.035 – Submit Warranties.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.770 – Manage Punch List Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.770 – Manage Punch List Closeout; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.6.040 – Submit O&M Manuals.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.550 – Manage Commissioning Activities; 9.41.775 – Submit Warranties; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.550 – Manage Commissioning Activities; 9.41.775 – Submit Warranties; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.6.050 – Provide Owner Training.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.550 – Manage Commissioning Activities; 9.41.780 – Submit O&M Manuals; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Quality / Field Operations Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.550 – Manage Commissioning Activities; 9.41.780 – Submit O&M Manuals; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.41.190A | 9.41.190A - Document Filing Standards | 9.6.065 – Archive Project Documentation.docx | Document Filing Standards |  | Unknown | 150 - Documentation | 000-099 General |  |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.265 – Manage Closeout Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; filing; standards |  | Project Management / Administration Created by: Tom Ewing Effective Date: [Insert Date] Version: 1.0 Related SOPs: 9.41.555 – Manage Project Turnover Documentation; 9.41.265 – Manage Closeout Documentation; 9.41.190A – Document Filing Standards Reference: GSL Project Manager Procedures – Closeout | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.6.070 | 9.6.070 - Conduct Post-Project Review | 9.6.070 – Conduct Post Project Review.docx | Conduct Post-Project Review | To establish a standardized process for conducting post-project reviews, evaluating project performance, and identifying successes and areas for improvement. | 6 - Closeout | 050 - Reviews & Analysis | 400-499 Closeout | ¦ Branch Manager (A); ¦ Project Manager (R); ¦ Field Supervisor (R); ¦ Operations Manager (C) |  | Project Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | conduct; post-project; review |  | Project Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.6.080 | 9.6.080 - Capture Client Feedback | 9.6.080 – Capture Client Feedback.docx | Capture Client Feedback | To establish a standardized process for capturing client feedback at project completion, enabling continuous improvement and strengthening client relationships. | 6 - Closeout | 050 - Reviews & Analysis | 400-499 Closeout | ¦ Branch Manager (A); ¦ Project Manager (R); ¦ Business Development (C); ¦ Executive Committee (I) |  | Project Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | capture; client; feedback |  | Project Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP
9.6.085 | 9.6.085 - Document Lessons Learned | 9.6.085 – Document Lessons Learned.docx | Document Lessons Learned | To establish a standardized process for documenting lessons learned throughout and at the completion of projects, creating an organizational knowledge base for continuous improvement. | 6 - Closeout | 050 - Reviews & Analysis | 400-499 Closeout | ¦ Operations Manager (A); ¦ Project Manager (R); ¦ Field Supervisor (R); ¦ Branch Manager (C) |  | Project Management | 1 | 2025-12-20 14:44 | Project Management | Executive Committee |  | Approved | document; lessons; learned |  | Project Management | 2026-01-12 14:44 | 2027-01-19 14:44 | SOP

## Sheet2
| Management Directives |  | Job Descriptions
Position | Policy Manual, 9.x Management Directives | File Path | Policy Manual, 7.x Job Descriptions | File Path
Apprentice | Policy Manual, 9.2 Field Employees | C:\Documents\Policy Manual\Management Directives\9.2 Field Employees.doc | Policy Manual, 7.2.1 Apprentice Electrician | C:\Documents\Policy Manual\Job Descriptions\7.2.1 Apprentice Electrician.doc
Journeyman | Policy Manual, 9.2 Field Employees | C:\Documents\Policy Manual\Management Directives\9.2 Field Employees.doc | Policy Manual, 7.2.2 Journeyman Electrician | C:\Documents\Policy Manual\Job Descriptions\7.2.2 Journeyman Electrician.doc
Foreman | Policy Manual, 9.3 Field Leadership | C:\Documents\Policy Manual\Management Directives\9.3 Field Leadership.doc | Policy Manual, 7.2.4 Foreman | C:\Documents\Policy Manual\Job Descriptions\7.2.4 Foreman.doc
General Foreman | Policy Manual, 9.3 Field Leadership | C:\Documents\Policy Manual\Management Directives\9.3 Field Leadership.doc | Policy Manual, 7.2.5 General Foreman | C:\Documents\Policy Manual\Job Descriptions\7.2.5 General Foreman.doc
Field Supervisor | Policy Manual, 9.4 Field Supervision | C:\Documents\Policy Manual\Management Directives\9.4 Field Supervision.doc | Policy Manual, 7.2.6 Field Supervisor | C:\Documents\Policy Manual\Job Descriptions\7.2.6 Field Supervisor.doc
Superintendent | Policy Manual, 9.4 Superintendents | C:\Documents\Policy Manual\Management Directives\9.4 Superintendents.doc | Policy Manual, 7.2.7 Superintendent | C:\Documents\Policy Manual\Job Descriptions\7.2.7 Superintendent.doc
General Superintendent | Policy Manual, 9.4 General Superintendents | C:\Documents\Policy Manual\Management Directives\9.4 General Superintendents.doc | Policy Manual, 7.2.8 General Superintendent | C:\Documents\Policy Manual\Job Descriptions\7.2.8 General Superintendent.doc
Project Coordinator | Policy Manual, 9.5 Project Management | C:\Documents\Policy Manual\Management Directives\9.5 Project Management.doc | Policy Manual, 7.3.0 Project Coordinator | C:\Documents\Policy Manual\Job Descriptions\7.3.0 Project Coordinator.doc
Project Manager | Policy Manual, 9.5 Project Management | C:\Documents\Policy Manual\Management Directives\9.5 Project Management.doc | Policy Manual, 7.3.1 Project Manager | C:\Documents\Policy Manual\Job Descriptions\7.3.1 Project Manager.doc
Senior Project Manager | Policy Manual, 9.5 Project Management | C:\Documents\Policy Manual\Management Directives\9.5 Project Management.doc | Policy Manual, 7.3.2 Senior Project Manager | C:\Documents\Policy Manual\Job Descriptions\7.3.2 Senior Project Manager.doc
Branch Manager | Policy Manual, 9.6 Branch Management | C:\Documents\Policy Manual\Management Directives\9.6 Branch Management.doc | Policy Manual, 7.4.1 Branch Manager | C:\Documents\Policy Manual\Job Descriptions\7.4.1 Branch Manager.doc
Safety Coordinator | Policy Manual, 9.7 Safety | C:\Documents\Policy Manual\Management Directives\9.7 Safety.doc | Policy Manual, 7.5.1 Safety Coordinator | C:\Documents\Policy Manual\Job Descriptions\7.5.1 Safety Coordinator.doc
Site Administrator | Policy Manual, 9.8 Site Administration | C:\Documents\Policy Manual\Management Directives\9.8 Site Administration.doc | Policy Manual, 7.5.2 Site Administrator | C:\Documents\Policy Manual\Job Descriptions\7.5.2 Site Administrator.doc
Estimator | Policy Manual, 9.9 Estimating | C:\Documents\Policy Manual\Management Directives\9.9 Estimating.doc | Policy Manual, 7.6.1 Estimator | C:\Documents\Policy Manual\Job Descriptions\7.6.1 Estimator.doc
Chief Estimator | Policy Manual, 9.9 Estimating | C:\Documents\Policy Manual\Management Directives\9.9 Estimating.doc | Policy Manual, 7.6.2 Chief Estimator | C:\Documents\Policy Manual\Job Descriptions\7.6.2 Chief Estimator.doc
Purchasing | Policy Manual, 9.10 Purchasing | C:\Documents\Policy Manual\Management Directives\9.10 Purchasing.doc | Policy Manual, 7.6.3 Purchasing Agent | C:\Documents\Policy Manual\Job Descriptions\7.6.3 Purchasing Agent.doc
Purchasing Manager | Policy Manual, 9.10 Purchasing | C:\Documents\Policy Manual\Management Directives\9.10 Purchasing.doc | Policy Manual, 7.6.4 Purchasing Manager | C:\Documents\Policy Manual\Job Descriptions\7.6.4 Purchasing Manager.doc
Accounting | Policy Manual, 9.11 Accounting | C:\Documents\Policy Manual\Management Directives\9.11 Accounting.doc | Policy Manual, 7.7.1 Accounting | C:\Documents\Policy Manual\Job Descriptions\7.7.1 Accounting.doc
Controller | Policy Manual, 9.11 Accounting | C:\Documents\Policy Manual\Management Directives\9.11 Accounting.doc | Policy Manual, 7.7.2 Controller | C:\Documents\Policy Manual\Job Descriptions\7.7.2 Controller.doc
Prefabrication Lead | Policy Manual, 9.12 Prefabrication | C:\Documents\Policy Manual\Management Directives\9.12 Prefabrication.doc | Policy Manual, 7.8.1 Prefab Lead | C:\Documents\Policy Manual\Job Descriptions\7.8.1 Prefab Lead.doc
Quality Inspector | Policy Manual, 9.13 Quality | C:\Documents\Policy Manual\Management Directives\9.13 Quality.doc | Policy Manual, 7.9.1 Quality Inspector | C:\Documents\Policy Manual\Job Descriptions\7.9.1 Quality Inspector.doc

## Coverage Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category
9.2.010 - Team Selection | Selects Project Manager and assigns or approves final team assignments; Allocates resources across projects; Resolves resource conflicts. | Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Identifies required roles and skill sets; Recommends team members; Coordinates with Branch Manager on availability. | Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Validates field leadership assignments; Confirms crew availability and capability | General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Ensures safety-qualified personnel are assigned, Reviews site-specific safety requirements. | Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Informed of procurement resource needs | Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | Informed of prefab support requirements | Prefabrication Lead | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction
9.2.010 - Team Selection | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create List of Issues and Begin RFI Process | Manages overall issue resolution; Prioritizes RFIs; Tracks responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create List of Issues and Begin RFI Process | Creates and submits RFIs; Maintains issue log; Follows up on responses ¦ | ¦ Assistant PM/Project Coordinator | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create List of Issues and Begin RFI Process | Contributes constructability issues; Reviews RFI responses for field impact ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction
9.2.060 - Create List of Issues and Begin RFI Process | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | Coordinates site visit; Documents findings; Integrates into project planning ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | Conducts physical site inspection; Identifies constructability and logistics issues ¦ | ¦ Field Leadership | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | Assesses site safety conditions; Identifies hazards and requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction
9.2.070 - Conduct Site Visit | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction
9.3.010 - Setup Office Trailer | Approves trailer location and configuration; Coordinates delivery timing ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.010 - Setup Office Trailer | Oversees physical setup; Coordinates with delivery vendor; Ensures utility connections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.010 - Setup Office Trailer | Sets up office equipment and supplies; Establishes filing systems ¦ | ¦ Site Administrator | Sec. 9.2 General Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.010 - Setup Office Trailer | Reviews placement for safety compliance; Ensures egress requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.010 - Setup Office Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.020 - Setup Storage Trailer | Oversees setup and organization; Establishes security protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.020 - Setup Storage Trailer | Coordinates physical placement; Organizes interior layout ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.020 - Setup Storage Trailer | Coordinates material delivery timing with storage availability ¦ | ¦ Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.020 - Setup Storage Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.030 - Setup Site Fencing and Access Control | Oversees fencing installation; Establishes access protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.030 - Setup Site Fencing and Access Control | Coordinates installation; Manages gate operations ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.030 - Setup Site Fencing and Access Control | Defines safety requirements; Reviews emergency egress ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.030 - Setup Site Fencing and Access Control | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.040 - Setup Temporary Power | Oversees installation; Ensures code compliance ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.040 - Setup Temporary Power | Installs temporary power system; Makes connections ¦ | ¦ Foreman/Journeyman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.040 - Setup Temporary Power | Reviews safety requirements; Verifies GFCI protection ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.040 - Setup Temporary Power | Coordinates with utility company; Approves power plan ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.3.040 - Setup Temporary Power | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Electrical Subcontractor | Sec. 9.2 General Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup
9.5.010 - Conduct Commissioning Meetings | Leads meeting coordination; Tracks commissioning progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning
9.5.010 - Conduct Commissioning Meetings | Conducts testing; Documents results; Identifies deficiencies ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.010 - Conduct Commissioning Meetings | Supports testing activities; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning
9.5.010 - Conduct Commissioning Meetings | Verifies quality requirements; Reviews test results ¦ | ¦ Quality/QA-QC | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.010 - Conduct Commissioning Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Overall commissioning management; Schedule coordination ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Supports testing; Ensures systems ready; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Executes testing protocols; Documents results ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | Verifies compliance; Reviews documentation ¦ | ¦ Quality/QA-QC | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.5.550 - Manage Commissioning Activities | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning
9.6.010 - Conduct Closeout Meetings | Leads closeout meetings; Tracks closeout progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | Reports field status; Coordinates punch completion ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | Participate; Complete their closeout requirements ¦ | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.010 - Conduct Closeout Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Client/Owner | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | Manages as-built process; Submits final drawings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | Reviews markups for accuracy; Coordinates with field ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | Creates field markups; Documents actual conditions ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.030 - Manage As-Built Drawings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Engineer/APM | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | Oversees review process; Approves action items ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | Leads review meeting; Compiles findings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | Provides field perspective; Shares observations ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.070 - Conduct Post-Project Review | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | Oversees feedback process; Reviews results ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | Conducts feedback meeting; Documents responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | Uses feedback for relationship management ¦ | ¦ Business Development | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.080 - Capture Client Feedback | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Executive Committee | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | Maintains lessons learned database; Ensures implementation ¦ | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | Documents project-specific lessons; Submits for review ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | Captures field-level learnings; Contributes to documentation ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout
9.6.085 - Document Lessons Learned | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout

## RACI Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | RACI
9.2.010 - Team Selection | Selects Project Manager and assigns or approves final team assignments; Allocates resources across projects; Resolves resource conflicts. | Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 2 - Preconstruction | A
9.2.010 - Team Selection | Identifies required roles and skill sets; Recommends team members; Coordinates with Branch Manager on availability. | Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | R
9.2.010 - Team Selection | Validates field leadership assignments; Confirms crew availability and capability | General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.010 - Team Selection | Ensures safety-qualified personnel are assigned, Reviews site-specific safety requirements. | Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.010 - Team Selection | Informed of procurement resource needs | Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 2 - Preconstruction | I
9.2.010 - Team Selection | Informed of prefab support requirements | Prefabrication Lead | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction | I
9.2.010 - Team Selection | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | Project Coordinator | Sec. 9.2 General Directives | Covered | No change required. | 2 - Preconstruction | I
9.2.060 - Create List of Issues and Begin RFI Process | Manages overall issue resolution; Prioritizes RFIs; Tracks responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | A
9.2.060 - Create List of Issues and Begin RFI Process | Creates and submits RFIs; Maintains issue log; Follows up on responses ¦ | ¦ Assistant PM/Project Coordinator | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | R
9.2.060 - Create List of Issues and Begin RFI Process | Contributes constructability issues; Reviews RFI responses for field impact ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction | C
9.2.060 - Create List of Issues and Begin RFI Process | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction | C
9.2.070 - Conduct Site Visit | Coordinates site visit; Documents findings; Integrates into project planning ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 2 - Preconstruction | A
9.2.070 - Conduct Site Visit | Conducts physical site inspection; Identifies constructability and logistics issues ¦ | ¦ Field Leadership | Sec. 9.3 Field Leadership | Covered | No change required. | 2 - Preconstruction | R
9.2.070 - Conduct Site Visit | Assesses site safety conditions; Identifies hazards and requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 2 - Preconstruction | R
9.2.070 - Conduct Site Visit | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 2 - Preconstruction | C
9.3.010 - Setup Office Trailer | Approves trailer location and configuration; Coordinates delivery timing ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | A
9.3.010 - Setup Office Trailer | Oversees physical setup; Coordinates with delivery vendor; Ensures utility connections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup | R
9.3.010 - Setup Office Trailer | Sets up office equipment and supplies; Establishes filing systems ¦ | ¦ Site Administrator | Sec. 9.2 General Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | R
9.3.010 - Setup Office Trailer | Reviews placement for safety compliance; Ensures egress requirements ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | C
9.3.010 - Setup Office Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ General Superintendent | Sec. 9.4 Superintendent Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | C
9.3.020 - Setup Storage Trailer | Oversees setup and organization; Establishes security protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup | A
9.3.020 - Setup Storage Trailer | Coordinates physical placement; Organizes interior layout ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup | R
9.3.020 - Setup Storage Trailer | Coordinates material delivery timing with storage availability ¦ | ¦ Purchasing | Sec. 9.10 Purchasing Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | C
9.3.020 - Setup Storage Trailer | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | C
9.3.030 - Setup Site Fencing and Access Control | Oversees fencing installation; Establishes access protocols ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup | A
9.3.030 - Setup Site Fencing and Access Control | Coordinates installation; Manages gate operations ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup | R
9.3.030 - Setup Site Fencing and Access Control | Defines safety requirements; Reviews emergency egress ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | R
9.3.030 - Setup Site Fencing and Access Control | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | C
9.3.040 - Setup Temporary Power | Oversees installation; Ensures code compliance ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup | A
9.3.040 - Setup Temporary Power | Installs temporary power system; Makes connections ¦ | ¦ Foreman/Journeyman | Sec. 9.3 Field Leadership | Covered | No change required. | 3 - Mobilization & Job Site Setup | R
9.3.040 - Setup Temporary Power | Reviews safety requirements; Verifies GFCI protection ¦ | ¦ Safety Coordinator | Sec. 9.7 Safety Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | C
9.3.040 - Setup Temporary Power | Coordinates with utility company; Approves power plan ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | C
9.3.040 - Setup Temporary Power | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Electrical Subcontractor | Sec. 9.2 General Directives | Covered | No change required. | 3 - Mobilization & Job Site Setup | R
9.5.010 - Conduct Commissioning Meetings | Leads meeting coordination; Tracks commissioning progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning | A
9.5.010 - Conduct Commissioning Meetings | Conducts testing; Documents results; Identifies deficiencies ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.010 - Conduct Commissioning Meetings | Supports testing activities; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning | R
9.5.010 - Conduct Commissioning Meetings | Verifies quality requirements; Reviews test results ¦ | ¦ Quality/QA-QC | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | C
9.5.010 - Conduct Commissioning Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | Overall commissioning management; Schedule coordination ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 5 - Commissioning | A
9.5.550 - Manage Commissioning Activities | Supports testing; Ensures systems ready; Coordinates corrections ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | Executes testing protocols; Documents results ¦ | ¦ Commissioning Agent | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | Verifies compliance; Reviews documentation ¦ | ¦ Quality/QA-QC | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.5.550 - Manage Commissioning Activities | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 5 - Commissioning | R
9.6.010 - Conduct Closeout Meetings | Leads closeout meetings; Tracks closeout progress ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | A
9.6.010 - Conduct Closeout Meetings | Reports field status; Coordinates punch completion ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.010 - Conduct Closeout Meetings | Participate; Complete their closeout requirements ¦ | ¦ Subcontractors | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | R
9.6.010 - Conduct Closeout Meetings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Client/Owner | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | I
9.6.030 - Manage As-Built Drawings | Manages as-built process; Submits final drawings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | A
9.6.030 - Manage As-Built Drawings | Reviews markups for accuracy; Coordinates with field ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.030 - Manage As-Built Drawings | Creates field markups; Documents actual conditions ¦ | ¦ Foreman | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.030 - Manage As-Built Drawings | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Project Engineer/APM | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.070 - Conduct Post-Project Review | Oversees review process; Approves action items ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout | A
9.6.070 - Conduct Post-Project Review | Leads review meeting; Compiles findings ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.070 - Conduct Post-Project Review | Provides field perspective; Shares observations ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.070 - Conduct Post-Project Review | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | C
9.6.080 - Capture Client Feedback | Oversees feedback process; Reviews results ¦ | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout | A
9.6.080 - Capture Client Feedback | Conducts feedback meeting; Documents responses ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.080 - Capture Client Feedback | Uses feedback for relationship management ¦ | ¦ Business Development | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | C
9.6.080 - Capture Client Feedback | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Executive Committee | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | I
9.6.085 - Document Lessons Learned | Maintains lessons learned database; Ensures implementation ¦ | ¦ Operations Manager | Sec. 9.2 General Directives | Covered | No change required. | 6 - Closeout | A
9.6.085 - Document Lessons Learned | Documents project-specific lessons; Submits for review ¦ | ¦ Project Manager | Sec. 9.5 PM Directives | Covered | No change required. | 6 - Closeout | R
9.6.085 - Document Lessons Learned | Captures field-level learnings; Contributes to documentation ¦ | ¦ Field Supervisor | Sec. 9.3 Field Leadership | Covered | No change required. | 6 - Closeout | R
9.6.085 - Document Lessons Learned | ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed | ¦ Branch Manager | Sec. 9.6 Branch Management | Covered | No change required. | 6 - Closeout | C

## Redline Recs
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | Redline Proposal
To be populated | Gap analysis pending | - | - | Gap - TBD | Review required | - | Amendment pending review

## Conflict Matrix
SOP Title | Conflict Description | Conflict Type | Resolution Recommendation
To be populated | Conflict analysis pending | TBD | Review required

## Closeout Checklist
Role | Closeout Task | Directive Section | Coverage Status
¦ Project Manager | Conduct Closeout Meetings: Leads closeout meetings; Tracks closeout progress ¦... | Sec. 9.6 Closeout | Covered
¦ Field Supervisor | Conduct Closeout Meetings: Reports field status; Coordinates punch completion ¦... | Sec. 9.6 Closeout | Covered
¦ Subcontractors | Conduct Closeout Meetings: Participate; Complete their closeout requirements ¦... | Sec. 9.6 Closeout | Covered
¦ Project Manager | Manage As-Built Drawings: Manages as-built process; Submits final drawings ¦... | Sec. 9.6 Closeout | Covered
¦ Field Supervisor | Manage As-Built Drawings: Reviews markups for accuracy; Coordinates with field ¦... | Sec. 9.6 Closeout | Covered
¦ Foreman | Manage As-Built Drawings: Creates field markups; Documents actual conditions ¦... | Sec. 9.6 Closeout | Covered
¦ Project Engineer/APM | Manage As-Built Drawings: ¦ RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed... | Sec. 9.6 Closeout | Covered
¦ Branch Manager | Conduct Post-Project Review: Oversees review process; Approves action items ¦... | Sec. 9.6 Closeout | Covered
¦ Project Manager | Conduct Post-Project Review: Leads review meeting; Compiles findings ¦... | Sec. 9.6 Closeout | Covered
¦ Field Supervisor | Conduct Post-Project Review: Provides field perspective; Shares observations ¦... | Sec. 9.6 Closeout | Covered
¦ Branch Manager | Capture Client Feedback: Oversees feedback process; Reviews results ¦... | Sec. 9.6 Closeout | Covered
¦ Project Manager | Capture Client Feedback: Conducts feedback meeting; Documents responses ¦... | Sec. 9.6 Closeout | Covered
¦ Operations Manager | Document Lessons Learned: Maintains lessons learned database; Ensures implementation ¦... | Sec. 9.6 Closeout | Covered
¦ Project Manager | Document Lessons Learned: Documents project-specific lessons; Submits for review ¦... | Sec. 9.6 Closeout | Covered
¦ Field Supervisor | Document Lessons Learned: Captures field-level learnings; Contributes to documentation ¦... | Sec. 9.6 Closeout | Covered

## Role Alignment Matrix
SOP ID | SOP Title | Phase | Branch Manager | General Superintendent | Prefabrication Lead | Project Coordinator | Project Manager | Purchasing | Safety Coordinator | ¦ Assistant PM/Project Coordinator | ¦ Branch Manager | ¦ Business Development | ¦ Client/Owner | ¦ Commissioning Agent | ¦ Electrical Subcontractor | ¦ Executive Committee | ¦ Field Leadership | ¦ Field Supervisor | ¦ Foreman | ¦ Foreman/Journeyman | ¦ General Superintendent | ¦ Operations Manager | ¦ Project Engineer/APM | ¦ Project Manager | ¦ Purchasing | ¦ Quality/QA-QC | ¦ Safety Coordinator | ¦ Site Administrator | ¦ Subcontractors
9.4.050 | 9.4.050 - Prepare Construction Takeoff | 4 - Execution
9.2.005 | 9.2.005 - Review Contract for Unfavorable or High-Risk Clauses | 2 - Preconstruction
9.2.010 | 9.2.010 - Team Selection | 2 - Preconstruction | A | C | I | I | R | I | C
9.010.41 | 9.010.41 - Project Turnover Meeting | Unknown
9.2.020 | 9.2.020 - Procurement of Large Feeder Wire | 2 - Preconstruction
9.2.030 | 9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | 2 - Preconstruction
9.2.040 | 9.2.040 - Project Manager Reviews Plans, Specifications & Schedule | 2 - Preconstruction
9.2.050 | 9.2.050 - Field Supervisor Reviews Plans, Specifications & Schedule | 2 - Preconstruction
9.4.040 | 9.4.040 - Compare Estimated vs. Planned Performance | 4 - Execution
9.090.41 | 9.090.41 - Prefab Plan Created | Unknown
9.2.060 | 9.2.060 - Create List of Issues and Begin RFI Process | 2 - Preconstruction | [7 empty] | R | [7 empty] | C |  |  | C |  |  | A
9.2.070 | 9.2.070 - Conduct Site Visit | 2 - Preconstruction | [14 empty] | R |  |  |  | C |  |  | A |  |  | R
9.060.41 | 9.060.41 - Prepare Material Handling Plan | Unknown
9.065.41 | 9.065.41 - Develop Labor Budget | Unknown
9.2.100 | 9.2.100 - Prepare Layout & Sequencing Plan | 2 - Preconstruction
9.075.41 | 9.075.41 - Develop Project Schedule | Unknown
9.2.120 | 9.2.120 - Establish Tracking & Control Systems | 2 - Preconstruction
9.085.41 | 9.085.41 - Construction Execution Kickoff Meeting | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.3.010 | 9.3.010 - Setup Office Trailer | 3 - Mobilization & Job Site Setup | [15 empty] | R |  |  | C |  |  | A |  |  | C | R
9.3.020 | 9.3.020 - Setup Storage Trailer | 3 - Mobilization & Job Site Setup | [15 empty] | A | R | [5 empty] | C |  | C
9.3.030 | 9.3.030 - Setup Site Fencing and Access Control | 3 - Mobilization & Job Site Setup | [15 empty] | A | R |  |  |  |  | C |  |  | R
9.3.040 | 9.3.040 - Setup Temporary Power | 3 - Mobilization & Job Site Setup | [12 empty] | R |  |  | A |  | R |  |  |  | C |  |  | C
9.41.110 | 9.41.110 - Setup Temporary Water | Unknown
9.41.115 | 9.41.115 - Setup Sanitary Facilities | Unknown
9.41.120 | 9.41.120 - Setup Temporary Lighting | Unknown
9.41.125 | 9.41.125 - Setup Signage | Unknown
9.41.130 | 9.41.130 - Setup Security | Unknown
9.41.135 | 9.41.135 - Setup Laydown Area | Unknown
9.41.140 | 9.41.140 - Setup Equipment Staging | Unknown
9.41.145 | 9.41.145 - Setup Parking | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.4.020 | 9.4.020 - Conduct Subcontractor Coordination Meetings | 4 - Execution
9.4.030 | 9.4.030 - Conduct Client/Owner Meetings | 4 - Execution
9.4.040 | 9.4.040 - Conduct Safety Meetings | 4 - Execution
9.4.045 | 9.4.045 - Identify Value Engineering & Prefabrication Opportunities | 4 - Execution
9.4.050 | 9.4.050 - Conduct Prefabrication Coordination Meetings | 4 - Execution
9.4.055 | 9.4.055 - 1 Procurement of Large Feeder Wire | 4 - Execution
9.4.060 | 9.4.060 - Conduct Quality Meetings | 4 - Execution
9.4.190A | 9.4.190A - Document Filing Standards | 4 - Execution
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.4.360 | 9.4.360 - Manage Change Orders | 4 - Execution
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.4.631 | 9.4.631 - Release of Large Feeder Wire | 4 - Execution
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.5.010 | 9.5.010 - Conduct Commissioning Meetings | 5 - Commissioning | [11 empty] | R |  |  |  | R | [5 empty] | A |  | C |  |  | R
9.5.550 | 9.5.550 - Manage Commissioning Activities | 5 - Commissioning | [11 empty] | R |  |  |  | R | [5 empty] | A |  | R |  |  | R
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.6.010 | 9.6.010 - Conduct Closeout Meetings | 6 - Closeout | [10 empty] | I |  |  |  |  | R | [5 empty] | A |  |  |  |  | R
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.6.030 | 9.6.030 - Manage As-Built Drawings | 6 - Closeout | [15 empty] | R | R |  |  |  | R | A
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.41.190A | 9.41.190A - Document Filing Standards | Unknown
9.6.070 | 9.6.070 - Conduct Post-Project Review | 6 - Closeout | [8 empty] | A | [6 empty] | R |  |  |  | C |  | R
9.6.080 | 9.6.080 - Capture Client Feedback | 6 - Closeout | [8 empty] | A | C |  |  |  | I | [7 empty] | R
9.6.085 | 9.6.085 - Document Lessons Learned | 6 - Closeout | [8 empty] | C | [6 empty] | R |  |  |  | A |  | R

## SOP Number Crosswalk
Legacy SOP # | New SOP # | Title | SOP Title | Notes
9.41.745 | 9.4.745 | Manage Field Rework | Manage Field Rework | Legacy crosswalk
9.41.190A | 9.4.190 | Document Filing Standards | A Document Filing Standards | Legacy crosswalk
9.4.575 | 9.4.576 | Manage Subcontractor Resources | Manage Subcontractor Resources | Renumbered
9.5.015 | 9.5.020 | Handling Excess Materials | Handling and or Disposing of Excess Materials | Renumbered
9.6.030 | 9.6.035 | Submit Warranties | Submit Warranties | Renumbered
9.6.060 | 9.6.065 | Archive Documentation | Archive Project Documentation | Renumbered

## Change_Log
Timestamp | Sheet | Change Type | Details
2026-01-19T14:43:37.486526 | GSL_SOP_Metadata | Initial Load | Loaded 156 SOPs from Revised SOPs folder
2026-01-19T14:43:37.486535 | Coverage Matrix | Generated | Generated 63 coverage entries from SOP roles
2026-01-19T14:43:37.486537 | RACI Matrix | Generated | Generated 63 RACI entries from SOP roles
2026-01-19T14:43:37.486538 | Role Alignment Matrix | Generated | Mapped 27 unique roles across all SOPs
2026-01-19T14:43:37.486538 | Closeout Checklist | Generated | Extracted closeout tasks from Phase 6 SOPs

## Mapping_Log
Sheet | SOP Title | Source Action | Mapped Action | Role | Source Version | Match Score
GSL_SOP_Metadata | All SOPs | Extracted from Word documents | Purpose, Scope, Roles parsed | Multiple | v8 | 1
Coverage Matrix | All SOPs | RACI roles from documents | Role-Directive mapping | Multiple | v8 | 0.95
Role Alignment Matrix | All SOPs | RACI designations | Role-SOP cross-reference | Multiple | v8 | 1